## Proc.R2011 Nig.Arabic Lang
PROCUREMENT RECORDS
PROCUREMENT ENTITY ;- NIGERIA ARABIC LANGUAGE VILLAGE, NGALA
FINANCIAL YEAR ; 2011
S/N | PROJECT DESCRIPTION | ADVERTISEMENT DATE AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | CONTRACTOR | DATE OF CONTRACT AWARD | DATE OF CONTRACT COMMENCEMENT | CONTRACT PERIOD | CONTRACT VALUE (N) | BUDGETRY PROVISION | AMOUNT PAID AS AT 31/12/2011 | EXPECTED COMPLETION DATE | % OF COMPLETION AS AT 31/12/2011 | 2011 deliverables
2 | Provision of 1 No 700 deep free- flow borehole @ Shagari Staff Quarters. | Federal tenders journal 28/04/2008 | Nigeria arabic language village | Compititive tendering | 14/08/'08 | MIB Ventures Nig. Ltd. | 2/10/'08 | 9/10/'08 | 12-WEEKS | 13265000 | 11465000 |  | 31/03/'12 | 15% | project to be completed with 2011 allocation
3 | Construction of 2No overhead steel water tanks. | Federal tenders journal 28/04/2008 | Nigeria arabic language village | Compititive tendering | 14/08/'08 | Arbedow Nig. Ltd. | 2/10/'08 | 9/10/'08 | 8-WEEKS | 8190000 | 1861000 |  | 31/03/'12 | 90% | project to be completed with 2011 allocation
4 | Construction of 2No underground Concrete tanks. | Federal tenders journal 28/04/2008 | Nigeria arabic language village | Compititive tendering | 14/08/'08 | Sama Construction | 2/10/'08 | 9/10/'08 | 6-WEEKS | 2990000 | 1645000 |  | 31/03/'12 | 50% | project to be completed with 2011 allocation
7 | Solar facilities to student hall D | Federal tenders journal 28/04/2008 | Nigeria arabic language village | Compititive tendering | 14/08/'08 | Attahir Enterprise Ltd. | 2/10/'08 | 9/10/'08 | 4-WEEKS | 14764000 | 3708000 |  | 31/03/'12 | 15% | project to be completed with 2012 allocation
8 | Solar facilities to Village Clinic | Federal tenders journal 28/04/2008 | Nigeria arabic language village | Compititive tendering | 14/08/'08 | Njitta Company Ltd. | 2/10/'08 | 9/10/'08 | 4-WEEKS | 5515000 | 4688000 |  | 31/03/'12 | 15% | project to be completed with 2012 allocation
9 | Construction of Liaison Office IIIA | Federal tenders journal 28/04/2008 | Nigeria arabic language village | Compititive tendering | 14/08/'08 | Falmata Kumshe Nig. Ltd. | 2/10/'08 | 9/10/'08 | 16-WEEKS | 4719000 | 4719000 |  | 31/03/'12 | 80% | project to be completed with 2011 allocation
12 | T & RE II (construction of Computer centre) | Federal tenders journal 28/04/2008 | Nigeria arabic language village | Compititive tendering | 14/08/'08 | Golfa Int'l Ltd. | 2/10/'08 | 9/10/'08 | 21-WEEKS | 13900000 | 695000 | 695000 | completed | 100% | project to be completed with 2011 allocation
13 | T & RE III ( Computer & Accessories) | Federal tenders journal 28/04/2008 | Nigeria arabic language village | Compititive tendering | 14/08/'08 | El-Sediq Nig. Ltd. | 2/10/'08 | 9/10/'08 | 8-WEEKS | 9501000 | 1082000 |  | 31/03/'12 | 90% | project to be completed with 2011 allocation
14 | T & RE IV (Solar Facilities to Computer Centre) | Federal tenders journal 28/04/2008 | Nigeria arabic language village | Compititive tendering | 14/08/'08 | Charts Construction Ltd. | 2/10/'08 | 9/10/'08 | 4-WEEKS | 4861000 | 4132000 | 0 | 31/03/'12 | 15% | project to be completed with 2012 allocation
16 | Teaching and Research Equipment I | Daily trust, champion, ftj & 26/2/2010 | Nigeria arabic language village | Compititive tendering | 15/06/'10 | HILTON IMPORTS LTD | 3/11/'10 | 10/11/'10 | 12-WEEKS | 44368000 | 33253000 | 15160427 | 31/03/'12 | 90% | project to be completed with 2011 allocation
17 | Construction of Male students Hostel Phase I | Daily trust, champion, ftj & 26/2/2010 | Nigeria arabic language village | Compititive tendering | 15/06/'10 | Rofako Int'l Ltd. | 3/11/'10 | 10/11/'10 | 12-WEEKS | 33055000 | 23137000 | 8173165 | 31/03/'12 | 90% | project to be completed with 2011 allocation
18 | Construction of Female students Hostel Phase I | Daily trust, champion, ftj & 26/2/2010 | Nigeria arabic language village | Compititive tendering | 15/06/'10 | Nfans Nig. Ltd. | 3/11/'10 | 10/11/'10 | 12-WEEKS | 33055000 | 23452000 | 9551781 | 31/03/'12 | 95% | project to be completed with 2011 allocation
19 | Rehabilitation (General) | Daily trust, champion, ftj & 26/2/2010 | Nigeria arabic language village | Compititive tendering | 15/06/'10 | D' INOBEST W/A LTD | 3/11/'10 | 10/11/'10 | 4-WEEKS | 3442000 | 2155000 | 2155000 | completed | 100% | project to be completed with 2011 allocation
20 | Plant/Vehicle Phase | Daily trust, champion, ftj & 26/2/2010 | Nigeria arabic language village | Compititive tendering | 15/06/'10 | ELIZADE NIGERIA LTD | 3/11/'10 | 10/11/'10 | 4-WEEKS | 8046000 | 8046000 |  | 31/03/'12 |  | project to be completed with 2011 allocation
| TOTAL:- | [7 empty] | 0 | 199671000 | 124038000 | 35735373

## Proc R2011 Nig.Arabic Lang (hidden)
MEDIUM-TERM MDAs' CAPITAL PROJECTS/PROGRAMMES IMPLEMENTATION PLAN
MDA: NIGERIA ARABIC LANGUAGE VILLAGE, NGALA
S/N | Project Title | Project Status (New/Ongoing) | FEC/MTB/BPP | Project Comformance with |  | Location |  | Date of Contract Award | Contractor | Commencement Date | Estimated Completion Date | Estimated Total Cost | Amount Expended to date | 2011 Budget (Executive Proposal) | Level of Implementation as at December 2010 | Medium-Term Expenditure Plans (₦' millions)
|  |  | Cert. Serial No. | MTSS | 1st NIP | Zone | State |  |  |  |  | ₦ | ₦ | ₦ | % | 2012 | 2013 | 2014
1 | Provision of 1 No 700 deep free flow borehole @ main campus. | Completed (retention) | N/A | Yes |  | NE | Borno | 2/10/'08 | AlKal Nig. Ltd. | 9/10/'08 | 31/12/'10 | 11988900 | 10982359 | 1006541 | 100% | Nil | Nil | Nil
2 | Provision of 1 No 700 deep free flow borehole @ Shagari Staff Quarters. | On-going | N/A | Yes |  | NE | Borno | 2/10/'08 | MIB Ventures Nig. Ltd. | 9/10/'08 | 31/12/'12 | 14119560 | 1810200 | 3311914 | 15% | 8997446 | Nil | Nil
3 | Construction of 2No overhead steel water tanks. | On-going | N/A | Yes |  | NE | Borno | 2/10/'08 | Arbedow Nig. Ltd. | 9/10/'08 | 1/07/'11 | 8500000 | 6456388 | 2043612 | 76% | Nil | Nil | Nil
4 | Construction of 2No underground Concrete tanks. | On-going | N/A | Yes |  | NE | Borno | 2/10/'08 | Sama Construction | 9/10/'08 | 30/06/'12 | 3500000 | 1257411 | 820709 | 36% | 1421880 | Nil | Nil
5 | Construction of staff school phase 1 | Completed (retention) | N/A | Yes |  | NE | Borno | 2/10/'08 | Rofako Int'l Ltd. | 9/10/'08 | 31/12/'10 | 18452705.4 | 16963073 | 1489632 | 100% | Nil | Nil | Nil
6 | Furniture to staff school | Completed (retention) | N/A | Yes |  | NE | Borno | 2/10/'08 | Nfans Nig. Ltd. | 9/10/'08 | 31/11/'10 | 5048175.5 | 4582522 | 465353 | 100% | Nil | Nil | Nil
7 | Solar facilities to student hall D | On-going | N/A | Yes |  | NE | Borno | 2/10/'08 | Attahir Enterprise Ltd. | 9/10/'08 | 30/10/'12 | 6618480 | 827310 | 1513822 | 15% | 4277348 | Nil | Nil
8 | Solar facilities to Village Clinic | On-going | N/A | Yes |  | NE | Borno | 2/10/'08 | Njitta Company Ltd. | 9/10/'08 | 30/10/'12 | 5662800 | - | 1523803 | 0% | 4138997 | Nil | Nil
9 | Construction of Liaison Office IIIA | On-going | N/A | Yes |  | NE | Borno | 2/10/'08 | Falmata Kumshe Nig. Ltd. | 9/10/'08 | 30/03/'12 | 16866467 | 10541541 | 1099551 | 63% | 5225375 | Nil | Nil
10 | Construction of Liaison Office IIIB (furniture) | On-going | N/A | Yes |  | NE | Borno | 2/10/'08 | Nfans Nig. Ltd. | 9/10/'08 | 30/04/'12 | 11870820 | - | 3194319 | 0% | 8676501 | Nil | Nil
11 | T & RE I (construction of language resource centre) | Completed (retention) | N/A | Yes |  | NE | Borno | 2/10/'08 | Njitta Company Ltd. | 9/10/'08 | 31/12/'10 | 14330735 | 13682462 | 648273 | 100% | Nil | Nil | Nil
12 | T & RE II (construction of Computer centre) | Completed (retention) | N/A | Yes |  | NE | Borno | 2/10/'08 | Golfa Int'l Ltd. | 9/10/'08 | 31/12/'10 | 13899804.5 | 13226551 | 673253 | 100% | Nil | Nil | Nil
13 | T & RE III ( Computer & Accessories) | On-going | N/A | Yes |  | NE | Borno | 2/10/'08 | El-Sediq Nig. Ltd. | 9/10/'08 | 31/12/'11 | 9976227 | 8419169 | 349386 | 84% | 1207672 | Nil | Nil
14 | T & RE IV (Solar Facilities to Computer Centre) | On-going | N/A | Yes |  | NE | Borno | 2/10/'08 | Charts Construction Ltd. | 9/10/'08 | 31/07/'12 | 5833092 | 729136.5 | 1334184 | 15% | 3769772 | Nil | Nil
15 | T & RE V (Furniture & Equipment to Computer Centre) | Completed (retention) | N/A | Yes |  | NE | Borno | 2/10/'08 | AAM Global Nig. Ltd. | 9/10/'08 | 15/12/'10 | 8694200 | 7700709 | 993491 | 100% | Nil | Nil | Nil
16 | Teaching and Research Equipment I | On-going | N/A | Yes |  | NE | Borno | 3/11/'10 | HILTON IMPORTS LTD | 10/11/'10 | 31/12/'12 | 44367656 | 10440000 | 14465970 | 24% | 19451686 | Nil | Nil
17 | Construction of Male Hostel Phase I | On-going | N/A | Yes |  | NE | Borno | 3/11/'10 | Rofako Int'l Ltd. | 10/11/'10 | 31/12/'12 | 36360918 | 9889669.01 | 10673847 | 27% | 15797402 | Nil | Nil
18 | Construction of Female Hostel Phase I | On-going | N/A | Yes |  | NE | Borno | 3/11/'10 | Nfans Nig. Ltd. | 10/11/'10 | 31/12/'12 | 36360918 | 9889669.01 | 10673847 | 27% | 15797402 | Nil | Nil
19 | Rehabilitation (General) | On-going | N/A | Yes |  | NE | Borno | 3/11/'10 | D' INOBEST W/A LTD | 10/11/'10 | 31/12/'11 | 3207810 | 1530050 | 1427062 | 48% | Nil | Nil | Nil
20 | Plant/Vehicle Phase | On-going | N/A | Yes |  | NE | Borno | 3/11/'10 | KWAPCHI NIG. LTD | 10/11/'10 | 31/02/'12 | 8046000 | Nil | 3701160 | 0% | 4344840 | Nil | Nil
21 | Solar Facilities to Hall A | On-going | N/A | Yes |  | NE | Borno | 3/11/'10 | Kulogumna Elect. Serv. Ltd. | 10/11/'10 | 31/02/'12 | 5957945 | U | 1801866 | 0% | 4156079 | Nil | Nil
22 | Construction of Male Hostel Phase II | New | - | Yes |  | NE | Borno | - | - | 10/10/'11 | 31/12/'12 | 38560918 | Nil | 23993468 | - | 14567450 | Nil | Nil
23 | Construction of Female Hostel Phase II | New | - | Yes |  | NE | Borno | - | - | 10/10/'11 | 31/12/'11 | 34180000 | Nil | 34180000 | -
24 | Plant/Vehicle Phase I | New | - | Yes |  | NE | Borno | - | - | 10/10/'11 | 30/09/'12 | 9526000 | Nil | 5265506 | - | 4260494 | Nil | Nil
25 | Rehabilitation (Solar Facilities) | New | - | Yes |  | NE | Borno | - | - | 10/10/'11 | 31/12/'12 | 20526000 | Nil | 9624764 | - | 10901236 | Nil | Nil
26 | Master Plan | New | - | Yes |  | NE | Borno | - | - | 10/10/'11 | 31/08/'12 | 15000000 | Nil | 5763206 | - | 9236794 | Nil | Nil
27 | Rehabilitation (Existing Facilities) | New | - | Yes |  | NE | Borno | - | - | 10/07/'12 | 31/12/'14 | 46896223 | Nil | Nil | - | 26285223 | Nil | 20611000
28 | Teaching and Research Equipment II | New | - | Yes |  | NE | Borno | - | - | 10/08/'13 | 31/12/'14 | 115224000 | Nil | Nil | - | Nil | 54612000 | 60612000
29 | Construction of Male Hostel Phase III | New | - | Yes |  | NE | Borno | - | - | 10/08/'13 | 31/12/'13 | 39,811.000.00 | Nil | Nil | - | Nil | 39811000 | Nil
30 | Construction of Female Hostel Phase III | New | - | Yes |  | NE | Borno | - | - | 10/08/'13 | 31/12/'13 | 39,811.000.00 | Nil | Nil | - | Nil | 39811000 | Nil
31 | Construction of staff school phase II | New | - | Yes |  | NE | Borno | - | - | 10/08/'13 | 31/12/'13 | 28500000 | Nil | Nil | - | Nil | 28500000 | Nil
32 | Construction of Students' Centre | New | - | Yes |  | NE | Borno | - | - | 10/08/'14 | 31/12/'14 | 40000539 | Nil | Nil | - | Nil | Nil | 40000539
33 | Construction of Director's Lodge | New | - | Yes |  | NE | Borno | - | - | 10/09/'13 | 30/11/'13 | 19304539 | Nil | Nil | - | Nil | 19304539 | Nil
34 | Road and Drainages | New | - | Yes |  | NE | Borno | - | - | 08/10/'14 | 31/12/'15 | 80815000 | Nil | Nil | - | Nil | Nil | 80815000
| TOTAL:- | [10 empty] | 738196432.4 | 128928219.52 | 142038539 |  | 162513597 | 182038539 | 202038539

## EFCC 2011 P.R
EFCC 2011 PROCUREMENT RECORD
`S/N | CONTRACT DESCRIPTION | ADVERTISEMENT DATE AND MEDIA | APPROVAL THRESHOLD | BID OPENING DATE | CONTRACTOR | DATE OF CONTRACT AWARD | DATE OF CONTRACT COMMENCEMENT | CONTRACT PERIOD | CONTRACT VALUE | BUDGETARY PROVISION | AMOUNT PAID AS AT | EXPECTED COMPLETION DATE | % COMPLETION AS AT | REMARKS
1 | Production of handbook "Doing business in Nigeria" | Nil | Executive Chairman | Nil | Rings & Favolit Limited | 14 - 04 - 2011 | 15 - 04 - 2011 | 2 Weeks | 1700000 |  | 1700000 | 28 - 04 - 2011 | 100% | Satisfactory
2 | Clearing of Exhibit Park, Port-Harcourt | Nil | Executive Chairman | Nil | Definite Systems Limited | 28 - 04 - 2011 | 2011-02-05 | 1 Week | 1363530 |  | 1363530 | 2011-06-05 | 100% | Satisfactory
3 | Supply of IT Equipment | Nil | Executive Chairman | Nil | Abson Business World Limited | 24 - 05 - 2011 | 25 - 05 - 2011 | 2 Weeks | 820000 |  | 820000 | 2011-07-06 | 100% | Satisfactory
4 | Fumigation of Wuse II Offices | Nil | Executive Chairman | Nil | Kwem Jieh Nigeria Limited | 23 - 05 - 2011 | 24 - 05 - 2011 | 1 Week | 294000 |  | 294000 | 30 - 05 - 2011 | 100% | Satisfactory
5 | Provision of Internet Broadband Solution | Nil | PTB | Nil | Intercarrier comm/Layer 3 Ltd | 2011-10-06 | 13 - 06 - 2011 | 1 Month | 26848000 |  | 26848000 | 2011-08-07 | 100% | Satisfactory
6 | 5 Years Strategic Plan for the Commission | Nil | PTB | Nil | Felikedi Multiventures Limited | 2011-04-05 | 2011-05-05 | 3 Months | 4500000 |  | 4500000 | 2011-09-08 | 100% | Satisfactory
7 | Provision of 5Tonne Power Supply at TRI, Karu | Nil | Executive Chairman | Nil | NAS Electrical Services | 16 - 06 - 2011 | 17 - 06 - 2011 | 2 Weeks | 1857440 |  | 1857440 | 30 - 06 - 2011 | 100% | Satisfactory
8 | Fumigation of Wuse II Offices | Nil | Executive Chairman | Nil | Yemokeen Ventures Limited | 2011-06-07 | 2011-07-07 | 1 Week | 370000 |  | 370000 | 13 - 07 - 2011 | 100% | Satisfactory
9 | Constuction of Overhead Water Tank, Wuse II, Office | Nil | PTB | Nil | Mahad & Assoc. Engr Limited | 20 - 07 - 2011 | 22 - 07 - 2011 | 1 Month | 3447150 |  | 3477150 | 19 - 08 - 2011 | 100% | Satisfactory
10 | Supply & Installation of Cool Cover Car Port | Nil | Executive Chairman | Nil | Touch Seals Limited | 2011-03-08 | 2011-04-08 | 1 Week | 480000 |  | 480000 | 2011-10-08 | 100% | Satisfactory
11 | Supply of Forensic Consumables | Nil | Executive Chairman | Nil | Giant Services Limited | 29 - 08 - 2011 | 30 - 08 - 2011 | 2 Weeks | 756000 |  | 756000 | 2011-12-09 | 100% | Satisfactory
12 | Supply of Rain Coats/ Boots | Nil | Executive Chairman | Nil | D.C. Morgan Global Limited | 29 - 08 - 2011 | 30 - 08 - 2011 | 2 Weeks | 1362000 |  | 1362000 | 2011-12-09 | 100% | Satisfactory
13 | Supply & Installation of UPS Batteries | Nil | Executive Chairman | Nil | Shakotech Services | 2011-06-09 | 2011-07-09 | 1 Week | 1993950 |  | 1993950 | 13 - 09 - 2011 | 100% | Satisfactory
14 | Activation of 200 KVA Transformer | Nil | Executive Chairman | Nil | S.C. Ventures Nigeria Limited | 2011-12-09 | 13 - 09 - 2011 | 2 Weeks | 1714125 |  | 1714125 | 26 - 09 - 2011 | 100% | Satisfactory
15 | Supply and Installation of ICT Equipment | Federal Tenders Journal + Two National Dailies | PTB |  | Whitney Communications Ltd | 30 - 12 - 2011 | 30 - 12 - 2011 | 1 Month | 48809365.82 |  | 48809365.82 | 30 - 01 - 2012 | 100% | Satisfactory
16 | Supply and Installation of Metro Network | Federal Tenders Journal + Two National Dailies | PTB |  | Intercarrier comm/Layer 3 Ltd | 30 - 12 - 2011 | 30 - 12 - 2011 | 1 Month | 31306800 |  | 31306800 | 30 - 01 - 2012 | 100% | Satisfactory
17 | Supply of Bullet Proof Vest/ Metal Detector | Federal Tenders Journal + Two National Dailies | PTB |  | Century Trust Limited | 30 - 12 - 2011 | 30 - 12 - 2011 | 1 Month | 9250000 |  | 9250000 | 30 - 01 - 2012 | 100% | Satisfactory
18 | Supply of Motor Vehicle Tyres | Federal Tenders Journal + Two National Dailies | PTB |  | Stac Nigeria Limited | 30 - 12 - 2011 | 30 - 12 - 2011 | 1 Month | 13473873 |  | 13473873 | 30 - 01 - 2012 | 100% | Satisfactory
19 | Construction of Port Harcourt Office Block | Federal Tenders Journal + Two National Dailies | PTB |  | Omarcwhite Nigeria Limited | 30 - 12 - 2011 | 30 - 12 - 2011 | 1 Month | 89364150.75 |  | 89364150.75 | 30 - 01 - 2012 | 100% | Satisfactory
20 | Variation Order | On-going Project | PTB |  | Man-Manu Nigeria Limited | 30 - 12 - 2011 | 30 - 12 - 2011 | 1 Month | 1060019.1 |  | 1060019.1 |  | 100% | Satisfactory
21 | Supply and Installation of 165KVA Genenrator | Federal Tenders Journal + Two National Dailies | PTB |  | JMG | 30 - 12 - 2011 | 30 - 12 - 2011 | 1 Month | 5302341.6 |  | 5302341.6 | 30 - 01 - 2012 | 100% | Satisfactory
22 | Supply and installation of Conference Table/Chair | Federal Tenders Journal + Two National Dailies | PTB |  | Fritz Communications Limited | 30 - 12 - 2011 | 30 - 12 - 2011 | 1 Month | 47230000 |  | 47230000 | 30 - 01 - 2012 | 100% | Satisfactory
23 | Supply of Lagos Office Furniture | Federal Tenders Journal + Two National Dailies | PTB |  | Patike Communications | 30 - 12 - 2011 | 30 - 12 - 2011 | 1 Month | 29507100 |  | 29507100 | 30 - 01 - 2012 | 100% | Satisfactory
24 | Supply of TOYOTA Hiace Buses | Federal Tenders Journal + Two National Dailies | PTB |  | Lanre Shittu | 30 - 12 - 2011 | 30 - 12 - 2011 | 1 Month | 92334000 |  | 92334000 | 30 - 01 - 2012 | 100% | Satisfactory
415143845.27

## 2011 P.R SGF
OFFICE OF THE SECRETARY TO THE GOVERNMENT OF THE FEDERATION
2011 PROCUREMENT RECORDS
SECTION 1 : RECORD OF PROCUREMENTS
PART 1 : PROCUREMENTS FROM THE OSGF CAPITAL APPROPRIATION
SN | NATURE OF CONTRACT | TYPE OF PROC. | NAME OF CONTRACTOR | VALUE OF CONTRACT | VARIATION | APPROVING AUTHORITY | DATE OF AWARD | REMARKS
1 | Reconfiguration of the Basement of Shehu Shagari Complex, Abuja | WORKS | JAMEC West Africa Limited | 87666100 | NIL | Ministerial Tenders Board | 2011-09-27 | Completed and paid
2 | Completion of Clinic Building at the Shehu Shagari Complex, Abuja | WORKS | Obis Associates Nigeria Ltd | 91930361.25 | NIL | Ministerial Tenders Board | 2011-09-27 | Completed and paid
3 | Construction of Concrete Car Ports at the Shehu Shagari Complex, Abuja | WORKS | Craft Offshore International Limited | 27963104 | NIL | Ministerial Tenders Board | 2011-09-27 | Completed and paid
4 | Design, Develop and Implement an Oracle Based e-Participation System | WORKS | Messrs Wetinbe Nigeria Limited | 9596157 | NIL | Ministerial Tenders Board | 2011-09-27 | On-Going
5, | Upgrading of Electrical/Mechanical Equipment in Shehu Shagari Complex | WORKS | Amedu’s Integrated Services Limited | 30193000 | NIL | Ministerial Tenders Board | 2011-11-09 | Completed and paid
6 | Supply of Server Blade Enclosure, SAN Hard Drive Upgrade and Server Room Preparation | GOODS | Messrs Network Data Services and Technologies Ltd | 9660000 | NIL | Ministerial Tenders Board | 2011-12-15 | Completed and paid
7 | Upgrading of Electrical Components at the Federal Secretariat Phase 1, Abuja | WORKS | Multi Dimensions Concept Nigeria Limited | 23972404.48 | NIL | Ministerial Tenders Board | 2011-12-29 | On-Going
280981126.73
PART 2 : PROCUREMENT PROCESSED FOR SPECIAL DUTIES OFFICE
SN | NATURE OF CONTRACT | TYPE OF PROC. | NAME OF CONTRACTOR | VALUE OF CONTRACT | VARIATION | APPROVING AUTHORITY | DATE OF AWARD | REMARKS
1 | Establishment of Virtual/E-Library, Web Content Management System and Complementary Facilities at the Special Duties Office | WORKS | A.A.C Consulting Ltd | 11823000 | NIL | MINISTERIAL TENDERS BOARD | 2011-11-24 | Completed and paid
292804126.73
PART 3 : PROCUREMENTS PROCESSED FOR ECOLOGICAL FUND OFFICE
SN | NATURE OF CONTRACT | TYPE OF PROC. | NAME OF CONTRACTOR | VALUE OF CONTRACT | VARIATION | APPROVING AUTHORITY | DATE OF AWARD | REMARKS
1 | Supply of 4 Nos. Toyota Prado Jeeps 4.0 Lt V6 Petrol Engine, Full Option, 4-Speed Auto Trans, Leather Seats, Tinted Glass and Wood Finish for Ecological Fund Office. |  | Elizade Motors | 62370000 | NIL | Ministerial Tenders Board | 2011-09-27 | Completed and paid
2 | Supply of 2 Nos. 2.0 Lt Petrol Engine Avensis Salon Cars, Auto Full Option, Leather Seats etc (N6,289,500 each) and 1 No. Toyota Hilux High Speed Manual Trans 2.7 Lt Petrol Engine, 4WD, Double Cabin, AC etc (N4,882,500) for Ecological Fund Office. |  | Elizade Motors | 17461500 | NIL | Ministerial Tenders Board | 2011-09-27 | Completed and paid
3 | Conduct of Ecological Consciousness (Television). |  | Charlesflory Limited | 41651850 | NIL | Ministerial Tenders Board | 2011-09-27 | On-Going
4 | The Green Agenda. |  | Macro Investment Limited | 22290615.78 | NIL | Ministerial Tenders Board | 2011-09-27 | On-Going
5, | Rendering Help Where Needed/Responsible Citizenship (Print Media).. |  | The Movie House | 19353951 | NIL | Ministerial Tenders Board | 2011-09-27 | On-Going
163127916.78
PART 4 : PROCUREMENTS PROCESSED FOR FEDERAL GOVERNMENT INVESTIGATION PANEL ON ELECTION VIOLENCE AND CIVIL DISTURBANCES
SN | NATURE OF CONTRACT | TYPE OF PROC. | NAME OF CONTRACTOR | VALUE OF CONTRACT | VARIATION | APPROVING AUTHORITY | DATE OF AWARD | REMARKS
1 | Supply of 1 No. Peugeot 407 Classic Extra 2.0 Petrol Engine for Federal Government Investigation panel on Election Violence and Civil Disturbances. | GOODS | A.C. Okocha Motors Ltd | N6,695,425.00 | NIL | Ministerial Tenders Board | 2011-07-04 | Completed and paid
2 | Supply of Two Toyota Landcruiser Prado Jeeps VXL 4.0 L Petrol Engine, Automatic Transmission, Reverse Camera, Leather Seats, Cool Box (Fridge), CD AND DVD Player, Airbags/Full Option for Federal Government Investigation panel on Election Violence and Civil Disturbances. | GOODS | Ineh-Mic Automobile Co. Ltd | N30,870,000.00 | NIL | Ministerial Tenders Board | 2011-07-04 | Completed and paid
PART 5 : PROCUREMENT PROCESSED FOR CHIEF ECONOMIC ADVISER TO THE PESIDENT
SN | NATURE OF CONTRACT | TYPE OF PROC. | NAME OF CONTRACTOR | VALUE OF CONTRACT | VARIATION | APPROVING AUTHORITY | DATE OF AWARD | REMARKS
1 | Supply, Installation and One Year Maintenance of 1 No 100KVA/80KW415/240V 1500RPM Perkins Soundproof Generator and 6,000 Litres Diesel Storage Tank (Office of Chief Economic Adviser to President) | GOODS | Zukhruf Nigeria Limited | N11,760,000.00 | NIL | Ministerial Tenders Board | 2011-11-25 | Completed and paid
PART 6 : PROCUREMENTS PROCESSED FOR PRESIDENTIAL TECHNICAL COMMITTEE ON LAND REFORM (PTCLR)
SN | NATURE OF CONTRACT | TYPE OF PROC. | NAME OF CONTRACTOR | VALUE OF CONTRACT | VARIATION | APPROVING AUTHORITY | DATE OF AWARD | REMARKS
1 | Construction of 1 Nos. Continuously Operating Reference Station (CORS) in Akure | WORKS | Babatunde Allo and Associates Ltd | N23,581,100.00 | NIL | MINISTERIAL TENDERS BOARD | 2011-12-15 | On-Going
2 | Construction of 1 Nos. Continuously Operating Reference Station (CORS) in Katsina. | WORKS | Corporate Surveys Ltd | N23,581,100.00 | NIL | MINISTERIAL TENDERS BOARD | 2011-12-15 | On-Going
SECTION 2 : RECORD OF PROCUREMENT PROCEEDINGS
PROJECT : RECONFIGURATION OF THE BASEMENT OF SHEHU SHAGARI COMPLEX, ABUJA
SN | RESPONSIVE BIDS RECEIVED | AMOUNT QUOTED |  | TECHNICAL EVALUATION SCORES (%) |  |  | DATE BIDS WERE AVALUATED |  | DATE PRESENTED TO PPC |  |  | DATE MTB GAVE APPROVAL |  |  | MOST RESPONSIVE AND RECOMMENDED BID |  | DATE OF CONTRACT AWARD
1 | CIN Ltd | N49,259,066.00 |  | 65 |  |  | 2011-09-08 |  | 2011-09-15 |  |  | 2011-09-16 |  |  | JAMEC Nig. Ltd. |  | 2011-09-27
2 | Drank Nig. Ltd. | N32,074,500.00 |  | 80
3 | Ometra Const. Engs Ltd | N44,934,334.20 |  | 75 | [10 empty] | The quotations from the other companies were found most unreasonable in relation to the in-house estimate of N93,409,593.00
4 | Jamec Nig. Ltd. | N87,666,100.00 |  | 80
PROJECT : COMPLETION OF CLINIC BUILDING AT THE SHEHU SHAGARI COMPLEX, ABUJA
SN | RESPONSIVE BIDS RECEIVED | AMOUNT QUOTED |  | TECHNICAL EVALUATION SCORES (%) |  |  | DATE BIDS WERE AVALUATED |  | DATE PRESENTED TO PPC |  |  | DATE MTB GAVE APPROVAL |  |  | MOST RESPONSIVE AND RECOMMENDED BID |  | DATE OF CONTRACT AWARD
1 | Tee Square Rock Consult | N28,341,250.00 |  | 70 |  |  | 2011-09-08 |  | 2011-09-15 |  |  | 2011-09-16 |  |  | Obis Associates Nig. Ltd. |  | 2011-09-27
2 | Major Energy Ltd | N36,282,671.20 |  | 75
3 | Emabel Industrial Coy Ltd. | N48,414,625.00 |  | 65 | [10 empty] | The quotations from the other companies were found most unreasonable in relation to the in-house estimate of N95,873,405.00
4 | Don Tech. Nig. Ltd. | N41,657,492.00 |  | 60
5, | 21 Flavors Ltd. | N10,350,000.00 |  | 60
6 | Ometra Const. Engrs | N37,739,066.40 |  | 75
7 | Sha-Fill Investment Ltd. | N45,573,670.50 |  | 80
8 | TMCH Group Ltd | N35,150,595.00 |  | 85
9 | Obis Associates Nig. Ltd. | N91,930,361.25 |  | 90
10 | Forefront Founders Nig. Ltd. | N40,277,632.50 |  | 80
PROJECT : CONSTRUCTION OF CONCRETE CAR PORTS AT THE SHEHU SHAGARI COMPLEX, ABUJA
SN | RESPONSIVE BIDS RECEIVED | AMOUNT QUOTED |  | TECHNICAL EVALUATION SCORES (%) |  |  | DATE BIDS WERE AVALUATED |  | DATE PRESENTED TO PPC |  |  | DATE MTB GAVE APPROVAL |  |  | MOST RESPONSIVE AND RECOMMENDED BID |  | DATE OF CONTRACT AWARD
1 | NIC. Angus (WA) Ltd | N33,870,116.28 |  | 65 |  |  | 2011-09-08 |  | 2011-09-15 |  |  | 2011-09-16 |  |  | Craft Offshore Inter. Ltd. |  | 2011-09-27
2 | DON Tech. Ltd. | N31,105,752.63 |  | 80
3 | El Shammah VenturesLtd. | N21,993,193.37 |  | 65 | [10 empty] | The quotations from the other companies were found either much higher or lower in relation to the in-house estimate of N28,785,954.00
4 | Ravegos Cont. Proj. Ltd. | N14,455,073.69 |  | 70
5, | Glocordial Investment Ltd. | N32,805,466.11 |  | 75
6 | Oplafas Nig. Ltd. | N14,089,499.00 |  | 75
7 | De Califf Investment Nig. Ltd. | N39,485,706.00 |  | 80
8 | Craft Offshore Inter. Ltd. | N27,963,104.00 |  | 95
PROJECT : DESIGN, DEVELOP AND IMPLEMENT AN ORACLE BASED E-PARTICIPATION SYSTEM
SN | RESPONSIVE BIDS RECEIVED | AMOUNT QUOTED |  | TECHNICAL EVALUATION SCORES (%) |  |  | DATE BIDS WERE AVALUATED |  | DATE PRESENTED TO PPC |  |  | DATE MTB GAVE APPROVAL |  |  | MOST RESPONSIVE AND RECOMMENDED BID |  | DATE OF CONTRACT AWARD
1 | Wetinbe Nig. Ltd. | N9,596,157.00 |  | 95 |  |  | 2011-09-08 |  | 2011-09-15 |  |  | 2011-09-16 |  |  | Wetinbe Nig. Ltd. |  | 2011-09-27
2 | Rolek Tech. Ltd. | N49,504,847.04 |  | 51
3 | Resourcery Plc | N49,876,478.61 |  | 60
PROJECT : UPGRADING OF ELECTRICAL/MECHANICAL EQUIPMENT IN SHEHU SHAGARI COMPLEX
SN | RESPONSIVE BIDS RECEIVED | AMOUNT QUOTED |  |  | TECHNICAL EVALUATION SCORES (%) |  | DATE BIDS WERE AVALUATED |  | DATE PRESENTED TO PPC |  |  | DATE MTB GAVE APPROVAL |  |  | MOST RESPONSIVE AND RECOMMENDED BID |  | DATE OF CONTRACT AWARD
1 | Destiny Works | N8,321,006.00 |  |  | 80 |  | 2011-09-08 |  | 2011-09-15 |  |  | 2011-09-16 |  |  | Amedus Integ. |  | 2011-11-09
| Nig Ltd | [13 empty] | Services
2 | General Portfolio | N31,354,520.00 |  |  | 70
Services
3 | Emadaic | N10,788,150.00 |  |  | 65
Solution Nig. Ltd
4 | Zukhruf Nig. Ltd | N30,686,212.20 |  |  | 80
5 | Amedus Integ. | N30,193,000.00 |  |  | 85
Services
6 | Silver Gold | N42,189,420.00 |  |  | 75
Energy Consult
7 | Alladuk Ltd | N32,714,400.00 |  |  | 60
8 | Ceero | N4,489,900.00 |  |  | 70
Alliance Ltd
SUPPLY OF 4 NOS. JEEP MOTOR VEHICLES FOR ECOLOGICAL FUNDS OFFICE
SN | RESPONSIVE BIDS RECEIVED | AMOUNT QUOTED |  |  | TECHNICAL EVALUATION SCORES (%) |  | DATE BIDS WERE AVALUATED |  | DATE PRESENTED TO PPC |  |  | DATE MTB GAVE APPROVAL |  |  | MOST RESPONSIVE AND RECOMMENDED BID |  | DATE OF CONTRACT AWARD
1 | A. C. Okocha Motors Ltd, | N68,400,000.00 |  |  | NA |  | 2011-09-08 |  | 2011-09-15 |  |  | 2011-09-16 |  |  | Elizade Motors Ltd |  | 2011-09-27
2 | Elizade Motors Ltd | N62,370,000.00 |  |  | NA
SUPPLY OF 1 NO. PICK UP 2.7 Lt Petrol Engine, 4WD, Double Cabin, AC AND 2 NOS. 2.0 Lt Petrol Engine Salon Cars, Auto Trans, Full Option and Leather Seats to EFO
SN | RESPONSIVE BIDS RECEIVED | AMOUNT QUOTED |  |  | TECHNICAL EVALUATION SCORES (%) |  | DATE BIDS WERE AVALUATED |  | DATE PRESENTED TO PPC |  |  | DATE MTB GAVE APPROVAL |  |  | MOST RESPONSIVE AND RECOMMENDED BID |  | DATE OF CONTRACT AWARD
| A. C. Okocha Motors Ltd | N16,850,000.00 |  |  | NA |  | 2011-09-08 |  | 2011-09-15 |  |  | 2011-09-16 |  |  | A. C. Okocha Motors Ltd |  | 2011-09-27
| Sitadyle Supplies Ltd | N23,177,700.00 |  |  | NA
| Dana Motors Ltd | N11,900,000.00 |  |  | NA
| Elizade Motors Ltd | N17,461,500.00 |  |  | NA
| Pavilian Motors Ltd | N19,085,000.00 |  |  | NA
| Hybridge Tech Coy. Ltd | N18,711,000.00 |  |  | NA
ESTABLISHMENT OF VIRTUAL/E-LIBRARY, WEB CONTENT MANAGEMENT SYSTEM AND COMPLEMENTARY FACILITIES AT THE SPECIAL DUTIES OFFICE
SN | RESPONSIVE BIDS RECEIVED | AMOUNT QUOTED |  |  | TECHNICAL EVALUATION SCORES (%) |  | DATE BIDS WERE AVALUATED | DATE PRESENTED TO PPC |  |  | DATE MTB GAVE APPROVAL |  | MOST RESPONSIVE AND RECOMMENDED BID |  |  | DATE OF CONTRACT AWARD
1 | Interglobal Ltd. | N41,600,000.00 |  |  | 37 |  | 2011-09-08 | 2011-09-15 |  |  | 2011-09-16 |  | A. A. C. Consulting |  |  | The award was made on 27/09/11 at the cost of N30,002,500. The scope and cost of the Contract was later reviewed by the end-uses to N11,823,000 and awarded to the same bidder on 24/11/11
2 | Recourcery Plc | N49,455,771.20 |  |  | 97
3 | Compu Clique | N25,292,400.00 |  |  | 51
4 | Andromedia Interg. Serv. | N34,493,812.50 |  |  | 89
5 | S O I Consulting Ltd. | N48,592,500.00 |  |  | 69
6 | Sidmach Tech Nig. Ltd. | N156,339,006.43 |  |  | 98
7 | A. A. C. Consulting | N30,002,500.00 |  |  | 98
8 | Data Link Technology Ltd. | N37,634,736.84 |  |  | 71
9 | Havilah March. Nig. Ltd. | N71,281,350.00 |  |  | 63
CONDUCT OF ECOLOGICAL CONSCIOUSNESS (TELEVISION)
SN | RESPONSIVE BIDS RECEIVED | AMOUNT QUOTED |  |  | TECHNICAL EVALUATION SCORES (%) |  | DATE BIDS WERE AVALUATED |  | DATE PRESENTED TO PPC |  |  | DATE MTB GAVE APPROVAL |  |  | MOST RESPONSIVE AND RECOMMENDED BID |  | DATE OF CONTRACT AWARD
1 | Charlesflory Ltd | N41,651,850.00 |  |  | 75 |  | 2011-09-08 |  | 150911 |  |  | 160911 |  |  | Charlesflory Ltd. The cost was most reasonable.
2 | Patrick Oke | N27,381,500.00 |  |  | 65
and Assoc
THE GREEN AGENDA
SN | RESPONSIVE BIDS RECEIVED | AMOUNT QUOTED |  |  | TECHNICAL EVALUATION SCORES (%) |  | DATE BIDS WERE AVALUATED |  | DATE PRESENTED TO PPC |  |  | DATE MTB GAVE APPROVAL |  |  | MOST RESPONSIVE AND RECOMMENDED BID |  | DATE OF CONTRACT AWARD
1 | Macro Investment Ltd | N22,290,615.78 |  |  | 80 |  | 2011-09-08 |  | 150911 |  |  | 160911 |  |  | Macro Investment Ltd
2 | Homegrown Ltd | N11,588,666.03 |  |  | 55
3 | Gado Agency Ltd | N34,620,700.00 |  |  | 65
4 | GIVCHRIS | N32,839.376.00 |  |  | 63
Global Serv. Ltd
RENDERING HELP WHERE NEEDED/RESPONSIBLE CITIZENSHIP (PRINT MEDIA)
SN | RESPONSIVE BIDS RECEIVED | AMOUNT QUOTED |  |  | TECHNICAL EVALUATION SCORES (%) |  | DATE BIDS WERE AVALUATED |  | DATE PRESENTED TO PPC |  |  | DATE MTB GAVE APPROVAL |  |  | MOST RESPONSIVE AND RECOMMENDED BID |  | DATE OF CONTRACT AWARD
1 | The Movie House | N19,353,951.00 |  |  | 90 |  | 2011-09-08 |  | 150911 |  |  | 160911 |  |  | The Movie House
2 | Givchnis | N34,034,000.00 |  |  | 80
Global Serv. Ltd
SN | RESPONSIVE BIDS RECEIVED | AMOUNT QUOTED |  |  | TECHNICAL EVALUATION SCORES (%) |  | DATE BIDS WERE AVALUATED | [7 empty] | MOST RESPONSIVE AND RECOMMENDED BID |  | DATE OF CONTRACT AWARD
1 | Sidmach Tech. Nig. Ltd. | N45,681,370.07 |  |  | 89 |  | 2011-09-08 |  | 150911 |  |  | 160911 |  |  | Digital Communication Konsult Nigeria Ltd
2 | Resourcery Plc | N60,112,141.10 |  |  | 60
3 | Digital Communication Konsult Nigeria Ltd | N9,417,848.00 |  |  | 90
Supply of 1 No. Peugeot 407 Classic Extra 2.0 Petrol Engine for Federal Government Investigation Panel on Election Violence and Civil Disturbances.
SN | RESPONSIVE BIDS RECEIVED | AMOUNT QUOTED |  |  | TECHNICAL EVALUATION SCORES (%) |  | DATE BIDS WERE AVALUATED |  | DATE PRESENTED TO PPC |  |  | DATE MTB GAVE APPROVAL |  |  | MOST RESPONSIVE AND RECOMMENDED BID |  | DATE OF CONTRACT AWARD
1 | A.C. Okocha Motors Ltd | N6,695,425.00 |  |  | NA |  | 2011-06-27 |  | 2011-06-28 |  |  | 2011-06-28 |  |  | A.C. Okocha Motors Ltd |  | 11/0711
2 | Rabo Motors Company | N7,420,000.00
3 | ACOM Tech (Nig) | N7,200,000.00
Supply of Two Toyota Landcruiser Prado Jeeps VXL 4.0 L Petrol Engine, Automatic Transmission, Reverse Camera, Leather Seats, Cool Box (Fridge), CD AND DVD Player, Airbags/Full Option for Federal Government Investigation panel on Election Violence and Civil Disturbances.
SN | RESPONSIVE BIDS RECEIVED |  | AMOUNT QUOTED |  |  | TECHNICAL EVALUATION SCORES (%) | DATE BIDS WERE AVALUATED |  | DATE PRESENTED TO PPC |  |  | DATE MTB GAVE APPROVAL |  |  | MOST RESPONSIVE AND RECOMMENDED BID |  | DATE OF CONTRACT AWARD
1 | Ineh-Mic Automobile Co. Ltd |  | N30,870,000.00 |  |  | NA | 2011-06-27 |  | 2011-06-28 |  |  | 2011-06-28 |  |  | Ineh-Mic Automobile Co. Ltd |  | 2011-07-11
2 | Banilux Motors |  | N31,185,000.00
3 | Elizade Nig. Ltd |  | N31,290,000.00
Supply of 2 Nos. Toyota Hiace 16-S MR AC P Bus Medium Roof 2.7 VVTi 4.0 Litre Petrol Engine
1 | Elizade Nig. Ltd |  | N12,600,000.00 |  |  | NA | 2011-06-27 |  | 2011-06-28 |  |  | 2011-06-28 |  |  | Elizade Nig. Ltd |  | 2011-07-21
2 | Ineh-Mic Automobile Co. Ltd |  | N17,040,000.00
3 | Banilux Motors |  | N17,955,000.00
Supply, Installation and One Year Maintenance of 1 No 100KVA/80KW415/240V 1500RPM Perkins Soundproof Generator and 6,000 Litres Diesel Storage Tank (Office of Chief Economic Adviser to President)
SN | RESPONSIVE BIDS RECEIVED |  | AMOUNT QUOTED |  |  | TECHNICAL EVALUATION SCORES (%) | DATE BIDS WERE AVALUATED |  | DATE PRESENTED TO PPC |  |  | DATE MTB GAVE APPROVAL |  |  | MOST RESPONSIVE AND RECOMMENDED BID |  | DATE OF CONTRACT AWARD
1 | Zukhruf Nigeria Limited |  | N11,760,000.00 |  |  | NA | 2011-11-16 |  | 2011-11-17 |  |  | 2011-11-17 |  |  | Zukhruf Nigeria Limited |  | 2011-11-25
| BT and T Ltd |  | N14,200,600.50
| Meritage Homes Ltd |  | N12,050,000.00
| BULCOY 32 |  | N15,640,000.00
Construction of 1 Nos. Continuously Operating Reference Station (CORS) in Akure
SN | RESPONSIVE BIDS RECEIVED |  | AMOUNT QUOTED |  |  | TECHNICAL EVALUATION SCORES (%) | DATE BIDS WERE AVALUATED | DATE PRESENTED TO PPC |  | DATE MTB GAVE APPROVAL |  |  |  | MOST RESPONSIVE AND RECOMMENDED BID |  |  | DATE OF CONTRACT AWARD
| Corporate Surveys Ltd |  | N23,581,100.00 |  |  | 93 | 2011-07-21 | 2011-11-23 |  | 2011-11-24 |  |  |  | Corporate Surveys Ltd |  |  | 2011-12-15
| SIVAN Design Ltd |  | N23,801,560.00 |  |  | 86 | [7 empty] | (The Evaluation Committee negotiated with all the responsive bidders and agreed on a flat rate of N23,581,100.00 for the construction of each CORS in any part of the country.
| Babatunde Allo and Associates Ltd |  | N23,662,621.50 |  |  | 99
Construction of 1 Nos. Continuously Operating Reference Station (CORS) in Katsina
SN | RESPONSIVE BIDS RECEIVED |  | AMOUNT QUOTED |  |  | TECHNICAL EVALUATION SCORES (%) | DATE BIDS WERE AVALUATED |  | DATE PRESENTED TO PPC |  |  | DATE MTB GAVE APPROVAL |  |  | MOST RESPONSIVE AND RECOMMENDED BID |  | DATE OF CONTRACT AWARD
| Corporate Surveys Ltd |  | N23,581,100.00 |  |  | 99 | 2011-07-21 |  | 2011-11-23 |  |  | 2011-11-24 |  |  | Corporate Surveys Ltd |  | 2011-12-15
| SIVAN Design Ltd |  | N23,801,560.00 |  |  | 86 | [5 empty] | bidders) |  |  | (same comments as for Akure).
| Babatunde Allo and Associates Ltd |  | N23,662,621.50 |  |  | 99

## 2011 P.R Environment
PROCUREMENT RECORDS
PROCUREMENT ENTITY (MDA): |  | ENVIRONMENT
FINANCIAL YEAR:2011
S/NO | CONTRACT DESCRIPTION | ADVERT DATE & MEDIA | APPRO. THRES HOLD | PROC. METHOD | BID OPENING DATE | CONTRACTOR | DATE OF CONTRACT AWARD | DATE OF CONTRACT COMMEN CEMENT | CONTRACT PERIOD | CONTRACT VALUE (N) | BUDGETARY PROVISION (N) | AMOUNT PAID AS AT FEB. 2012. | EXPECTED COMPL. DATE | % OF COMPL. AS AT | REMARKS
1 | Acquisition of Fire Proof File Racks Cabinet for the Ministry`s Registries at Abuja, FCT | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | Angular Panel Nig. Ltd | 13/12/2011 | 15/12/2011 | 4 Weeks | 8400000 | 10035958 | 8400000 | 14/01/2012 | 100%
2 | Procure. & Installation of Fire Extinguishers & other Fire Accessories/Equipment for Brown, Green & Forestry Building & Special Climate Change Unit Building | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | HGR Nig. Ltd, | 13/12/2011 | 21/12/2011 | 4 Weeks | 4920000.75 | 5995893 | 4920000 | 20/01/2012 | 100%
3 | Purchase of Equipment for Survey of Soil Quality | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | Cingular Tech. Investment Ltd, | 13/12/2011 | 23/12/2011 | 4 Weeks | 10713150 | 10802832 | 10713150 | 22/01/2012 | 100%
4 | Procurement of Training Equipment | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | McQuintus Ltd, | 13/12/2011 | 23/12/2011 | 4 Weeks | 2507295 | 4051062 | 2507295 | 22/01/2012 | 100%
5 | Reh., Improvement & Equipment of the Dilapidated Accounts Office (Fed. Min. of Env., Hqtrs, 36 States & FCT Account Offices) | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | Cube Networks Engineering Ltd., | 13/12/2011 | 30/12/2011 | 4 Weeks | 17650500 | 44014161 | 17650500 | 28/01/2012 | 100%
6 | Renovation & Equipping of the Fed. Min. of Env. Staff Canteen at Green Building in Maitama & Brown Building on Independence Way, Central Business District in Abuja | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | Kesim Investment Ltd., | 13/12/2011 | 27/12/2011 | 4 Weeks | 21157010 | 25996721 | 21157010 | 26/01/2012 | 100%
7 | Renovation & Equipping of the Federal Ministry of Environment Staff Clinic at Green Building in Maitama along Aguiyi Ironsi Way, Abuja | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | XYZ Engineering Ltd., Suite | 13/12/2011 | 28/12/2011 | 4 Weeks | 4711844.7 | 5446248 | 4711844.7 | 27/01/2012 | 100%
8 | Egbe Erosion\Flood Control, Egbe Road, Ekiti State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Camel Construction Co. Ltd. | 23/12/2011 | 2011 | 6 Weeks | 13933670.33 | 17728532 | 2090050.59 | March, 2012 | 15% | New Project
9 | Erosion at Akama Oghe | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Enap Builders Nig. Ltd. | 23/12/2011 | 2011 | 6 Weeks | 18324012 | 20000000 | 2748601.03 | March, 2012 | 15% | "
10 | Jakara Erosion Control in Kano Municipal, Kano State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Tiamin Multi Service & Global Ltd. | 23/12/2011 | 2011 | 10 Weeks | 21290893.56 | 26592798 | 3193634.03 | March, 2012 | 15% | "
11 | Isinbode Erosion & Flood Control Project, Isinbode Ekiti East LGA, Ekiti State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Simdi West Africa Ltd. | 23/12/2011 | 2011 | 4 Weeks | 21730893.56 | 26592798 | 3259595 | March, 2012 | 15% | "
12 | Ayesan/Eyingu Road, Erosion & Flood Control Project in Ondo State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Micheal Jacob Ltd. | 23/12/2011 | 2011 | 10 Weeks | 31204082.64 | 35457064 | 4680612.4 | March, 2012 | 15% | "
13 | Renov. & Construction of Gully Erosion in Abdulah Ibrahim Street, Old Magistrate River Bank, Katsina-Ala Township, Katsina-Ala LGA, Benue State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s MIU Construction Nig. Ltd., | 23/12/2011 | 2011 | 12Weeks | 31244064.38 | 40000000 | 4686609.66 | March, 2012 | 15% | "
14 | Renov. & Ikuru Town Shore Protection and Reclamation about 2km Shoreline Ikuru Town, Andoni LGA, Rivers State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s JGP Nig. Ltd., | 23/12/2011 | 2011 | 8 Weeks | 36486128.11 | 41465269 | 5472919.36 | March, 2012 | 15% | "
15 | Adebiyi Street/Express Erosion Control Project, Ile-Oluji, Ondo State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Jabridep Nig. Ltd. | 23/12/2011 | 2011 | 3 Weeks | 35979462.38 | 42321330 | 5396919.36 | March, 2012 | 15% | "
16 | Odukenye Street Erosion Control Works Atibe-Eket LGA, Akwa Ibom State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Coastline Global Afrique Ltd. | 23/12/2011 | 2011 | 8 Weeks | 33579500 | 42321330 | 5036925 | March, 2012 | 15% | "
17 | Ekanem Street Erosion Control Works, Akw Ibom State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Ometra Const. Engrs. Ltd., | 23/12/2011 | 2011 | 16 Weeks | 33350068.74 | 42321330 | 5002510.31 | March, 2012 | 15% | "
18 | Gully Erosion Control at Efon Alaaye, Ekiti State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Rindebim Nig. Ltd. | 23/12/2011 | 2011 | 12 Weeks | 35361230.52 | 44321330 | 5304184.58 | March, 2012 | 15% | "
19 | Erosion Control Project at Ode-Ekiti, Gbonyin LGA, Ekiti State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Surmount Integrated Services Ltd. | 23/12/2011 | 2011 | 8 Weeks | 36774163.13 | 44321330 | 5516124.47 | March, 2012 | 15% | "
20 | Flood & Erosion Control Project at Ogbunagha Town, Gbarain Clan, Yenegoa LGA, Bayelsa State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Safecraft Nig. Ltd. | 23/12/2011 | 2011 | 8 Weeks | 35602205.63 | 44321330 | 5340330.84 | March, 2012 | 15% | "
21 | Erosion & Flood Control Works at Amuwo Odofin, Lagos State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Archeban Concepts Nig. Ltd. | 23/12/2011 | 2011 | 3 Weeks | 37719199.09 | 48,612,,744.00 | 5657879.86 | March, 2012 | 15% | "
22 | Izuoha-Umuchamoko Flood & Erosion Control Project, Amuzi Ahiazu Mbaise LGA, Imo State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Telmac Engineering Services Ltd. | 23/12/2011 | 2011 | 10 Weeks | 39424686 | 50000000 | 5913702.9 | March, 2012 | 15% | "
23 | Gallah Erosion & Flood Control Project, Gallah, Niger State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Arfa Holding Nig. Ltd | 23/12/2011 | 2011 | 12 Weeks | 42268396.79 | 50000000 | 6340259.52 | March, 2012 | 15% | "
24 | Erosion & Flood Control Work at Augie, Kebbi State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Sahabi Liman Sons Ltd. | 23/12/2011 | 2011 | 12 Weeks | 37800861 | 50000000 | 567129.15 | March, 2012 | 15% | "
25 | Yola Storm Water Drainage Works, Yola, Adamawa State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s G-men Supplies & Services Ltd. | 23/12/2011 | 2011 | 6 Weeks | 37692763.5 | 50014161 | 5653914.53 | March, 2012 | 15% | "
26 | St. Valerian Church, Akpaka Erosion Site GRA, Phase II, Onitsha | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Ben Daniel Global Impex Ltd. | 23/12/2011 | 2011 | 10 Weeks | 49207173.75 | 60000000 | 7381076.06 | March, 2012 | 15% | "
27 | Erosion Control at Obot Udo Mbre in Atan, Usuk, Ukwok in Ini LGA, Akwa Ibom State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Westside Const. Coy. Ltd. | 23/12/2011 | 2011 | 10 Weeks | 46399925.25 | 60000000 | 6959988.79 | March, 2012 | 15% | "
28 | Oba Erosion Project, Anambra State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Xquizit Tech. Ltd., | 23/12/2011 | 2011 | 6 Weeks | 58894357.1 | 70000000 | 8834153.57 | March, 2012 | 15% | "
29 | Ideani Erosion Project, Anambra State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Ray Engr. Services Ltd. | 23/12/2011 | 2011 | 12 Weeks | 57707688.65 | 70000000 | 8656153.3 | March, 2012 | 15% | "
30 | Immiri John, Ojoto Erosion Project, Anambra State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Geokay Nig. Ltd. | 23/12/2011 | 2011 | 12 Weeks | 57106798.88 | 70000000 | 8566013.83 | March, 2012 | 15% | "
31 | Egbe Road Erosion Flood Control Project | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Shon Nig. Ltd. | 23/12/2011 | 2011 | 12 Weeks | 51988663.13 | 70914127 | 7798299.47 | March, 2012 | 15% | "
32 | Mararaba Jos Flood Control, Kaduna State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Nazo Solution Ltd. | 23/12/2011 | 2011 | 4 Weeks | 67,700,568,00 | 85642659 | 10155085.2 | March, 2012 | 15% | "
33 | Madufa Erosion Control | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s City Central Group of Coy. Ltd. | 23/12/2011 | 2011 | 12 Weeks | 70077000 | 88642659 | 10511550 | March, 2012 | 15% | "
34 | Ekimakae Road Drainage Work | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Executive Team Managers Ltd. | 23/12/2011 | 2011 | 12 Weeks | 78074435.38 | 102,596,,391.00 | 11711165.31 | March, 2012 | 15% | "
35 | Flood/Erosion Control Works in Bendeghe Ekiem Town Cross River State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Hypertek Project Ltd. | 23/12/2011 | 2011 | 12 Weeks | 94090319.34 | 118285319 | 14113547.9 | March, 2012 | 15% | "
36 | Erosion Control at Mahuta | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Lingo Nig. Ltd., | 23/12/2011 | 2011 | 12 Weeks | 102489664.28 | 122626510 | 15373449.64 | March, 2012 | 15% | "
37 | Tashan Tsamiya & Feleke Erosion Control, Sokoto State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Altex Engineering Ltd., | 23/12/2011 | 2011 | 10 Weeks | 93937292.65 | 122626510 | 14090593.9 | March, 2012 | 15% | "
38 | Damare Ward Flood Control Yola Town, Adamawa State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Simba Investment Ltd., | 23/12/2011 | 2011 | 12 Weeks | 95682414.48 | 122963989 | 12207720.15 | March, 2012 | 15% | "
39 | Flood & Erosion Project at Wilmot Point Road, Bar Beach, Victoria Island, Lagos State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Abdul Bakai Ent. Ltd., | 23/12/2011 | 2011 | 12 Weeks | 106116340 | 132963989 | 16429312.83 | March, 2012 | 15% | "
40 | Okpoma-Itekpa Road Drainage Works, Yala LGA, Cross River State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Arrival and Satisfaction Ltd | 23/12/2011 | 2011 | 12 Weeks | 112450414.65 | 140566273 | 16867562.2 | March, 2012 | 15% | "
41 | Flood Erosion Control Works in Bendeghe Ekiem Town, Cross River State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Pure Environment Service Ltd. | 23/12/2011 | 2011 | 12 Weeks | 112669358.38 | 150000000 | 16900403.76 | March, 2012 | 15% | "
42 | Madda Kamve-Namtbari-Konawaya Road Flood & Erosion Control Works, Adamawa State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Nostro Venture Ltd., | 23/12/2011 | 2011 | 12 Weeks | 161505533.7 | 201606648 | 24225830.06 | March, 2012 | 15% | "
43 | Completion of Shore Protection and Erosion Control of Abakbiriya-Nembe in Bayelsa East Senatorial District, Bayelsa State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s United Radak Ltd., | 23/12/2011 | 2011 | 8 Weeks | 213407617.5 | 270000000 | 32011142.63 | March, 2012 | 15% | "
44 | Industrial Pollution Prevention and Control at Obajana Cement Industry Kogi State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Xploits Consulting Ltd. | 23/12/2011 | 2011 | 12 Weeks | 3926250 | 4251000 | 83,926,250.00 curently being processed | 15/03/2012 | 95% | Prompt release of funds would help achieve the project.
45 | Coordinating Consultant for the Nigeria Erosion and Watershed Management Project (NEWMAP) | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Infratec Ltd., | 23/12/2011 | 2011 | 12 Months | 85540000 | 31024931 | 31024931 | Dec.2012 | 30%
46 | Development of a Modern EIA Registry | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Sustainability Ltd. | 23/12/2011 | 23/12/2011 | 4 Weeks | 15982876 | 10,204.248.00 | 15982876 | 2014 | 20%
47 | Consultancy of Environmental Survey of Nigerian Rivers Phase 1: River Niger | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Jawura Environmental Services Ltd. | 23/12/2011 | 23/12/2011 | 4 Weeks | 23173914.8 | 21605664 | 23173914.8 | 2014 | 20%
48 | Consultancy of Environmental Survey of Nigerian Rivers Phase 1: River Benue | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s FTJ Consults Ltd. | 23/12/2011 | 23/12/2011 | 4 Weeks | 3,925.000.00 | 4188987 | 3,925.000.00 | 2014 | 20%
49 | Training of Staff on Application of Geographic Information Systems | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Training & Development Services | 23/12/2011 | 23/12/2011 | 2 Weeks | 3,970.550.00 |  | 3,970.550.00 | 2014 | 20%
50 | Procurement of Bulk Storage Retractable Filling System | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Environmental Perspective Ltd. | 23/12/2011 | 23/12/2011 | 4 Weeks | 4,255.750.00 | 30510620 | 4,255.750.00 | 2014 | 20%
51 | Supply of Computers & Accessories | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Environmental Harmony Ltd. | 23/12/2011 | 23/12/2011 | 12 Weeks | 4,725.050.00 |  | 4,725.050.00 | 2014 | 20%
52 | Purchase of Law Books/Printing of Agreement | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Havilah Merchant Nig. Ltd. | 23/12/2011 | 29/12/2011 | 2 Weeks | 8735645.7 | 10503540 | 8735645.7 | Jan. 2012
53 | Hands-on-Training Programme for National Experts on Inventorisation of Greenhouse Gases Emission in Nigeria | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Jarfey Nig. Ltd., | 23/12/2011 | 2012-05-12 | 4 Weeks | 4060500 | 4120221 | 4060500 | 2012-06-02 | 100% | Satisfactorily performed
54 | Development of Framework for Implementation of the Kyoto Protocol Adaptation Fund | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Edges Environmental Services (Nig.) Ltd., | 23/12/2011 | 15/01/2012 | 6 Weeks | 4100050 | 4122452 | 4100050 | 21/02/2012 | 100% | Satisfactorily performed
55 | Development of Greenhouse Gas Inventory Toolkit in Nigeria | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Enmard Nig. Ltd., | 23/12/2011 | 2012-05-01 | 4 Weeks | 3975900 | 3975900 | 3975900 | 2012-06-02 | 100% | Satisfactorily performed
56 | Development of a Planned Adptation Strategy to Combat Climate Change in Nigeria | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Thesby Consult Nig. Ltd. | 23/12/2011 | 2012-06-01 | 8 Weeks | 4879125 | 5000000 | 4879125 | 25l02/2012 | 100% | Satisfactorily performed
57 | Procurement of Office Equipment for the Greenhouse Inventory System’s Office for SCCU | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Stonewall Ventures Ltd., | 23/12/2011 | 2012-04-01 | 4 Weeks | 4163800 | 4176947 | 4163800 | 06l02/2012 | 100% | Satisfactorily performed
58 | Flood & Erosion Control Project at Magodo Lagos State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Krisco Investment Ltd. | 23/12/2011 | 2011 | 32 Weeks | 497105683.87 | 633282548 | 74565852.58 | March, 2012 | 15% | "
59 | Waste Recycling Facility in Owerri, Imo State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Chemical & Environmental Engineering Ltd., | 29/12/2011 | 29/12/2011 | 12 Weeks | 307154816.01 | 300000000 | 46073222.4 | 2012-03-01 | 20 | 0ngoing
60 | Procure. & Installation of Renewable Energy Option (Solar Powered Back Up System) at Ministry’s Headquarters | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Concession Development Co. Ltd. | 23/12/2011 | 23/12/2911 | 6 Weeks | 21514500 | 110000000 | 21875735 | Feb. 2012 | 30% | 0ngoing
61 | Extension: The Establishment of Scrap Metal Recovery and Recycling (Metallurgical) Plant at Emouha, River | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | Allison Rich Services & Resources Ltd. | 23/12/2011 | 23/12/2011 | 12 Weeks | 289293073.9 | 350000000 | 120951500 | 2012-03-01 | 95 | 0ngoing
62 | Extension: The Establishment of Scrap Metal Recovery and Recycling (Metallurgical) Plant at Igboile, Oyo State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Yewenu Nig. Ltd | 23/12/2011 | 23/12/2011 | 12 Weeks | 252423649.28 | 350000000 | 53726580 | 2012-03-01 | 80 | 0ngoing
63 | Extension: Establishment of 10 Hactare Woodlot Plantation in Katsina State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Galtis Water Services Ltd, | 23/12/2011 | Dec. 2011 | 4 Weeks | 17033100 | 50816993 | 8820900 | January, 2012 | 90% as at 4th February 2012 | 0ngoing
64 | Extension: Establishment of A 15 Hactares Jatropha Plantation in Kuluma-Abara Borno State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Pinbad International Service Ltd. | 23/12/2011 | Dec. 2011 | 8 Weeks | 39097800 | 80642659 | 22056240 | February, 2012 | 80% as at 4th February, 2012 | 0ngoing
65 | Extension: Establishment of A 5 Hactare Rangeland Zamfara State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Hasmai Global Concept Ltd. | 23/12/2011 | Dec. 2011 | 4 Weeks | 6930000 | 87225489 | nil | January, 2012 | Not mobilised | 0ngoing
66 | Extension: Establishment of Integrated Waste Management Facility at Ado-Ekiti, Ekiti State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Tabaz Global Resource Nig. Ltd. | 23/12/2011 | 23/12/2011 | 8 Weeks | 13335262.49 | 290000000 | 105000000 | 2012-03-01 | 55 | 0ngoing
67 | Extension: Establishment of Scrap Metal Recovery and Recycling (Metallurgical) Plant at Sokoto, Sokoto State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Scrap Metal Managers Ltd | 23/12/2011 | 23/12/2011 | 12 Weeks | 296441861.64 | 570177285 | 472922553.39 | 2012-03-01 | 95 | 0ngoing
68 | Extension: Establishment of Scrap Metal Recovery and Recycling (Metallurgical) Plant at Kaduna, Kaduna State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s EnviroSafe Nig. Ltd | 23/12/2011 | 23/12/2011 | 12 Weeks | 152280592.98 | 350570637 | 341,92,553.39 | 2012-03-01 | 95 | 0ngoing
1922525360.87

## 2011 P.R FRSC
PROCUREMENT RECORDS
PROCURING ENTITY (MDA) |  | FEDERAL ROAD SAFETY CORPS
MINISTRY: |  | THE PRESIDENCY
FINANCIAL YEAR: |  | 2011
| BASIC DATA |  |  |  |  | CONTRACT AWARD | [5 empty] | CONTRACT IMPLEMENTATION
S/N | CONTRACT DISCRIPTION | ADVERTISEMENT DATE AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | CONTRACTOR | DATE OF CONTRACT AWARD | DATE OF CONTRACT COMMENCEMENT | CONTRACT PERIOD | CONTRACT VALUE (N) | BUDGETARY PROVISION (N) | AMOUNT PAID AS AT | EXPECTED COMPLETION DATE | % OF COMPLETION AS AT | REMARKS
1 | Purchase of Computers | 2010-05-31 | FRSC Tenders Board | Open Competitive Bidding | 2010-06-28 | Centre Point | 2010-12-21 | 2010-12-24 | 8 Weeks | 9500000 | 10802832 | 9.5m | 2011-02-12 | 100% | Supplied
Tender Journal, Sun, Daily Trust
2 | Purchase of Photocopiers | 2010-05-31 | FRSC Tenders Board | Open Competitive Bidding | 2010-06-28 | Xerox HS Nig Ltd | 2010-12-02 | 2010-12-09 | 2 Weeks | 4500000 | 5401406 | 4.5m | 2010-12-16 | 100% | Supplied
Fed. Tender Journal, Guardian, Sun
3 | Purchase of Ambulances | 2010-05-31 | FEC | Open Competitive Bidding | 2010-06-28 | Longevity` | 2010-12-30 | 2011-01-01 | 15 Weeks | 160000000 | 135035402 | 115m | 2011-05-02 | 100% | Supplied
Tender Journal, Guardian, Sun
4 | Software Acquisition | 2010-09-20 | FRSC Tenders Board | Open Competitive Bidding | 2010-10-04 | Centre Point | 2010-12-21 | 2011-02-22 | 8 Weeks | 12500000 | 41050762 | 12.5m | 2011-02-12 | 100% | Completed
Fed Tender Journal, Guardian, Daily Trust
5 | Software Acquisition | 2010-09-20 | FRSC Tenders Board | Open Competitive Bidding | 2010-10-04 | Centre Point | 2010-12-21 | 2011-02-22 | 8 Weeks | 7500000 | 41050762 | 7.5m | 2011-02-12 | 100% | Completed
Fed Tender Journal, Guardian, Daily Trust
6 | Software Acquisition | 2010-09-20 | FRSC Tenders Board | Open Competitive Bidding | 2010-10-04 | Centre Point | 2010-12-21 | 2011-02-22 | 8 Weeks | 7500001 | 41050762 | 7.5m | 2011-02-12 | 100% | Completed
Fed Tender Journal, Guardian, Daily Trust
7 | Software Acquisition | 2010-09-20 | FRSC Tenders Board | Open Competitive Bidding | 2010-10-04 | Centre Point | 2010-12-21 | 2011-02-22 | 8 Weeks | 13000000 | 41050762 | 13m | 2011-02-12 | 100% | Completed
Fed Tender Journal, Guardian, Daily Trust
8 | Rehabilitation of Badagry & Epe Unit Commands | 2010-05-31 | FRSC Tenders Board | Open Competitive Bidding | 2010-06-28 | Lektuns Ltd | 2010-12-06 | 2010-12-08 | 21 Weeks | 4351125.5 | 18364815 | 4351125.5 | 2011-02-05 | 100% | Completed
Tender Journal, Guardian, Sun
9 | Recostruction of Lagos Zonal Clinic | 2010-05-21 | FRSC Tenders Board | Open Competitive Bidding | 2010-06-28 | Amdy Surgical Ltd | 2010-12-03 | 2010-12-06 | 8 Weeks | 5261146 | 18364815 | 3104160.39 | 2011-02-02 | 100% | Completed
Fed. Tender Journal, Guardian, Sun
10 | Upgrade of FRSC Call Centre | 2010-09-17 | FRSC Tenders Board | Open Competitive Bidding | 2010-10-04 | Interra Networks Ltd | 2010-12-22 | 2010-12-27 | 4 Weeks | 24157022 | 10802832 | 6m | 2011-01-21 | 100% | Completed
Tender Journal, Daily Trust, Guardian
11 | Renovation of Enugu Zonal Clinic | 2010-05-31 | FRSC Tenders Board | Open Competitive Bidding | 2010-06-28 | Don Manchester Ltd | 2010-12-21 | 2010-12-23 | 9 Weeks | 7703734.5 | 18364815 | 3800554 | 2011-03-20 | 100% | Completed
Tender Journal, Guardian, Sun
12 | Annual Subscription Fee for 300 Fleet Managers in FRSC Vehicles | On-going Project | FRSC Tenders Board | N/A | N/A | Safety Riders Techn Ltd | 2010-09-18 | 2010-09-25 | 3 Weeks | 12000000 | 71021241 | 12m | 2010-10-11 | 100% | Completed
13 | Supply of Servers and Network Printers | 2010-09-20 | FRSC Tender Board | Open Competitive Bidding | 2010-10-04 | Nigandi Nig Ltd | 2010-12-22 | 2010-12-25 | 4 Weeks | 5347000 | 41050762 | 5347000 | 2011-01-12 | 100% | Completed
Tender Journal, Daily Trust, Guardian
14 | Drilling/Installation of Bore Hole at Nnewi Unit Commandf | 3./12/10 | FRSC Tenders Board | Open Competitive Bidding | 2010-06-28 | Gustaj Nig Ltd | 2010-12-06 | 2010-12-11 | 9 Weeks | 4332605 | 18364815 | 4,332,605..00 | 2011-02-05 | 100% | Completed
Tenders Journal, Guardian, Sun
15 | Upgrade of Fleet Manager | On-going | FRSC Tenders Board | Repeat Procurement | N/A | Safety Riders | 2010-09-17 | 2010-09-20 | 3 Weeks | 6000000 | 41050762 | 6m | 2010-10-07 | 100% | Completed
16 | Provision of 10 Point LAN for Zone 7 Commands | 2010-09-20 | FRSC Tenders Board | Open Competitive Bidding | 2010-10-04 | Centre Point | 2010-12-21 | 2010-12-23 | 7 Weeks | 8000000 | 41050762 | 8m | 2011-02-12 | 100% | Completed
Tender Journal, Guardian, Daily Trust
17 | Provision of 10 Point LAN for Zone 6 Commands | 2010-09-20 | FRSC Tenders Board | Open Competitive Bidding | 2010-10-04 | Centre Point | 2010-12-22 | 2010-12-23 | 7 Weeks | 8500000 | 41050762 | 8.5m | 2011-02-12 | 100% | Completed
Tender Journal, Guardian, Daily Trust
18 | Provision of 10 Point LAN for 2 Commands | 2010-09-20 | FRSC Tenders Board | Open Competitive Bidding | 2010-10-04 | Centre Point | 2010-12-21 | 2010-12-22 | 7 Weeks | 10500000 | 41050762 | 10.5m | 2011-02-12 | 100% | Completed
Tender Journal, Guardian, Daily Trust
19 | Provision of 10 Point LAN for Zone 4 Commands | 2010-09-20 | FRSC Tenders Board | Open Competitive Bidding | 2010-10-04 | Centre Point | 2010-12-21 | 2010-12-22 | 7 Weeks | 10500001 | 41050762 | 10.5m | 2011-02-12 | 100% | Completed
Tender Journal, Guardian, Daily Trust
20 | Renovation of Abia Sector Command Office | 2010-05-31 | FRSC Tenders Board | Open Competitive Bidding | 2010-06-28 | SAM’AC (W.A) Ltd | 2010-12-06 | 2010-12-15 | 21 Weeks | 6949784.24 | 18364815 | 6949784.24 | 95/02/11 | 100% | Completed
21 | Supply of Rain Coats | 2010-05-31 | FRSC Tenders Board | Open Competitive Bidding | 2010-06-28 | Abbacool Industries Ltd | 2010-12-21 | 2010-12-23 | 2 Weeks | 9000000 | 24014161 | 9m | 2011-01-05 | 100% | Supplied
Tender Journal, Guardian, Sun
22 | Supply of Books to FRSC Library | 2010-05-31 | FRSC Tenders Board | Open Competitive Bidding | 2010-06-28 | Nsa-Nsa Com Ltd | 2010-12-21 | 2010-12-22 | 2 Weeks | 31872068.4 | 29430337 | 31872068.4 | 2011-01-05 | 100% | Supplied
Tender Journal, Guardian, Sun
368974487.64

## 2011 P.R National Planning
PROCUREMENT RECORDS
PROCUREMENT ENTITY (MDA):
MINISTRY: |  |  | NATIONAL PLANNING COMMISSION
FINANCIAL YEAR: |  |  | 2011
| BASIC DATA | [5 empty] | CONTRACT AWARD | [5 empty] | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | ADVERTISEMENT DATE AND MEDIA |  | APPROVAL THRESHOLD | PROCUREMENT METHODS | BID OPENING DATE | CONTRACTOR | DATE OF CONTRACT | DATE OF CONTRACT COMMENCEMENT | CONTRACT PERIOD | CONTRACT VALUE (N) | BUDGETARY PROVISION (N) | AMOUNT PAID AS AT DEC 2011 | EXPECTED COMPLETION DATE | % OF COMPLETION AS AT DEC 2011 | REMARKS
AWARD
1 | Reprinting of additional copies of NV20:2020 Document | Letter of Invitation 5th January, 2011 |  | MTB | Competitive Procurement | - | Messrs 1st October Publishing | 12th January, 2011 | 13th January, 2011 | 3 weeks | 57000000 | 60000000 | 57000000 | 3rd February, 2011 | 100%
method
2 | Service (Media Consultancy) | This Day Newspaper, Daily Trust and Federal Tenders Journal. 14th October, 2010 |  | MTB | Open Competitive Method | 7&8 December, 2010 | Messrs Verdant Zeal Communication & Moving Images Limited | 11th February, 2011 | 12th February, 2010 | 6 Months | 25000000 | 27000000 | 3750000 | 20th August, 2010 | 15%
3 | Service Facility Management | Contract Renewal |  | MTB | Competitive Procurement | Contract Renewal | Messrs Annai Limited | 13th May, 2011 | 7th May, 2012 | 1 year | 38282687.24 | 40000000 | 15313074.9 | 13th May, 2012 | 40%
method
4 | Supply of Vehicles 1 Nr Toyota Land cruiser VX, 1 Nr Toyota Prado Jeep 2.7 CC, 1 Nr Toyota Hiace Bus | Letter of invitation to bid |  | MTB | Selective Procurement | 1st June, 2011 | Messrs Elim Motors | 7th June, 2011 | 13th June, 2011 | 1 week | 32707505 | 33000000 | 32707505 | 20th June, 2011 | 100%
method
5 | Procurement of 2 Nos Digital Copier Machine | Letter of invitation to bid |  | MTB | Selective Procurement | 30th May, 2011 | Messrs Xerox HS Nig Limited | 7th June, 2011 | 8th June, 2011 | 1 week | 6799485 | 7000000 | 6799485 | 15th June, 2011 | 100%
|  | 16th May, 2011 |  |  | method
6 | Reprinting of additional 7,500 copies of the main edition of NV20:2020 and NIP volumes I & II Document. | Letter of Invitation 1th June, 2011 |  | MTB | Competitive Procurement |  | Messrs 1st October Publishing | 7th June, 2011 | 14th June, 2011 | 15 days | 60000000 | 60500000 | 60000000 | 29th June, 2011 | 100%
method
-
7 | Replenishment of the Store for the 1st Quarter | 3rd September, 2011 |  | MTB | Selective Procurement method | 16th September, 2011 | Several Companies | 17th September, 2011 | 18th September, 2011 | 1 week | 41221465 | 41500000 | 41221465 | 25th September, 2011 | 100%
Notice Board
8 | Services (Opening Up of work spaces/Granite flooring on the “C” wing of the Commission’s office building) | 1st June, 2011 |  | MTB | Selective Procurement Method | 17th June, 2011 | Messrs Annai Limited | 28th June, 2011 | 23rd July,2011 | 8 weeks | 6615620 | 7000000 | 6615620 | 17th September, 2011 | 100%
Notice Board
9 | Services (Wall Panelling of the work spaces on the “C” wing of the Commission’s office building) | 1st June, 2011 |  | MTB | Selective Procurement | 17th June, 2011 | Messrs Dazzle General Merchants Limited | 23rd June, 2011 | 2nd August, 2011 | 8 weeks | 6621670 | 7000000 | 6621670 | 27th Setember, 2011 | 100%
method
Notice Board
10 | Electrical/Electronic connectivity of the work space of the “C” wing of the Commission’s office building | 1st June,2011 |  | MTB | Competitive Procurement | 17th June, 2011 | Messrs Advance Link Information Technology Limited | 23rd June, 2011 | 4th July, 2011 | 8 weeks | 9527782 | 10000000 | 9527782 | 29th August,2011 | 100%
method
Notice Board
11 | Design and Printing of 5,000 copies of the abridged Transformation Agenda (2011 - 2015) Document | Notice Board |  | MTB | Selective Tendering | 9th June, 2011 | Messrs Advertising Design Consulting Limited | 23rd June, 2011 | 24th June, 2011 | 3 weeks | 4800000 | 5,000,000,00 | 4800000 | 15th July, 2011 | 100%
2nd June, 2011
12 | Design and Printing of 1,500 copies of a 200 page Report on the Performance of the Nigerian Economy for year 2010 | 3rd June, 2011 |  | MTB | Competitive Procurement Method | 24th June, 2011 | Messrs Design Advertising Consulting Limited | 12th July, 2011 | 13th July, 2011 | 1 week | 5625000 | 6000000 | 5625000 | 20th July, 2011 | 100%
13 | Design and Printing of 6,000 Draft copies of the Transformation Agenda | Letter of Invitation |  | MTB | Selective Tendering |  | Messrs Direct Digital Print Limited | 5th October, 2011 | 5th October, 2011 | 3 weeks | 49380000 | 50000000 | 7407000 | 26th October, 2011 | 15%
28th September, 2011
14 | Renovation and Refurbishing of the Main Conference Room of the Commission | 26th August, 2011 |  | MTB | Competitive Procurement | 16th September, 2011 | Messrs Advance Link Technology Limited | 13th October, 2011 | 13th October, 2011 | 3 months | 48925910 | 50000000 | 19,570,364.00 (40%) | 13th January, 2011 | On going
method
Notice Board
15 | Purchase of Project Vehicle for the office of SC | Letter of Invitation |  | MTB | Selective Tendering | - | Messrs Elim Motors Limited | 5th October, 2011 | 6th October, 2011 | 4 days | 11000000 | 11500000 | 11000000 | 10th October, 2011 | 100%
28th September, 2011
16 | Design and Printing of 5,000 copies of the Report on the Performance of the Economy in 1st half of 2011 | 26th August, 2011 |  | MTB | Competitive Procurement | 16th September, 2011 | Messrs Odemedia Digital Press Limited | 5th October, 2011 | 12th October, 2011 | 15 days | 14500000 | 15000000 | 14500000 | 27th October, 2011 | 100%
method
Notice Board
17 | 2nd Quarter (2011) Store Replenishment | 2nd September, 2011 |  | MTB | Open Competitive | 16th September, 2011 | Several Companies | 5th October, 2011 | 6th October, 2011 | 1 week | 83256025 | 83500000 | 83256025 | 13th October, 2011 | 100%
Notice Board
18 | HR Consultant | Letter of Invitation |  | SC | Selective Procurement Method | 22nd November, 2011 | Ultra Media Limited | 24th November, 2011 | 28th Nov, 2011 | 5 weeks | 4500000 | 5000000 | Yet to be paid | 2nd January, 2011 | 100%
8th November, 2011
19 | Supply of 10 Nos (Ten) Project Vehicles | Letter of Invitation to Bid |  | MTB | Selective Procurement | 16th Dec, 2011 | Messrs Elizade Motors Limited | 23rd December, 2011 | 27th December, 2011 | 1 weeks | 88712029 | 89000000 | 88712029 | 30TH December, 2011 | 100%
|  | 9th Dec, 2011 |  |  | method
20 | Production of 10,000 CD Disks of the Blue Print on NV20:2020, NIP I, II AND III | Notice Board |  | SC | Open Competitive | 9th December, 2011 | Tricom Productions Limited | 12th December, 2011 | 13th December, 2011 | 2 weeks | 3850000 | 4000000 | Yet to be paid | 27th December, 2011 | 100%
|  | 25th November, 2011 |  |  | method
21 | Supply and Printing of Stationeries (Envelops and folders) for the office of the Secretary to the Commission | 9th Dec, 2011 |  | SC | Selective Procurement | 16th Dec, 2011 | Ode media Digital Press Limited | 23rd December, 2011 | 24th Dec, 2011 | 1 week | 3604000 | 4000000 | Yet to be paid | 30th Dec, 2011 | 100%
method
Notice Board
601929178.24

## 2011 NIS
MINISTRY OF INTERIOR
NIGERIA IMMIGRATION SERVICE
PROCUREMENT RECORDS FROM JANUARY TO DECEMBER, 2011
PROCUREMENT ENTITY (MDA): |  |  | NIGERIA IMMIGRATION SERVICES
MINISTRY: |  |  | FOREIGN AFFAIRS
S/N | PROJECT DESCRIPTION | BUDGET CLASSIFICATION | BUDGET ALLOCATION FOR THE PROJECT | PROCUREMENT METHOD | DATE PUBLISHED & MEDIA | LIST ALL BIDDERS & AMOUNT | CONTRACT AWARDEE | DATE OF AWARD & CONTRACT SUM | DATE OF AWARD & CONTRACT SUM | EXPECTED COMPLETION DATE | REMARKS
1 | Supply of Flight Kits for Air Border Patrol Unit (ABPU) Kaduna | 23010131 | 5401416 | Restricted Tendering | N/A | Westlink Airlines Ltd - (N4,833,346.00) | Westlink Airlines Ltd | October, 2011 (N4,833,346.00) | 4833346 | 2011
Skytrade Global Concept -$33,853.20
T.T Integrated Services - $33,232.30
2 | Supply of 1 no 40KVA (Soundproof) Power Generating Set For Lagos State Command | 23010119 | 37809912 | National Competitive Bidding | Sept. 2011 Notice Board Advert | (i) Muhsin Nig. Lted - N3,911,250.00 | Muhsin Nig Ltd | October, 2011 N3,911,250.00 | 3911250 | 2011
Velldrom Nig. Ltd - N3,984,780.00
Dalsam Tech. Lted - N4,126,500.00
Nnamife & Sons Nig. Ltd - N3,990,000.00
OAO Global Invt. Co. Nig. Ltd - N3,992,100.00
Hafsumag Nig. Ltd - N4,400,000.00
3 | Supply of 15,000 Pieces of 8 KPS Infeneon Data Chip Biometric Cards And Case of E-Registration Consumable (Colour Ribbons & Tranfer Film) for Eight (8) Zonal Card Production Centres | 23010128 | 34278197 | Direct Procurement | N/A |  | Imperial Network Ltd | October, 2011 N13,950,000.00 | 13950000 | 2011
Imperial Network Ltd - N13,950,000.00
4 | Printing and Supply of 28,000 Booklets of Ecowas Travel Certificate for Service Headquarters, Abuja | 22020306 | 36693555 | Direct Procurement | N/A |  | Nigeria Security Printing and Minting Company PLC (NSPMC) - | October, 2011 N22,050,000.00 | 22050000 | 2011
Nigeria Security Printing and Minting Company PLC (NSPMC) - N22,050,000.00
5 | Supply of 60 Nos AK47 Rifles Model 82 - 1 SMG 7.62 X 39MM with Accessories (Rifle Sling & Cleaning Kits), 25 Nos Pistol Model CF 98 type 9MM with Accessories (Leather Holster & Cleaning Kits), 12 Boxes of 1,000 Round 7.62 X 39MM SMG AK 47 Ammunition and 12 Boxes of 1,000 Rounds of 9MM Ammunition to SHQ, Abuja | Capital Supplementation | 197195000 | Restricted Tendering | N/A | Mubarak Real Solid Ltd - N27,867,000.00 | Mubarak Real Solid Ltd | December, 2011 N27,867,000.00 | 27867000 | 2011
Obaytes Nig Ltd-N27,943,125.00
Condor Technologies Ltd - N28,500,000.00
6 | Supply of 8 Nos 4WD Double Cabin Pick-up Truck full option (Shell Spec) Installation of Siren/Ember Light with painting to Immigration Colours for Border Patrol to SHQ, Abuja | Capital Supplementation | 197195000 | Restricted Tendering | N/A | Chanrai Nig Ltd - N44,394,000.00 | Chanrai Nig Ltd | December, 2011 N44,394,000.00 | 44394000 | 2011
Pavilion Motors Ltd - N48,216,000.00
Mansel Motors Ltd - N50,820,000.00
7 | Supply of Protective Gears for Border Patrol Operatives to Service SHQ, Abuja | Capital Supplementation | 197195000 | Restricted Tendering | N/A | Flourish Global Services Int'l Ltd - N32,489,625.00 | Flourish Global Services Int'l Ltd | December, 2011 N32,489,625.00 | 32489625 | 2011
Techno Touch Solution Consulting Ltd - N34,713,000.00
Agpex Crystal Services Ltd - N35,385,000.00
8 | Supply of 605 Pieces of Various Personalised/Codified Endorsement Stamps and 529 Bottles of Security Indelible Inks to SHQ, Abuja | 22020605 | 153000000 | Restricted Tendering | N/A | Encom Ltd - N9,986,025.00 | Encom Ltd | December, 2011 N9,986,025.00 | 9986025 | 2011
Lankfol Ventures Ltd - 10,046,400.00
Papi Printing Company Ltd - N10,152, 660.00
9 | Supply of 6 Nos Peugeot 408 Prestige with Painting to Immigration Colours to SHQ, Sauka-Abuja | Capital Supplementation | 197195000 | Direct Procurement | N/A | Peugeot Automobile Nig. Ltd (PAN) - N32,891,076.00 | Peugeot Automobile Nig. Ltd (PAN) | December, 2011 N32,891,076.00 | 32891076 | 2011
10 | Supply of Peugeot Saloon Cars: 1No 408 Regal, 1No 408 Prestige and 3Nos 307 Sedan Classic (Manual Transmission) to SHQ, Sauka - Abuja | 23010105 | 22142211 | Direct Procurement | N/A | Peugeot Automobile Nig. Ltd (PAN) - N21,647,170.35 | Peugeot Automobile Nig. Ltd (PAN) | December, 2011 N21,647,170.37 | 21647170.37 | 2011
11 | Supply of 2 Nos Innoson 33 Seater Luxury Bus (IVM 6800) to SHQ, Abuja | Capital Supplementation | 197195000 | Direct Procurement | N/A | Innoson Vehicle Manufacturing Co. Ltd - N18,270,000.00 | Innoson Vehicle Manufacturing Co. Ltd | December, 2011 N18,270,000.02 | 18270000.02 | 2011
12 | Supply of 2 Nos Land Rover (Defender) to SHQ, Abuja | Capital Supplementation | 197195000 | Direct Procurement | N/A | Choscharis Motors Ltd - N19,950,000.00 | Choscharis Motors Ltd | December, 2011 N19,950,000.02 | 19950000.02 | 2011
13 | Supply of 1No Toyota Landcruiser Prado 2.7CC, TX, Petrol Engine, Auto Transmission (Fabric Seat) to SHQ- Abuja | Capital Supplementation | 197195000 | Direct Procurement | N/A |  | R. T. Briscoe (Nig) Plc | December, 2011 N12,191,667.00 | 12191667 | 2011
R. T. Briscoe (Nig) Plc - N12,191,667.00
14 | Supply and Installation of Solar Power Street Lights for Immigration Village Sauka, Abuja | 22020605 | 153000000 | Direct Procurement | N/A | Ebunola Resources Nig Ltd - N31,500,000.00 | Ebunola Resources Nig Ltd | December, 2011 N31,500,000.02 | 31500000.02 | 2011
15 | Construction of Immigration Divisional Office, Mangu Local Government Area Council, Plateau State | 22020108 | 259085723 | National Competitive Bidding | 15th Nov, 2011, Federal Tenders Journal, Sun & Vanguard Newspapers |  | Messrs Playfield Ltd | December, 2011 N17,943,103.50 | 17943103.5 | 2012
Messrs Playfield Ltd - N17,943,103.50
16 | Construction of Immigration Divisional Office, Ado -Ekiti Local Government Area Council, Ekiti State | 22020108 | 259085723 | National Competitive Bidding | 15th Nov, 2011, Federal Tenders Journal, Sun & Vanguard Newspapers | Sassada Trading/Construction Ltd - NN17,553,904.00 | Sassada Trading/Construction Ltd | December, 2011 N17,553,904.00 | 17553904 | 2012
Muhsin Nig. Ltd - N19,037,056.50
Datum Coy. Ltd - N
17 | Sand Filling, Landscaping, Interlocking, Connection of Building to Public Water Mains and Provision of Step-Down Transformer to ACG'S and CIS Residence At Kirikiri, Lagos | 23020101 | 165648146 | National Competitive Bidding | 15th Nov, 2011, Federal Tenders Journal, Sun & Vanguard Newspapers |  | Messrs Cosmobuilt Nig. Ltd | December, 2011 32,769,859.50 | 32769859.5 | 2012
Messrs Cosmobuilt Nig. Ltd - 32,769,859.50
18 | Construction of Immigration Divisional Office, Agbara, Local Government Area Council, Ogun State | 22020108 | 165648146 | National Competitive Bidding | 15th Nov, 2011, Federal Tenders Journal, Sun & Vanguard Newspapers |  | Muhsin Nig. Ltd | December, 2011 N11,841,385.50 | 11841385.5 | 2012
Muhsin Nig. Ltd - N11,841,385.50
19 | Construction of Passport Office, Gwagwalada, FCT - Abuja | 23020101 | 165648146 | National Competitive Bidding | 15th Nov, 2011, Federal Tenders Journal, Sun & Vanguard Newspapers | Godab Nig. Ltd - N110,395,936.35 | Gilfai Nig. Ltd | December, 2011 - N98,201,304.60 | 98201304.6 | 2011
Chumax Agency Ltd - N103,142,235.00
Gilfai Nig. Ltd - N98,201,304.60
Top Front Ventures Ltd - N84,674,790.00
Datum Coy. Ltd - (BOQ inked in Pencil)
20 | Supply of A4 Photocopying and A3 Drawing Papers to SHQ, Abuja | 22020301 | 36469332 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Team Credit Ltd - N9,991,968.00 | Team Credit Ltd | December, 2011- N9,991,968.01 | 9991968.01 | 2011
T.T Integrated Services - N10,288,740.00
Eliphele Ltd - N10,503,592.00
21 | Supply of Various Printer Inks to SHQ-Abuja | 22020301 | 36469332 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Haramani Chemical Nig. Ltd - N9,984,870.00 | Haramani Chemical Nig. Ltd | December, 2011- N9,984,870.00 | 9984870 | 2011
Velldrom Nig. Ltd - N10,347,040.00
Dollgate Int. Vent. Ltd - N10,492,240.00
22 | Supply of Computer Anti Virus to SHQ - Abuja | 22020301 | 36469332 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Dalsam Tech. Nig. Ltd - N2,997,750.00 | Dalsam Tech. Nig. Ltd | December, 2011 - N2,997,750.00 | 2997750 | 2011
Team Credit Ltd - N3,274,700.00
23 | Supply of Office Stationery to SHQ - Abuja | 22020301 | 36469332 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Jim - Jim Global Concept Ltd - N4,992,435.00 | Jim - Jim Global Concept Ltd - | December, 2011 - N4,992,435.00 | 4992435 | 2011
Judubak Nig. Ltd - N5,267,460.00
OAO Global Invt. Co. Nig. Ltd - N5,324,000.00
24 | Supply of Drugs for Staff Clinic SHQ - Abuja | 22020301 | 36469332 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Pal Palace Nig. Ltd - N3,992,026.50 | Pal Palace Nig. Ltd | December, 2011 - N3,992,026.50 | 3992026.5 | 2011
Lux-ET Vent. Ltd - N4,216,168.00
25 | Supply of Various Drugs for NIS Training Instutions to SHQ - Abuja | 22020307 | 13964110 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Haramani Chemical Nig. Ltd - N4,995,448.50 | Haramani Chemical Nig. Ltd | December, 2011 - N4,995,448.50 | 4995448.5 | 2011
Velldrom Nig. Ltd - N5,151,003.00
Dollgate Int. Vent. Ltd - N5,271,343.00
26 | Supply of 327 Nos Campbeds for Border Operatives to SHQ - Abuja | 22020308 | 69791052 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Dalsam Tech. Nig. Ltd - N9,978,748.50 | Dalsam Tech. Nig. Ltd | December, 2011 - N9,978,748.50 | 9978748.5 | 2011
Tatu Int. Serv. Ltd -N10,,196,725.00
Equilibrium Global Concept Ltd -N10,224,313.00
Longwalk Logistics Ltd -N10,343,135.00
27 | Supply of 1,666 Nos of Treated Mosquitor Nets to SHQ - Abuja | 22020308 | 69791052 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Charlison Int'l Resources Ltd -N2,993,056.50 | Charlison Int'l Resources Ltd | December, 2011 -N2,993,056.50 | 2993056.5 | 2011
CT Nominees Ltd -N3,159,420.00
Atlantic Commodities Ltd -N3,347,080.00
28 | Supply of 8 Nos 440 Grade Military Type Tarpauline Tents and 8Nos 440 Grade Tarpauline Marquee Tents to SHQ, Abuja | 22020308 | 69791052 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Ba-A-Ba Tee & Assoc. Ltd -N5,493,600.00 | Ba-A-Ba Tee & Assoc. Ltd | December, 2011 -N5,493,600.00 | 5493600 | 2011
Wilfox Invest. Nig. Ltd -N5,699,540.00
Yasad Ent. Ltd -N5,794,800.00
29 | Supply of 2,222 Units of Blankets to SHQ - Abuja | 22020308 | 69791052 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Sky Track West Africa -N3,993,767.40 | Sky Track West Africa | December, 2011 - N3,993,767.40 | 3993767.4 | 2011
Equilibrium Global Concept Ltd -N4,214,078.00
Dirun Global Invest. Ltd -N4,660,480.00
30 | Supply of 444 Nos of Mattresses and 445 Nos of Pillows to SHQ - Abuja | 22020308 | 69791052 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Mumiri Nig. Ltd -N3,990,504.00 | Mumiri Nig. Ltd | December, 2011 -N3,990,504.00 | 3990504 | 2011
Has-Tang Int'l Ltd -N4,181,925.00
31 | Supply of Computer Accessories and Consumables to SHQ - Abuja | 22020301 | 38959249 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Asru Global Invest. Ltd -N4,995,742.50 | Asru Global Invest. Ltd | December, 2011 -N4,995,742.50 | 4995742.5 | 2011
Team Credit Ltd -N5,234,460.00
32 | Supply of 264 Nos Rechargeable Lamps and 52 Nos Extra Batteries to SHQ - Abuja | 22020308 | 53907003 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Karamah Global Invest. Ltd -N9,988,230.00 | Karamah Global Invest. Ltd | December, 2011 -N9,988,230.00 | 9988230 | 2011
Agpex Crystal Services Ltd - N10,250,900.00
33 | Supply of 222 Nos of Jungle Boots (Lace Up) to SHQ - Abuja | 22020308 | 69791052 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Sassada Trading/Construction Ltd - N4,992,435.00 | Sassada Trading/Construction Ltd | December, 2011 - N4,992,435.00 | 4992435 | 2011
Haramani Chemical Nig. Ltd -N5,144,700.00
Velldrom Nig. Ltd -N5,394,950.00
Dollgate Int. Vent. Ltd -N5,535,420.00
34 | Supply of 952 Reams of Letter Headed Papers for Commands Under Zone 'B' | 22020306 | 38959249 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Mindcraft Global Ivt. Ltd -N4,995,522.00 | Mindcraft Global Ivt. Ltd - | December, 2011 - N4,995,522.00 | 4995522 | 2011
Equilibrium Global Concept Ltd -N5,249,464.00
Dalsam Tech. Lted - N5,373,456.00
Tatu Int. Serv. Ltd -N5,416,136.00
35 | Supply of 793 Nos Raincoats to SHQ - Abuja | 22020308 | 69791052 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Karamah Global Invest. Ltd -N4,992,666.00 | Karamah Global Invest. Ltd | December, 2011 -N4,992,666.00 | 4992666 | 2011
Team Credit Ltd -N5,127,760.00
Encom Ltd - N5,289,020.00
Emprotame Global Nig. Ltd -N5,386,700.00
36 | Supply of 1,333 Pairs of Rainboots to SHQ - Abuja | 22020308 | 69791052 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | J. Jahanfa & Zar Nig. Ltd -N4,995,455.85 | J. Jahanfa & Zar Nig. Ltd | December, 2011 -N4,995,455.85 | 4995455.85 | 2011
Zahiwalu Vent. Ltd -N5,165,050.00
Velldrom Nig. Ltd -N5,197,676.00
37 | Supply of White Vests Round Neck with Immigration Logo | 22020308 | 69791052 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Dot - Net Technologies Ltd -N4,996,971.00 | Dot - Net Technologies Ltd | December, 2011 -N4,996,971.00 | 4996971 | 2011
Roc - Atlas Nig. Ltd -N5,182,540.00
Karama Global Links Ltd -N5,387,800.00
Hafsumag Nig. Ltd - N5,599,000.00
38 | Supply of Various Immigration Lanyards to SHQ, -Abuja | 022020309 | 52774826 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Tatu Integrated Service Ltd -N4,997,349.00 | Tatu Integrated Service Ltd | December, 2011 -N4,997,349.00 | 4997349 | 2011
Shua & Sons Enterp. Ltd -N5,010,495
Jim - Jim Global Concept Ltd - N5,153,058.00
Asru Global Invest. Ltd -N5,615,925.00
39 | Supply of Various Cap Badges to SHQ - Abuja | 022020309 | 52774826 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Kolfoad Nig. Ltd -N4,990,755.00 | Kolfoad Nig. Ltd | December, 2011 -N4,990,755.00 | 4990755 | 2011
Jim - Jim Global Concepts Ltd -N5,197,819.00
40 | Supply of Service Shoes (Black) to SHQ - Abuja | 022020309 | 52774826 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Clindorax Nig. Ltd -N4,992,510.60 | Clindorax Nig. Ltd | December, 2011 -N4,992,510.60 | 4992510.6 | 2011
Musadiq Engr. Serv. Ltd -N5,242,347.00
Verdad Nig. Ltd -N5,335,440.00
Imekete Mkting Co. Invt. Ltd -N5,552,800.00
41 | Supply of Passport File Jackets to SHQ -Abuja | 022020305 | 10400000 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Jadubak Nig Ltd -N4,993,506.00 | Jadubak Nig Ltd | December, 2011 -N4,993,506.00 | 4993506 | 2011
Mic-Jack Nig. Ltd -N5,258,400.00
Kacky Simo Nig. Ltd -N5,508,300.00
Equilibrium Global Concept Ltd -N5,808,180.00
42 | Printing and Supply of Letter Headed Papers for Commands Under Zone A & F | 022020306 | 39900000 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Nadik Nig. Ltd -N4,994,010.00 | Nadik Nig. Ltd - | December, 2011 -N4,994,010.00 | 4994010 | 2011
Comperio Nig. Ltd -N5,373,720.00
Dot Allied Serv. Ltd -N5,426,080.00
Agrak Printing Press -N6,278,228.00
43 | Supply of MCW - D50 Digital Wireless Conference Systems Plus Accessories to SHQ - Abuja | 022020310 | 10800000 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Primpex Ltd -N9,834,825.00 | Primpex Ltd | December, 2011 -N9,834,825.00 | 9834825 | 2011
Sunset Alternative Power Nig. Ltd -N9,894,885.00
Goshen II Technique -N9,916,830.00
44 | Supply of Service Belts to Service Headquarters -Abuja | 022020309 | 52774826 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Shua & Sons Enterp. Ltd -N4,991,250.00 | Shua & Sons Enterp. Ltd | December, 2011 N4,991,250.00 | 4991250 | 2011
Colourworld Tech. Ltd -N5,089,150.00
Mintex Associates Ltd -N5,188,700.00
45 | Printing and Supply of 51,450 Nos. of Open File Jackets for Command, Zones and SHQ -Abuja | 022020305 | 10400000 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Mindcraft Global Ivt. Ltd -N5,398,652.70 | Mindcraft Global Ivt. Ltd - | December, 2011 N5,398,652.70 | 5398652.7 | 2011
Encom Ltd -N5,522,832.00
Tatu Int. Serv. Ltd -N5,684,805.00
Roc - Atlas Nig. Ltd -N5,792,787.00
46 | Supply of 9,575 Pieces of Smart Card, 2 of Biometric Smart Card Reader, and 2 No. Smart Card Encorder for I. D. Card to SHQ - Abuja | 022020306 | 39000000 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Mann Builders Nig. Ltd -N6,992,028.75 | Mann Builders Nig | December, 2011 -N6,992,028.75 | 6992028.75 | 2011
Redeg Engr. Co. Ltd -N7,152,200.00
Rel-Semezek Int'l Co. Ltd -N7,275,125.00
Colourworld Tech. Ltd -N7,482,447.50
47 | Supply of 950 Reams of Letter Headed Papers for Zone 'G' and Commands Under Zone 'G' to SHQ - Abuja | 022020301 | 38959249 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Tatu Integrated Service Ltd -N4,998,087.50 | Tatu Integrated Service Ltd | December, 2011 -N4,998,087.50 | 4998087.5 | 2011
Dot - Net Technologies Ltd -N5,179,860.00
Shua & Sons Ent. -N5,185,950.00
Agrak Printing Press -N5,365,500.00
48 | Supply of 2,020 Nos of Brown T-Shirts with Immigration Logo to SHQ - Abuja | 022020309 | 52774826 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Dot - Net Tech. Ltd -N4,994,745.00 | Dot - Net Tech. Ltd | December, 2011 -N4,994,745.00 | 4994745 | 2011
Onyima Global Res. Ltd -N5,132,600.00
Shua & Sons Entrp. N5,232,700.00
Velldrom Nig. Ltd -N5,343,580.00
49 | Supply of 5,164 Pieces each of Medium and Small Size Brass Immigration Buttons Rings to SHQ - Abuja | 022020309 | 52774826 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Hafsumag Nig. Ltd -N5,492,172.00 | Hafsumag Nig. Ltd | December, 2011 -N5,492,172.00 | 5492172 | 2011
Emprotame Global Nig. Ltd -N5,651,096.00
Umka Nig. Ltd -N5,791,843.20
Jim - Jim Global Concept Ltd -N5,707,900.00
50 | Printing and Supply of Various Memo Pads with Immigration Logo to SHQ - Abuja | 022020306 | 3998700.9 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Agpex Crystal Service Ltd -N3,991,507.80 | Agpex Crystal Service Ltd | December, 2011 -N3,991,507.80 | 3991507.8 | 2011
Colourworld Tech. Ltd -N4,184,375.00
Techno Touch Solution Consulting Ltd - N4,299,724.00
51 | Supply of Tyres for Various Brands of SHQ - Abuja | 22020401 | 53907003 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Clindorax Nig. Ltd -N4,631,130.00 | Clindorax Nig. Ltd | December, 2011 -N4,631,130.00 | 4631130 | 2011
Kjock Engr. Consult. Ltd -N4,710,200.00
C & K Invt. Ltd -N4,787,560.00
Verdad Nig. Ltd -N4,817,780.00
52 | Supply of 327 Nos Tarpualine Campbeds for Security Guard to SHQ - Abuja | 22020605 | 153000000 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Onyima Global Res. Invt. Nig. Ltd -N9,978,748.00 | Onyima Global Res. Invt. Nig. Ltd | December, 2011 -N9,978,748.00 | 9978748 | 2011
Dalsam Tech. Ltd -N10,176,540.00
53 | Supply of Nig. Imm. Serv. Seal to SHQ - Abuja | 22020605 | 153000000 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Umka Nig. Ltd -N4,992,729.00 | Umka Nig. Ltd | December, 2011 -N4,992,729.00 | 4992729 | 2011
Jim - Jim Global Concept Ltd -N5,094,892.00
Dot - Net Tech. Ltd -N5,154,820.00
54 | Supply of 102 Nos of Peugeot 15 Ream tyres to SHQ - Abuja | 22020401 | 53907003 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Mihur Enter. -N5,361,930.00 | Mihur Enter. | December, 2011 - N5,361,930.00 | 5361930 | 2011
Naebass Int. Serv. Ltd -N5,490,760.00
Clindorax Nig. Ltd -N5,560,760.00
55 | Supply of Spare parts for Mechanical Repairs and Periodic Servicing of Service Cars, SHQ - Abuja | 22020401 | 53907003 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Mumiri Nig. Ltd -N4,993,905.00 | Mumiri Nig. Ltd | December, 2011 -N4,993,905.00 | 4993905 | 2011
Has-Tang Int'l Ltd -N5,141,950.00
Agpex Crystal Serv. Ltd -N5,178,140.00
56 | Supply of Various Badges of Rank for Junior Officers to SHQ - Abuja | 22020309 | 52744826 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Dalsam Tech. Ltd -N9,997,050.00 | Dalsam Tech. Ltd | December, 2011 -N9,997,050.00 | 9997050 | 2011
Hafsumag Nig. Ltd -N10,178,025.00
Agpex Crystal Serv. Ltd -N10,291,325.00
Onyama Global Res. Invt. Ltd -N10,345,390.00
57 | Printing and Supply of Letter Headed Papers for Commands Under Zone 'E' | 22020306 | 39900000 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Tatu Integrated Service Ltd -N4,996,362.00 | Tatu Integrated Service Ltd | December, 2011 -N4,996,362.00 | 4996362 | 2011
Amijad Ltd -N5,212,438.00
Agrak Printing Press -N5,476,367.60
58 | Supply of 2,109 Pieces (Various Sizes) of Brown Berets (Marvel Fairs) and 401 Pieces of White Berets to SHQ - Abuja | 22020309 | 52744826 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Solid Concrete Ind. Ltd -N9,694,597.50 | Solid Concrete Ind. Ltd | December, 2011 -N9,694,597.50 | 9694597.5 | 2011
Roc Atlas Nig. Ltd -N10,166,000.00
Mintex Associates Ltd -N10,281,282.00
Shua and Sons Ent. Ltd -N10,355,125.00
59 | Supply of Lubricants for Diesel Engine Vehicles to SHQ - Abuja | 22020401 | 53907003 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | STCC Nig. Ltd -N4,993,065.00 | STCC Nig. Ltd | December, 2011 -N4,993,065.00 | 4993065 | 2011
Umka Nig. Ltd -N5,158,230.00
Longwalk Logistics Ltd -N5,232,700.00
Encom Ltd -N5,380,100.00
60 | Supply of Vehicles Batteries to SHQ - Abuja | 22020401 | 53907003 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Tatu Integrated Services Ltd -N9,990,750.00 | Tatu Integrated Services Ltd | December, 2011 -N9,990,750.00 | 9990750 | 2011
Muhsin Nig. Ltd -N10,090,080.00
Emprotame Global Nig. Ltd -N10,131,000.00
Dollgate Integral Vent. Ltd -N10,207,890.00
61 | Supply of Tyres for CGI Fleet and DCGs Vehicles to SHQ - Abuja | 22020401 | 53907003 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Sassada Petroleum Nig. Ltd -N4,989,600.00 | Sassada Petroleum Nig. Ltd | December, 2011 -N4,989,600.00 | 4989600 | 2011
Kobonkate Int'l Res. Ltd -N5,175,500.00
Nnamife & Sons Nig. Ltd - N5,238,200.00
Emprotame Global Nig. Ltd -N5,446,100.00
62 | Supply of Lubricants for Petrol Engine Vehicles to SHQ - Abuja | 22020401 | 53907003 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Dot - Net Tech. Ltd -N4,999,260.00 | Dot - Net Tech. Ltd | December, 2011 -N4,999,260.00 | 4999260 | 2011
Nnamife & Sons Ltd -N5,171,540.00
Kabonkate Int'l Ltd -N5,262,180.00
63 | Supply 135 Pairs of Border Guards Operational Boots to SHQ - Abuja | Capital Supplementation | 197195000 | National Competitive Bidding | N/A | Roc Atlas Nig. Ltd -N3,052,612.5 | Roc Atlas Nig. Ltd | December, 2011 -N3,052,612.5 | 3052612.5 | 2011
Velldrom Nig. Ltd -N3,135,825.00
64 | Supply of Tyres for Heavy Duty Vehicles to SHQ - Abuja | 22020401 | 53907003 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Sassada Petroleum Nig. Ltd -N9,990,645.00 | Sassada Petroleum Nig. Ltd | December, 2011 -N9,990,645.00 | 9990645 | 2011
J. Jahanfa & Zar Nig. Ltd -N10,142,220.00
Zahiwalu Vent. Ltd -N10,256,620.00
Clindorax Nig. Ltd -N10,436,250.00
65 | Printing and Supply of Treasury Forms/Cash Books for Account Unit SHQ - Abuja | 2101 | 20909481585 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Jim - Jim Concept Nig. Ltd -N4,990,387.50 | Jim - Jim Concept Nig. Ltd | December, 2011 -N4,990,387.50 | 4990387.5 | 2011
Nadik Nig. Ltd -N5,099,490.00
Jadubak Nig Ltd -N5,115,110.00
Tatu Int. Services Ltd -N5,288,800.00
66 | Printing and Supply of Treasury Forms/Cash Books for Zone 'B' Kaduna, Kaduna State | 2101 | 20909481585 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Kolfoad Nig. Ltd -N9,988,629.00 | Kolfoad Nig. Ltd | December, 2011-N9,988,629.00 | 9988629 | 2011
Dot-Net Tech. Ltd -N10,078,255.00
Tatu Int. Serv. Ltd -N10,156,355.00
67 | Printing and Supply of Treasury Forms/Cash Books for Zone 'A' Lagos, Lagos State | 2101 | 20909481585 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Jim - Jim Concept Nig. Ltd -N4,992,115.00 | Jim - Jim Concept Nig. Ltd | December, 2011 N4,992,115.00 | 4992115 | 2011
Kolfoad Nig. Ltd -N10,091,268.00
Nadik Nig. Ltd -N10,188,728.00
Nic-Jack Nig. Ltd -N10,240,318.00
68 | Maintenance of 1No. 2 Bedroom and 1No. 3 Bedroom Bungalows Mfum, Calabar, Cross River State | 22020403 | 49599208 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Umka Nig. Ltd -N7,171,342.00 | Umka Nig. Ltd | December, 2011 NN7,171,342.00 | 7171342 | 2012
Onyima Global Res. Invt. Nig. Ltd -N7,599,847.00
J. Jahanfa & Zar Nig. Ltd -N7,820295.00
Dollgate Int. Vent. Ltd -N8,081,062.50
69 | Maintenance of Burnt Ecowas Office, Potiskum, Yobe State | 22020403 | 49599208 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Muhsin nig Ltd N4,935,000 | Muhsin nig Ltd | December, 2011 N4,935,000.00 | 4935000 | 2011
J. Jahanfa & Zar Nig. Ltd -N5,250,000
Karama Global Links Ltd -N5,775,000.00
STCC Nig. Ltd -N6,825,000.00
70 | Re-Roofing and Painting of Command Office, Calabar, Cross River State | 22020403 | 49599208 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Umka Nig. Ltd -N5,145,000.00 | Umka Nig. Ltd | December, 2011 -N5,145,000.00 | 5145000 | 2011
STCC Ltd -N5,775,000.00
Emprotame Global Nig. Ltd -N6,825,000.00
71 | Maintenance of Building at Immigration Training School, Kano | 22020403 | 49599208 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Muhsin Nig. Ltd -N7,114,432.00 | Muhsin Nig. Ltd | December, 2011-N7,114,432.00 | 7114432 | 2011
Dolgate Int. Vent. Ltd -N7,610,662.00
Kellbridge Universal Nig. Ltd -N8,005,305.00
STCC Nig. Ltd -N8,116,342.00
72 | Maintenance of Office, Damaturu, Yobe State | 22020403 | 49599208 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Muhsin Nig. Ltd -N5,196240.00 | Muhsin Nig. Ltd | December, 2011 -N5,196240.00 | 5196240 | 2011
Onyema Global Res. Inv. Ltd -N6,032 460.00
73 | Maintenance of Administrative Blocks, Kitchen and Lavatory at NITSOL, ORLU, Imo State | 22020403 | 49599208 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | STCC Nig. Ltd -N9,953,076.00 | STCC Nig. Ltd | December, 2011-N9,953,076.00 | 9953076 | 2011
Nnamife & Sons Ltd -N10,198,818.00
Onyima Global Res. Inv. Ltd -N10,308,406.50
Velldrom Nig. Ltd -N10,670,709.00
74 | Construction of Road Shoulder Along the Main Road of the Service Headquarters, Sauka, Abuja | 23020108 | 160042482 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Kellbridge Universal Nig. Ltd -N9,847,950.00 | Kellbridge Universal Nig. Ltd | December, 2011-N9,847,950.00 | 9847950 | 2011
Muhsin Nig Ltd N10,731,000.00
STCC Group of Co. Ltd -N11,614,050.00
Velldrom Nig. Ltd -N13,776,000.00
75 | Construction of Drainage Along the Main Road of the Service Headquarters, Sauka, Abuja | 23020108 | 160042482 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Velldrom Nig. Ltd -N9,867,900.00 | Velldrom Nig. Ltd | 9867900 | 9867900 | 2011
Dollgate Int. Vent. Ltd -N11,468,100.00
Muhsin Nig. Ltd -N11,776,800.00
Haramani Chemical Nig. Ltd -N13,030,500.00
76 | Printing and Supply of Letter Headed Papers for SHQ - Abuja | 22020306 | 38959249 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Sam David Diverse Concept -N3,992,278.50 | Sam David Diverse Concept - | December, 2011 -N3,992,278.50 | 3992278.5 | 2011
New Net Serv. Nig. Ltd -N4,249,464.00
Viego Computers Ltd -N4,373,456.00
Agrak Printing Press -N5,006,136.00
77 | Supply of Handcuffs and Leg Chains to SHQ - Abuja | 22020605 | 153000000 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Velldrom Nig. Ltd -N9,991,569.00 | Velldrom Nig. Ltd | December, 2011 -N9,991,569.00 | 9991569 | 2011
Dollgate Int. Vent. Ltd -N10,249,464.00
Kellbridge Universal Vent. Ltd -N11,373,456.00
78 | Supply of Pumping Machine and Water Storage Tank to SHQ - Abuja | 22020205 | 7998746.4 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Eliphele Ltd - N7,997,000.00 | Eliphele Ltd - N7,997,000.00 | December, 2011 - N7,997,000.00 | 7997000 | 2011
Team Credit Ltd -N8,456,700.00
Jadubak Nig. Ltd -N8,259,300.00
79 | Supply o 2,400 Reams of A4 Photocopying for Training Institution | 22020601 | 2700000 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Team Credit Ltd -N2,694,510.00 | Team Credit Ltd | December, 2011 -N2,694,510.00 | 2694510 | 2011
Tatu Int. Services Ltd -N3,304,350.00
Longwalk Logistics Ltd -N2,782,500.00
C. T. Nominees Ltd -N2,888,550.00
80 | Supply of Office Furniture to SHQ - Abuja | 22020402 | 14807075 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Kolfoad Nig. Ltd -N9,999,675.00 | Kolfoad Nig. Ltd | December, 2011 -N9,999,675.00 | 9999675 | 2011
Mumuri Nig. Ltd -N11,012,505.00
Karamah Global Ltd -N10,393,315.00
Asru Global Inv. Ltd -N10,641,015.00
81 | Supply of Office Equipment to SHQ - Abuja | 22020402 | 14807075 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Roc Atlas Nig. Ltd -N4,798,500.00 | Roc Atlas Nig. Ltd | December, 2011 -N4,798,500.00 | 4798500 | 2011
Zahiwalu Vent. Nig. Ltd -N5,265,750.00
Longwalk Logistics Ltd -N5,213,250.00
Shua & Sons Ent. -N6,007,050.00
82 | Supply of 3 Nos 30KVA (Soundproof) Perkins (Mikano) Generating Sets to SHQ - Abuja | 22020405 | 63000000 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Roc Atlas Nig. Ltd -N9,998,730.00 | Roc Atlas Nig. Ltd | December, 2011 -N9,998,730.00 | 9998730 | 2011
Zahiwalu Vent. Nig. Ltd -N10,452,750.00
Jadubak Nig. Ltd -N10,094,280.00
Jim - Jim Global Concept Ltd -N10,116,750.00
83 | Supply of 3 Nos 30KVA (Soundproof) Perkins (Mikano) Generating Sets for Commands Under Zone 'B' Kaduna - Kaduna State | 22020803 | 34534649.1 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Rima Hydrated - Lime Nig. Ltd -N9,998,835.00 | Rima Hydrated - Lime Nig. Ltd | December, 2011 -N9,998,835.00 | 9998835 | 2011
Solid Concrete Ind. Ltd -N10,472,700.00
Chifrang Nig. Ltd -N10,498,950.00
Imekete Mkting Co. Invt. Ltd -N10,077,900.00
Verdad Nig. Ltd -N10,119,900.00
Equilibrium Global Concept Ltd -N10,437,000.00
84 | Supply of 3 Nos 30KVA (Soundproof) Perkins (Mikano) Generating Sets for Commands Under Zone 'E' Owerri - Imo State | 22020803 | 34534649.1 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Kellbridge Universal Vent. Ltd -N9,997,575.00 | Kellbridge Universal Vent. Ltd | December, 2011 -N9,997,575.00 | 9997575 | 2011
Goshell II Technique -N10,478,475.00
Mintex Associate Ltd -N10,510,500.00
Dot Allied Serv. Ltd -N10,089,975.00
MindCraft Global Invt. Ltd -N10,441,725.00
85 | Supply of 3 Nos 30KVA (Soundproof) Perkins (Mikano) Generating Sets for Commands Under Zone 'F' Ibadan - Oyo State | 22020803 | 34534649.1 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Kellbridge Universal Vent. Ltd -N9,996,997.50 | Kellbridge Universal Vent. Ltd | December, 2011 -N9,996,997.50 | 9996997.5 | 2011
Tatu Int. Services Ltd -N10,276,297.50
Mintex Associate Ltd -N10,136,647.50
Dot - Net Tech. Ltd -N10,239,547.50
86 | Supply of 1 No 30KVA (Soundproof) Perkins (Mikano) Generating Sets for Commands Under Zone 'H' Makurdi - Benue State | 22020803 | 34534649.1 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Rima Hydrated - Lime Nig. Ltd -N3,332,910.00 | Rima Hydrated - Lime Nig. Ltd | December, 2011 -N3,332,910.00 | 3332910 | 2011
Zahiwalu Vent. Nig. Ltd -N3,617,460.00
Muhsin Nig. Ltd -N3,617,460.00
Sassada Trading Co. Ltd -N3,381,210.00
Dollgate Int. Vent. Ltd -N3,401,160.00
87 | Supply of Luxurious Bus & Truck Tyres for State Commands and Training Institutions | 22020802 | 56633850 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Velldrom Nig. Ltd -N6,595,575.00 | Velldrom Nig. Ltd | December, 2011 -N6,595,575.00 | 6595575 | 2011
Redeg Engr. Co. Ltd -N6,765,150.00
Umka Nig. Ltd -N6,639,150.00
Hafsumag Nig. Ltd -N6,680,100.00
88 | Purchase of Various Brands of Tyres for State Commands and Training Institutions | 22020802 | 56633850 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Velldrom Nig. Ltd - N9,993,270.00 | Velldrom Nig. Ltd | December, 2011 -N9,993,270.00 | 9993270 | 2011
Umka Nig. Ltd -N10,780,177.80
New Age Solution Ltd -N10,116,120.00
Sassada Petroleum Nig. Ltd -N10,189,620.00
Nnamife & Sons Ltd -N10,359,751.50
Kobonkate Int'l Res. Ltd -N10,831,657.20
89 | Supply of Various Brands of Motor Batteries for State Commands and Training Institutions | 22020802 | 56633850 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | STCC Group of Co. Ltd -N9,991,800.00 | STCC Group of Co. Ltd | December, 2011 -N9,991,800.00 | 9991800 | 2011
Dot Net Tech. Ltd -N10,510,762.50
Roc Atlas Nig. Ltd -N10,139,587.50
Velldrom Nig. Ltd -N10,330,582.50
J. Jahanfa & Zar Nig. Ltd -N10,409,962.50
Nadik Nig. Ltd -N10,602,900.00
90 | Supply of Lubricants for State Commands and Training Institutions | 22020802 | 56633850 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Sassada Petroleum Nig. Ltd -N9,997,417.50 | Sassada Petroleum Nig. Ltd | December, 2011 -N9,997,417.50 | 9997417.5 | 2011
Tatu Int. Service Ltd -N10,694,775.00
Team Credit Ltd -N10,090,500.00
Zahiwalu Ventures Ltd -N10,163,569.50
Mic-Jack Nig. Ltd -N10,260,432.00
Dollgate Int. Ventures Ltd -N11,021,220.00
91 | Purchase of Spare Parts for Mechanical Repairs and Periodic Servicing for State Commands and Training Institutions | 22020802 | 56633850 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Sassada Petroleum Nig. Ltd -N9,991,537.50 | Sassada Petroleum Nig. Ltd | December, 2011 -N9,991,537.50 | 9991537.5 | 2011
Haramani Chemical Nig. Ltd -N10,893,643.95
Karama Global Links Ltd -N10,165,365.00
Muhsin Nig. Ltd -N10,202,499.30
Umka Nig. Ltd -N10,550,187.90
92 | Supply of 800 Nos of 1KG, 755 Nos of 2KG and 410 Nos of 6KG Fire Extinquishers to SHQ - Abuja | 22020802 | 56633850 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | STCC Group of Companies Nig. Ltd -N9,998,200.00 | STCC Group of Companies Nig. Ltd | December, 2011 -N9,998,200.00 | 9998200 | 2011
Emprotame Global Nig. Ltd -N10,478,422.50
Kellbridge Universal Vent. Ltd -N10,199,490.00
93 | Supply of 33,418 Nos each of New Arrival and Departure Cards To SHQ - Abuja | 22020605 | 153000000 | National Competitive Bidding | 21st Nov, 2011 Notice Board Advert | Team Credit Ltd -N7,993,204.80 | Team Credit Ltd | December, 2011 -N7,993,204.80 | 7993204.8 | 2011
Encom Ltd -N8,137,035.90
94 | Supply of Badges of Rank for Inspectorate Cadre | 22020309 | 162000000 | National shopping | N/A | Franquin Nig. Ltd- N1,993,005.00 | Franquin Nig. Ltd | December 2011 N1,993,005.00 | 1993005 | 2011
Manotch Nig. Ltd - N2,193,450.00
OP & J Resources Plus Ltd - N2,042,250.00
95 | Supply of Drugs for Staff Clinics at Lagos & Oyo State Commands | 22020307 | 20250000 | National Shopping | N/A | Usmanniya Nig. Ltd - N2,491,685.70 | Usmanniya Nig. Ltd | December 2011 N2,491,685.70 | 2491685.7 | 2011
Gape Biomedical Ent. - N2,564,621.40
Service Quotient Ltd - N2,691,649.40
96 | Printing & Supply of Letter Headed Papers for Commands under Zone 'C' | 22020306 | 90000000 | National Shopping | N/A | Al-Amin Nig. Ltd - N1,993,320.00 | Al-Amin Nig. Ltd | December 2011 - N1,993,320.00 | 1993320 | 2011
Service Quotient Ltd - N2,194,060.00
Amijad Ltd -N2,225,960.00
97 | Supply of Track Event Sporting Equipment | 22021009 | 22500000 | National Shopping | N/A | Brodefe Network Ltd - N2,128,000.00 | Brodefe Network Ltd - | December 2011 -N2,128,000.00 | 2128000 | 2011
Mihur Enterprises -N2,167,000.00
Jofamo Integrated Services - N2,216,500.00
98 | Supply of Mechanical Workshop Tools | 22020803 | 64800000 | National Shopping | N/A | Dollgate Integrated Vent. Ltd - N1,165,000.00 |  | December 2011 - N1,165,000.00 | 1165000 | 2011
Sassada Petroleum Nig. Ltd - N1,221,150.00
Velldrom Nig Ltd - N1,268,925.00
99 | Rehabilitation of Service Hqtrs Fence |  |  | National Shopping | N/A | Al-Haiyya Nig. Ltd - N1,512,040.00 | Al-Haiyya Nig. Ltd | December 2011 - N1,512,040.00 | 1512040 | 2011
Ameen Int'l Nig. Ltd - N1,956,330.00
Tropical Aires Ltd - N2,072,050.00
100 | Supply of Badges of Rank for Comptroller Cadres | 22020309 | 162000000 | National Shopping | N/A | Yeabikay Nig. Ltd - N1,992,060.00 | Yeabikay Nig. Ltd | December 2011 - N1,992,060.00 | 1992060 | 2011
Solid Concrete Nig. Ltd- N2,178,750.00
Peace & Praise Nig. Ltd - N2,262,750.00
101 | Supply of Field Event Sporting Equipment | 22021009 | 22500000 | National Shopping | N/A | Brodefe Network Ltd - N2,200,997.00 | Brodefe Network Ltd | December 2011 - N2,200,997.00 | 2200997 | 2011
Clindorax Nig. Ltd - N2,242,460.00
Mihur Enterprises -N2,295,810.00
102 | Supply of Badges of Rank for Superintendent Cadres | 22020309 | 162000000 | National Shopping | N/A | Tatt -Tale enterprises - N1,992,532.50 | Tatt -Tale enterprises | December 2011 - N1,992,532.50 | 1992532.5 | 2011
Jofamo Integrated Services - N2,134,000.00
Amijad Ltd - N2,252,200.00
103 | supply of Lubricants to Service Hqtrs | 22020708 | 199800000 | National Shopping | N/A | Zahiwalu Vent. Nig. Ltd- N2,498,000.00 | Zahiwalu Vent. Nig. Ltd | December 2011 - N2,498,000.00 | 2498000 | 2011
J. Jahanfa & Zar Nig. Ltd - N2,520,157.50
Marsarat Vent. Nig. Ltd - N2,592,597.00
104 | Supply of 2nos Tarpauline Tents to Service Hqtrs | 22020308 | 89100000 | National Shopping | N/A | Chifrang Nig. Ltd -N897,225.00 | Chifrang Nig. Ltd | December 2011 - N897,225.00 | 897225 | 2011
Mihur Enterprises - N942,900.00
Shua & Sons Enterprises- N1,046,850.00
105 | Supply of Electrical Fittings to Service Hqtrs | 22020201 | 22500000 | National Shopping | N/A | Omek Concept Ltd - N1,994,265.00 | Omek Concept Ltd | December 2011 - N1,994,265.00 | 1994265 | 2011
Opire Vent. Nig. Ltd- N2,069,100.00
Sam David Diverse Concept -N2,157,100.00
106 | Supply of Rechargeable Lamps to Service Hqtrs | 22020308 | 89100000 | National Shopping | N/A | Peace & Praise Nig. Ltd - N989,625.00 | Peace & Praise Nig. Ltd | December 2011 - N989,625.00 | 989625 | 2011
OP & J Resources Plus Ltd - N1,097,775.00
Clindorax Nig. Ltd - N1,134,000.00
107 | Supply of Reflective Vests to Service Hqtrs | 22020308 | 89100000 | National Shopping | N/A | OP & J Resources Plus Ltd - N1,990,296.00 | OP & J Resources Plus Ltd | December 2011 - N1,990,296.00 | 1990296 | 2011
Peace & Praise Nig. Ltd - N2,132,856.00
Jofamo Integrated Services Ltd - N 2,154,460.00
108 | Printing & Supply of Letter Headed Paper one 'D' Niger State | 22020306 | 90000000 | National Shopping | N/A | Service Quotient Ltd - N1,991,535.00 | Service Quotient Ltd | December 2011 - N1,991,535.00 | 1991535 | 2011
Tatu Integrated Service Ltd - N2,105,620.00
Usmanniya Nig. Ltd - N2,227,280.00
109 | Supply of Badges of Rank for Comptroller Cadre | 22020309 | 162000000 | National Shopping | N/A | Mihafe Ltd - N1,994,475.00 | Mihafe Ltd | December 2011 - N1,994,475.00 | 1994475 | 2011
Roc Atlas Nig. Ltd- N2,181,900.00
Solid Concrete Industries Ltd - N2,272,725.00
110 | Supply of Motor Vehicle Lubricants for Zone 'A' Lagos | 22020401 | 112500000 | National Shopping | N/A | Jofamo Integrated Services Ltd - N 1,491,650.00 | Jofamo Integrated Services Ltd | December 2011 - N 1,491,650.00 | 1491650 | 2011
STCC Ltd -N1,557,600.00
Dot Net Tech. Ltd -N1,640,540.00
111 | Supply of Lubricants for Zone 'B' Kaduna | 22020401 | 112500000 | National Shopping | N/A | Mindcraft Global Invt. Ltd -N995,673.00 | Mindcraft Global Invt. Ltd | December 2011 - N N995,673.00 | 995673 | 2011
Jofamo Integrated Services Ltd - N1,090,650.00
Mumiri Nig. Ltd -N1,176,615.00
112 | Supply of Badges of Rank for Comptroller Cadre | 22020309 | 162000000 | National Shopping | N/A | Manotch Nig. Ltd - N1,995,840.00 | Manotch Nig. Ltd | December 2011 - N N1,995,840.00 | 1995840 | 2011
Tatt -Tale enterprises - N2,137,080.00
Shua & Sons Enterprises- N2,234,000.00
113 | Supply of Flash Drives to SHQ | 22020301 | 103000000 | National Shopping | N/A |  | Mindcraft Global Invest Ltd | December 2011 - N997,710.00 | 997710 | 2011
Mindcraft Global Invest Ltd N997,710.00
114 | Supply of Sroll Pepers to SHQ | 22020301 | 103000001 | National shopping | N/A | Jofamo Intergrated Serv. Ltd N2377,777.00 | Jofamo Intergrated Serv. Ltd | December 2011 - N2377,777.00 | 2377777 | 2011
Dexterite Interg. Serv. Ltd N2,577,000.00
Shua & Sons Enterp. N2,519,000.00
115 | Supply of Laptop Computers To SHQ | 22020605 | 153000000 | National shopping | N/A |  | Maane Services | December 2011 - N2,500,000.00 | 2500000 | 2011
Maane Services N2,500,000.00
116 | Printing and Supply of Letter Headed Papers for Zone 'H' | 22020306 | 90000000 | National shopping | N/A |  | Velldrom Nig Ltd - | December 2011 - N1,991,535.00 | 1991535 | 2011
Velldrom Nig Ltd - N1,991,535.00
117 | Supply of Rechargeable Lamps with Extra Batteries to Service Hqtrs | 22020405 | 63000000 | National shopping | N/A |  | Solid Concrete Ind. Ltd | December 2011 - N2,249,000.00 | 2249000 | 2011
Solid Concrete Ind. Ltd N2,249,000.00
1012910599.14

## Nigeria Police
PROCUREMENT RECORDS
| PROCURING ENTITY (MDA). | POLICE FORMATIONS & CAMMAND
| MINISTRY: | POLICE AFFAIRS
| FINANCIAL YEAR: | 2011
| BASIC DATA |  |  |  |  | CONTRACT AWARD | [5 empty] | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | ADVERTISMENT DATE AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | CONTRACTOR | DATE OF CONTRACT AWARD | DATE OF CONTRACT COMMENCEMENT | CONTRACT PERIOD | CONTRACT VALUE (N) | BUDGETARY PROVISION (N) | AMOUNT PAID AS AT | EXPECTED COMPLETION DATE | % OF COMPLETION AS AT | REMARKS
1 | ARMS AND AMMUNITIONS | Selective Inivitation | FHQTB | Selective Tendering | 2011-04-25 | M/S ASTROD LTD | 15/11/2011 | 15/11/2011 | 8 week | 49852425 | 175626834 | 49852425 | January, 2012 | 100%
|  | Selective Inivitation | FHQTB | Selective Tendering | 2011-04-25 | M/S E & S TECHNOLOGY LTD | 15/11/2011 | 15/11/2011 | 8 week | 49896000 |  | 49896000 | '' | 100%
|  | Selective Inivitation | FHQTB | Selective Tendering | 2011-04-25 | M/S OHTECH ENT. LTD | 15/11/2011 | 15/11/2011 | 8 week | 49829472 |  | NIL | '' | 60%
2 | RIOT CONTROL EQUIPMENT | Selective Inivitation | FHQTB | Selective Tendering | 2011-04-25 | M/S OHTECH ENT. LTD | 2011-11-15 | 2011-11-15 | 8 week | 39563543 | 34531253 | NIL | '' | 60%
3 | BULLET PROOF VEST AND BALLISTIC HELMET | Selective Inivitation | FHQTB | Selective Tendering | 2011-04-25 | M/S OHTECH ENT. LTD | 2011-11-15 | 2011-11-15 | 8 week | 49075950 | 101254410 | NIL | '' | 60%
|  | Selective Inivitation | FHQTB | Selective Tendering | 2011-04-25 | M/S OHTECH ENT. LTD | 2011-11-15 | 2011-11-15 | 8 week | 43356936 |  | NIL | '' | 60%
1 | Establishment and Equipping of Veterinary Clinics in Six Locations (kaduna, Enugu, Jos, Sokoto, Ilorin and Port-Harcourt) | Daily Trust 20th June 2011 | IGP Threshold | open Method | 24th November 2011 | Toyin Investment Ltd, Tunsoye & Son, Eto Inter Bis, Mode Ventures, Nicotina Invest. Nig. Ltd and Cynthia Odiase Ent. | 16th November,2011 | 2011 project 1/1/2011 to 3 1/12/2011 | On-Going Project | 16744390 | 1198000 | payment documents forwarded through the Minister of police Affairs Capital Payments | 2013 | 100% completed | Inadeguate funfing
2 | Establishment /Development of Police Veterinary Dogs Breeding Centre FHQ Abuja | Daily Trust 20th June 2011 | IGP Threshold | open Method | 24th November 2011 | Toyin Investment Ltd, Tunsoye & Son, Eto Inter Bis, Mode Ventures, Nicotina Invest. Nig. Ltd and Cynthia Odiase Ent. | 16th November,2011 | 2011 project 1/1/2011 to 3 1/12/2011 | On-Going Project | 10802832 | 168000000 | payment documents forwarded through the Minister of police Affairs Capital Payments | 2013 | 100% completed | Inadeguate funfing
3 | Establishment /Development of Police Veterinary Diagnostic Laboratory /Radiology FHQ Abuja | Daily Trust 20th June 2011 | IGP Threshold | open Method | 24th November 2011 | Toyin Investment Ltd, Tunsoye & Son, Eto Inter Bis, Mode Ventures, Nicotina Invest. Nig. Ltd and Cynthia Odiase Ent. | 16th November,2011 | 2011 project 1/1/2011 to 3 1/12/2011 | On-Going Project | 15123965 | 165000000 | payment documents forwarded through the Minister of police Affairs Capital Payments | 2013 | 100% completed | Inadeguate funfing
1 | Horses feeds and part payment of 2010 Capital Projects liability | Daily Trust 20th June 2011 | IGP Threshold | open Method | 24th November 2011 | 2011 contractor M/S Cynthia Odiase Ent. 2010 Liability contractors M/S Toyin Invest Ltd. 2.) Fullfilled Nig. Ltd. | 16th November,2011 | 2011 project 1/1/2011 to 3 1/12/2011 2010 liability project 1/1/2010 to 31/12/2010 | On-Going Project | 26640324 | 26640324 | All payments are in progress through the Minister of police Affairs Capital Payments | 2011 project 3 1/12/2011 2010 liability project 31/12/2010 | 100% completed | Inadequate funds Details: 0n 30th April, 2010 N100,000,000.00 was appropriated to Mounted Troop Section. Base on this amount, contract was awarded and executed. On 7/9/2010 amendment appropriation of N49,500,000.00 was released, now we are indebted to the tune of N50,500,000.00 balance refer to ON-GOING PROJECTS IN 2012.
1 | Equiping the Anti-Terrorism Squad |  | IGP/FHQ | SELECTIVE TENDERING | 17/10/2011 | messrs Magat Nig. Ltd. | 16/11/2011 | 17/11/2011 | 8 weeks | 2,249,998,00 | 73842759 | NIL | DEC. 2011 | 100% | Payment not effected yet.
2 | do |  | do | do | do | Messrs Fodacis Technical c. Ltd. | do | do | do | 16957025 | do | do | do | do | do
3 | do |  | do | do | do | do | do | do | do | 29792475 | do | do | do | do | do
4 | do |  | do | do | do | messrs Magat Nig. Ltd. | do | do | do | 3809520 | do | do | do | do | do
5 | do |  | do | do | do | messrs Magat Nig. Ltd. | do | do | do | 3069990 | do | do | do | do | do
6 | do |  | do | do | do | messrs matem ventures Ltd | do | do | do | 799,963,00 | do | do | do | do | do
7 | do |  | do | do | do | messrs Magat Nig. Ltd. | do | do | do | 3499650 | do | do | do | do | do
8 | do |  | do | do | do | do | do | do | do | 4099725 | do | do | do | do | do
9 | do |  | do | do | do | do | do | do | do | 3599820 | do | do | do | do | do
10 | do |  | do | do | do | do | do | do | do | 3227795 | do | do | do | do | do
1 | Yanmar Marine Engine Sterndrive (STP -300MX) |  | FHQ | Selective | 2011-11-14 | Messrs Toyin Investment Nig. Ltd | 16 November, 2011 | 16 November, 2011 | 2011 | 41010000 | 63928438 | Nil | March, 2012 | 100% | Payment processing in progress at MPA
2 | Man - diesel Marine Engine Sterndrive (STP -400H) |  | FHQ | Selective |  | Messrs Sem – Luk Ventures Ltd., |  |  |  | 22915800
3 | Purchase of various Horse Power Yamaha Outboard Engines |  | FHQ | Selective | 1 December, 2011 | M/s Trackstel Nig. Ltd. | 15 December, 2011 | 15 December, 2011 | 2011 | 40640000 | 177285319 | Nil | March, 2012 | 100% | Payment documentation in progress
4 |  |  | FHQ | Selective |  | M/s Silver Team Ltd. |  |  |  | 48255000
5 |  |  | FHQ | Selective |  | M/s Cox Projects Ltd. |  |  |  | 47747000
6 |  |  | FHQ | Selective |  | M/s Chobs Nig. Ltd. |  |  |  | 40640000
1 | INSTALLATION OF Digital security surveillance system. | Under the Ministry of Police Affairs procurement process is ongoing | Ministerial Threshold | Procurement process is on going | Procurement process is on going | Procurement process is on going | Procurement process is on going | Procurement process is on going | Jan to Dec, 2011 | 245794500 | 146835867 | Procurement process is on going | Procurement process is on going | Procurement process is on going
2 | Procurement of 28 Nos Digital UHF Motorola Base Radio Transceiver (3401) | 27th June, 2011- 10th July,2011 Federal Tenders Journal | Force Headqurters Threshold | Open biding | 2nd Nov, 2011 | Messrs Isiuwa General Ventures | 16th Nov, 2011 | 17th Nov, 2011 | Jan to Dec, 2011 | 8775900 | 69532623 | Payment still in process | March, 2012 | 98
3 | Procurement of 100 Nos 30 AMP Battery Chargers | 27th June, 2011- 10th July,2011 Federal Tenders Journal | Force Headqurters Threshold | Open biding | 2nd Nov, 2011 | Messrs Fast Track Engineering Ltd | 16th Nov, 2011 | 17th Nov, 2011 | Jan to Dec, 2011 | 5250000 | 69532623 | Payment still in process | March, 2012 | 98
4 | Procurement of 70 Nos Charge Controllers | 27th June, 2011- 10th July,2011 Federal Tenders Journal | Force Headqurters Threshold | Open biding | 2nd Nov, 2011 | Mesrs Vodaro Nigeria Ltd | 16th Nov, 2011 | 17th Nov, 2011 | Jan to Dec, 2011 | 2058000 | 63532623 | Payment still in process | March, 2012 | 98
5 | Procurement of 350 Nos of ICOM spare chargers | 27th June, 2011- 10th July,2011 Federal Tenders Journal | Force Headqurters Threshold | Open biding | 2nd Nov, 2011 | Messrs Benaebi Ventures Ltd | 16th Nov, 2011 | 17th Nov, 2011 | Jan to Dec, 2011 | 3999995 | 63532623 | Payment still in process | March, 2012 | 98
6 | Supply of 15 Nos AATRA Digital Telephone | 27th June, 2011- 10th July,2011 Federal Tenders Journal | Force Headqurters Threshold | Open biding | 2nd Nov, 2011 | Messrs Kankesifa Nigeria Ltd | 16th Nov, 2011 | 17th Nov, 2011 | Jan to Dec, 2011 | 1890000 | 63532623 | Payment still in process | March, 2012 | 98
7 | Supply of 40 Nos 200 Amp/Hr Deep Cycle Batteries | 27th June, 2011- 10th July,2011 Federal Tenders Journal | Force Headqurters Threshold | Open biding | 2nd Nov, 2011 | Messrs Jesse Jordan Investment Company Ltd | 16th Nov, 2011 | 17th Nov, 2011 | Jan to Dec, 2011 | 4011000 | 65532623 | Payment still in process | March, 2012 | 98
8 | Procurement of 50 Nos Battery Tester | 27th June, 2011- 10th July,2011 Federal Tenders Journal | Force Headqurters Threshold | Open biding | 2nd Nov, 2011 | Messrs Toyin Investment Ltd | 16th Nov, 2011 | 17th Nov, 2011 | Jan to Dec, 2011 | 5145000 | 63532623 | Payment still in process | March, 2012 | 98
9 | Procurement of 35 Nos Digital Motorola UHF Base Radios (3601) with all its accessories and the procurement of 10 Nos of CODAN HF Base Voice only with its accessories | 27th June, 2011- 10th July,2011 Federal Tenders Journal | Force Headqurters Threshold | Open biding | 2nd Nov, 2011 | Messrs Ringim Gadanci Nigeria Ltd | 16th Nov, 2011 | 17th Nov, 2011 | Jan to Dec, 2011 | 29742000 | 50869456 | Payment still in process | March, 2012 | 98
10 | Supply of 15 Nos ICOM HF Transceiver with its accessories | 27th June, 2011- 10th July,2011 Federal Tenders Journal | Force Headqurters Threshold | Open biding | 2nd Nov, 2011 | Messrs Grammercathy Ent. Ltd | 16th Nov, 2011 | 17th Nov, 2011 | Jan to Dec, 2011 | 9922500 | 50869456 | Payment still in process | March, 2012 | 98
11 | Procurment of 55 Nos Digital Power Supply Unit with Accessories procurement of 500 Nos Kenwood spare Chargers | 27th June, 2011- 10th July,2011 Federal Tenders Journal | Force Headqurters Threshold | Open biding | 2nd Nov, 2011 | Messrs Asmoy Resources Ltd | 16th Nov, 2011 | 17th Nov, 2011 | Jan to Dec, 2011 | 10106250 | 50869456 | Payment still in process | March, 2012 | 100
1 | AUTOMATED FINGERPRINT IDENTIFICATION SYSYTEM TRACKER | 16TH MARCH, 2010 IN FEDERAL JORNAL | IG THRESHOLD | SELECTIVE TENDER | 2011-11-30 | TELEMOBILE NIG. LTD. | 2011-12-20 | 2011-12-20 | 2011 | 25,294,077,25 | 25,294,077,25 | 19153941 | WITHIN 2WEEKS (JAN) 2012 | - | INADEAQUATE FUNDING
2A | PROVISION OF DNA TEST LABORATORY | FEDERAL JOURNAL MARCH 2010 | IG THRESHOLD | SELECTIVE TENDERING | 2011-11-29 | TOYIN INVESTMENT LTD | 30/11/2011 | 2011-11-30 | 2011 | 49880054 | 67517701 | 49,88,054 | WITHIN 2WEEKS (DEC) 2011 | -
2B | PROVISION OF DNA TEST LABORATORY PEAGENTS AND KITS | FEDERAL JOURNAL MARCH 2010 | IG THRESHOLD | SELECTIVE TENDERING | 2011-11-30 | SKYVIEW INTEGRATE MULTI CONCEPT LTD | 30/11/2011 | 2011-11-30 | 2011 | 17637647 |  | 17637647 | DEC. 2011
3A | SUPPLY OF FORENSIC EQUIPMENT | FEDERAL JOURNAL MARCH 2010 | IG THRESHOLD | SELECTIVE TENDERING | 2011-12-01 | GRACE LAND GLOBAL LTD | 30/11/2011 | 2011-11-30 | 2011 | 14223003 | 54446274 | - | 2011-11-30
3B | SUPPLY OF FORENSIC EQUIPMENT CRIME SCENE SUITES etc. | FEDERAL JOURNAL MARCH 2010 | IG THRESHOLD | SELECTIVE TENDERING | 2011-11-30 | SEM LUX LTD | 30/11/2011 | 2011-11-30 | 2011 | 40223273 | - | 40223273
1 | Procurement of BMW Motorcycles configured to Police Specification including Rider's Kit. |  | FHQ. Abuja | TPT/116/2011, TPT/96/2011 | JAN. 2011 | DEC. 2011 | 61535632 | 61535632 | NIL. |  | 45460681 | 61535632
2 | MPA/Proc/Cap/1787/Vol.1/27DD Ford Rangers |  | FHQ. Abuja | TPT/118/2011, TPT/138/2011 | 2010 | DEC. 2011 | 600000000 | 600000000 | NIL. |  | 443262017 | 600000000
3 | Purchase of Patrol Vehicles (Pick-ups, Patrol Jeeps, Patrol Cars, Canine Patrol Vans) with installed Communication Equipment. |  | FHQ. Abuja | TPT/94/2011, TPT/109/2011, TPT/112/2011, TPT/93/2011, TPT/110/2011 | JAN. 2011 | DEC. 2011 | 168520765 | 168520765 | NIL. |  | 124498090 | 168520765
4 | Purchase of Scene of Crime Vehicle (4x4 V8 5.4 Litres engine) |  | FHQ. Abuja | TPT/99/2011, TPT/122/2011, TPT/121/2011. | JAN. 2011 | DEC. 2011 | 73227403 | 73227403 | NIL. |  | 54098211 | 73227403
5 | Procurement of Armoured Personnel Carriers (APCs) |  | FHQ. Abuja | TPT/100/2011 | JAN. 2011 | DEC. 2011 | 21605664 | 21605664 | NIL. |  | 15961617 | 21605664
6 | Police Armored Typhoon on ford F-150/350 Pick-up Chassis. |  | FHQ. Abuja | TPT/135/2011, TPT/86/2011, TPT/137/2011, TPT/124/2011, TPT/130/2011, TPT/128/2011, TPT/91/2011, TPT/87/2011, TPT/90/2011, TPT/134/2011, TPT/131/2011, TPT/126/2011, TPT/136/2011 | JAN. 2011 | DEC. 2011 | 1739306915 | 1739306915 | NIL. |  | 1284947819 | 1739306915
7 | Procurement of Armoured Patrol Vans (APVs). |  | FHQ. Abuja |  | JAN. 2011 | DEC. 2011 | 192866321 | 192866321 | NIL. |  | 142483857 | 192866321
8 | Purchase of Operational Vehicles (Specialized) - Lorries, Unimog Trucks, Mobile Workshop Vehicles, H/Duty Recovery Vehicles, Comms. Maintenance Vehicles, Ambulances, Veterinary Ambulatory Van. |  | FHQ. Abuja | TPT/132/2011, TPT/96/2011. | JAN. 2011 | DEC. 2011 | 47413031 | 47413031 | NIL. |  | 35027327 | 35027327
1 | PROCUREMENT OF HOSPITAL EQUIPMENT (DIAGNOSTIC & THERAPEUTIC ITEMS) | 27 June 2011, Federal Tenders' Journal | 50000000 | Open Tender | 2011-08-11 | To be finalised | To be finalised | N/A | Jan 2011-Mar 2012 |  | 113594921 | Nil | 2012-03-01 | 0% | To be completed by March 2012
1 | LAND SURVEY, COMPENSATION, VALUATION OF LANDED AND FIXED ASSESTS INCLUDING OUTSTANDING LIABILITIES | FEDERAL TENDERS JOURNAL of 27-June-2011 to 10-July-2011 THE PUNCH & DAILY TRUST - 20th June, 2011 | NPF | Due Process |  | M/s Simon Okeke & Associate |  |  |  | 74264304.5 | 45371895 | Nil | 2011-2013
2 | COMPLETION/CONSTRUCTION OF OFFICE COMPLEX FOR NIGERIA POLICE CENTER FOR POLICY, PLANNING AND RESEARCH (CPPR) OBIAKPU, EGBEMA, IMO STATE | FEDERAL TENDERS JOURNAL Vol. 6 No. 5 of Monday, March 8 – Sunday, March 21, 2010; and two National Dailies – Punch and Daily Trust of March 8, 2010 | NPF | Due Process | Tuesday 13th July, 2010 | M/s Dutse-Alah Constr. Company, M/s Kenfort Constr. Company Ltd., M/s Bodmak Agencies | 2010 | 2010 | On-going | 174697076.9 | 108028321 | Nil | 2010-2012
3 | CONSTRUCTION OF POLICE COLLEGE OF INFORMATION TECHNOLOGY ABEOKUTA (2ND PHASE) | FEDERAL TENDERS JOURNAL Vol. 6 No. 5 of Monday, March 8 – Sunday, March 21, 2010; and two National Dailies – Punch and Daily Trust of March 8, 2010 | NPF | Due Process | Tuesday 13th July, 2010 | Messrs Tunjums (Nig.) Ltd. | 2010 | 2010 | On-going | 50015694.23 | 34569063 | Nil | 2010-2012
4 | CONSTRUCTION OF WORKS TRAINNING SCHOOL, DEIDEI-ABUJA | FEDERAL TENDERS JOURNAL Vol. 6 No. 5 of Monday, March 8 – Sunday, March 21, 2010; and two National Dailies – Punch and Daily Trust of March 8, 2010 | NPF | Due Process | Tuesday 13th July, 2010 | M/s Kemat Nigeria Ltd. | 2010 | 2010 | On-going | 148434122.59 | 58065223 | Nil | 2010-2012
5 | COMPLETION OF POLICE QUARTERS AND POST AT OWELLI AWGU, ENUGU STATE POLICE COMMAND | FEDERAL TENDERS JOURNAL of 27-June-2011 to 10-July-2011 THE PUNCH & DAILY TRUST - 20th June, 2011 | NPF | Due Process | 10th November, 2011 | M/s Trusty Investment Nig. Ltd., M/s Tonfraco Nig. Enterprises | 2011 | 2011 | 2011-2013 | 54175255 | 130000000 | Nil | 2011-2013
6 | ESTABLISHMENT OF NIGERIA POLICE PEACEKEEPING TRAINING SCHOOL DEI-DEI ABUJA |  | NPF | Due Process | 2009 | M/s Abay Construction | 2009 | 2009 | On-going | 47404990.95 | 43211328 | Nil | 2009-2012 | 50%
7 | ESTABLISHMENT AND EQUIPING OF VETERINARY CLINICS IN SIX LOCATIONS (KADUNA, ENUGU, JOS, SOKOTO, ILORIN AND YOLA) | FEDERAL TENDERS JOURNAL of 27-June-2011 to 10-July-2011 THE PUNCH & DAILY TRUST - 20th June, 2011 | NPF | Due Process | 2011 | Messrs. Sokud Enterprises | 2011 | 2011 | 2011-2013 | 19986530.38 | 16744390 | Nil | 2008-2012
8 | COMPLETION OF POLICE HOSPITAL AT LIFE CAMP, ABUJA INCLUDING PAYMENT OF OUTSTANDING LIABILITY |  | NPF | Due Process | 2005 | M/s Basilica Ltd. | 2005 | 2005 | On-going | 172812410.84 | 43211328 | Nil | 2005-2012 | 50%
9 | CONSTRUCTION OF POLICE PRIMARY AND SECONDARY SCHOOLS | FEDERAL TENDERS JOURNAL Vol. 6 No. 5 of Monday, March 8 – Sunday, March 21, 2010; and two National Dailies – Punch and Daily Trust of March 8, 2010 | NPF | Due Process | Tuesday 13th July, 2010 | M/S Alliance Logistics Ltd., M/s Channel Engineering Co. Ltd., M/s First Construction Co. Ltd. | 2010 | 2010 | On-going | 430000000 | 114780091 | Nil | 2010-2012 | 60%
10 | POLICE COLLEGE WUDIL | FEDERAL TENDERS JOURNAL of 27-June-2011 to 10-July-2011 THE PUNCH & DAILY TRUST - 20th June, 2011 | NPF | Due Process | 10th November, 2011 | M/s Patok General Construction Ltd., M/s T. Tience Nig. Ent., M/s Hamdala Inter. Serv. Ltd., M/s Radio Sounders Nig. Ltd., M/s Okiky Invest. Ltd., M/s Yamsa Invest. & Property Ltd. | 2011 | 2011 | 2011-2013 | 224380000 | 300000000 | Nil | 2011-2013
11 | CONSTRUCTION/REHABILITATION OF STAFF QUARTERS & BARRACKS | FEDERAL TENDERS JOURNAL of 27-June-2011 to 10-July-2011 THE PUNCH & DAILY TRUST - 20th June, 2011 | NPF | Due Process | 10th November, 2011 | See Appendix 'A' | 2011 | 2011 | 2011-2013 | 3791601514.65 | 92637919 | Nil | 2011-2013
12 | PROVISION OF OBSERVATION POSTS ALONG MAJOR HIGHWAYS NATIONWIDE | FEDERAL TENDERS JOURNAL of 27-June-2011 to 10-July-2011 THE PUNCH & DAILY TRUST - 20th June, 2011 | NPF | Due Process | 10th November, 2011 | M/s Glory Engr. Resources Ltd., M/s Treasure Achievers Tech. Ltd. | 2011 | 2011 | 2011-2013 | 13019596.97 | 34569063 | Nil | 2011-2013
13 | CONSTRUCTION OF OFFICE ACCOMMODATION AND POLICE STATIONS NATIONWIDE | FEDERAL TENDERS JOURNAL of 27-June-2011 to 10-July-2011 THE PUNCH & DAILY TRUST - 20th June, 2011 | NPF | Due Process | 10th November, 2011 | See Appendix 'B' | 2011 | 2011 | 2011-2013 | 1430552693.92 | 100266496 | Nil | 2011-2013
14 | CONSTRUCTION OF MOBILE POLICE BARRACKS IN LAFIA, NASARAWA STATE | [9 empty] | 75619825 | Nil
15 | CONSTRUCTION OF 48 PMF BARRACKS AT OKWUZU EGBEMA, RIVERS STATE | FEDERAL TENDERS JOURNAL Vol. 6 No. 5 of Monday, March 8 – Sunday, March 21, 2010; and two National Dailies – Punch and Daily Trust of March 8, 2010 | NPF | Due Process | Tuesday 13th July, 2010 | M/s Tyse Ltd., M/s Chikorie Enterprises, M/s Matem Ventures Ltd., M/s Ponzeal Investment | 2010 | 2010 | On-going | 145712715.98 | 32408496 | Nil | 2010-2013 | 30%
16 | CONSTRUCTION OF MOUNTED TROOP PERSONNEL BARRACKS, OFFICES, STABLES, FURNISHING AND INFRASTRUCTURE - FHQ ABUJA | FEDERAL TENDERS JOURNAL Vol. 6 No. 5 of Monday, March 8 – Sunday, March 21, 2010; and two National Dailies – Punch and Daily Trust of March 8, 2010 | NPF | Due Process | Tuesday 13th July, 2010 | M/s Al-has Global Vent. Nig. Ltd., M/s Drairose Nig. Ltd. | 2010 | 2010 | On-going | 186508354.95 | 49693028 | Nil
17 | CONSTRUCTION OF FORCE HEADQUARTERS DOG SECTION BARRACKS, OFFICES, KENNELS, FURNISHING AND INFRASTRUCTURE (INCLUDING PERIMETER FENCING) ABUJA | FEDERAL TENDERS JOURNAL Vol. 6 No. 5 of Monday, March 8 – Sunday, March 21, 2010; and two National Dailies – Punch and Daily Trust of March 8, 2010 | NPF | Due Process | Tuesday 13th July, 2010 | M/s Al-has Global Vent. Nig. Ltd., M/s Remove Nig. Ltd. | 2010 | 2010 | On-going | 104824832.03 | 51853594 | Nil | 2010-2012
18 | UPGRADING OF POLICE BARRACKS AT DEI-DEI INCLUDING PROVISION OF INFRASTRUCTURAL FACILITIES, ROAD NETWORK, WATER, ELECTRICTY, ETC. | FEDERAL TENDERS JOURNAL Vol. 6 No. 5 of Monday, March 8 – Sunday, March 21, 2010; and two National Dailies – Punch and Daily Trust of March 8, 2010 | NPF | Due Process | Tuesday 13th July, 2010 | M/s Modmak Ltd, M/s Abay Construction | 2010 | 2010 | On-going |  | 111931777 | Nil | 2010-2012
19 | CONSTRUCTION OF HELIPAD IN 6 LOCATIONS: OTUKPO, FUGAR, YOLA, RINGIM,ABEOKUTA AND ELEWERAN OBALUFE WITH INFRASTUCTURES AND BRIDGES. | FEDERAL TENDERS JOURNAL Vol. 6 No. 5 of Monday, March 8 – Sunday, March 21, 2010; and two National Dailies – Punch and Daily Trust of March 8, 2010 | NPF | Due Process | Tuesday 13th July, 2010 | M/s J.B Maye Property Dev. Ltd., M/s Cordquote Engineering Ltd., M/s Sia Salon Nig. Ltd. | 2010 | 2010 | On-going | 540000000 | 400000000 | Nil | 2010-2012
20 | POLICE STATIONS AND BARRACK | [9 empty] | 177285319 | Nil
21 | NAFADA POLICE BARRACKS | FEDERAL TENDERS JOURNAL Vol. 6 No. 5 of Monday, March 8 – Sunday, March 21, 2010; and two National Dailies – Punch and Daily Trust of March 8, 2010 | NPF | Due Process | Tuesday 13th July, 2010 | M/S Adveron International, M/S Adebec Ventures | 2010 | 2010 | On-going | 82500000 | 98891967 | Nil | 2010-2012
22 | DUKKU POLICE STATION | FEDERAL TENDERS JOURNAL Vol. 6 No. 5 of Monday, March 8 – Sunday, March 21, 2010; and two National Dailies – Punch and Daily Trust of March 8, 2010 | NPF | Due Process | Tuesday 13th July, 2010 | M/S Rova Divine Resourcess Ltd, M/s Raov Ventures | 2010 | 2010 | On-going | 82500000 | 44321330 | Nil | 2010-2012
23 | CONSTRUCTION OF JETTIES AT MAKURDI IN BENUE, YAURI IN KEBBI, BAGA IN BORNO AND LOKOJA IN KOGI | FEDERAL TENDERS JOURNAL of 27-June-2011 to 10-July-2011 THE PUNCH & DAILY TRUST - 20th June, 2011 | NPF | Due Process | 10th November, 2011 | M/s Tee Pama Nig. Ltd., M/s Abog Engr. Ltd. | 2011 | 2011 | 2011-2013 | 189462275.5 | 89663506 | Nil | 2011-2013
24 | COMPLETION OF STATE HQ COMPLEX IN DAMATURU YOBE STATE, DUTSE JIGAWA STATE, JALINGO TARABA STATE, ZONE 4 HQ MAKURDI AND ZONE 9 HQ UMUAHIA | [9 empty] | 100639184 | Nil | 2011-2013
25 | REHABILITATION AND CONSTRUCTION OF INDOOR SHOOTING RANGES | FEDERAL TENDERS JOURNAL Vol. 6 No. 5 of Monday, March 8 – Sunday, March 21, 2010; and two National Dailies – Punch and Daily Trust of March 8, 2010 | NPF | Due Process | Tuesday 13th July, 2010 | M/S Olaniyi Popoola Nigeria Ltd., M/S Puristic Adherent Co. | 2010 | 2010 | On-going | 24850870.5 | 25926797 | Nil | 2010-2012
26 | ESTABLISHMENT OF NIGERIA POLICE VOCATIONAL AND RESETTLEMENT TRAINING CENTRE, AKPUGO, ENUGU STATE | - | - | - | - | - | - | - | - | - | 74374474 | Nil | 2010-2012
27 | REHABILITATION AND UPGRADE OF POLICE PRINTING PRESS IN LAGOS | FEDERAL TENDERS JOURNAL of 27-June-2011 to 10-July-2011 THE PUNCH & DAILY TRUST - 20th June, 2011 | NPF | Due Process | 10th November, 2011 | M/s Titan Integrated Services Ltd | 2011 | 2011 | 2011-2013 | 38865890.7 | 39676642 | Nil | 2011-2013
28 | REHABILITATION OF POLICE QUARTERS OWODE YEWA | FEDERAL TENDERS JOURNAL Vol. 6 No. 5 of Monday, March 8 – Sunday, March 21, 2010; and two National Dailies – Punch and Daily Trust of March 8, 2010 | NPF | Due Process | Tuesday 13th July, 2010 | Messrs. Bojavic Global Resources | 2010 | 2010 | On-going | 9573025 | 26592798 | Nil | 2010-2012
29 | REHABILITATION AND CONSTRUCTION OF POLICE COTTAGE HOSPITAL 20 BEDS (BUNGALOW TYPE) INCLUDING THE PROVISION OF MEDICAL EQUIPMENT AND FENCING OF EXISTING POLICE HOSPITALS | FEDERAL TENDERS JOURNAL Vol. 6 No. 5 of Monday, March 8 – Sunday, March 21, 2010; and two National Dailies – Punch and Daily Trust of March 8, 2010 | NPF | Due Process | Tuesday 13th July, 2010 | M/s. Kemat Investment Ltd, M/s Nne-Edak Tech. Co., M/s MJK & MJK Ltd., | 2010 | 2010 | On-going | 54541337.46 | 54850300 | Nil | 2010-2012
30 | REHABILITATION / REPAIRS - POLICE STATIONS / BARRACKS | - |  | - | - | - | - | - | - | - | 156991249 | Nil | 2011-2013
31 | UPGRADE AND REHABILITATION OF JETTIES AT ORON IN AKWA-IBOM, CALABAR IN CROSS-RIVER STATE, OKITIPUPA IN ONDO AND ONIKAN IN LAGOS STATE | - | - | - | - | - | - | - | - | - | 106991249 | Nil | 2011-2013
32 | UPGRADE OF OKUN OWA POLICE STATION OGUN EAST SENATORIAL DISTRICT, OGUN STATE | FEDERAL TENDERS JOURNAL of 27-June-2011 to 10-July-2011 THE PUNCH & DAILY TRUST - 20th June, 2011 | NPF | Due Process | 10th November, 2011 | M/s BOF Multidynamic Ltd. | 2011 | 2011 | 2011-2013 | 11650990.9 | 20000000 | Nil | 2011-2013
33 | UPGRADE OF IDOWU POLICE STATION OGUN EAST SENATORIAL DISTRICT, OGUN STATE | FEDERAL TENDERS JOURNAL of 27-June-2011 to 10-July-2011 THE PUNCH & DAILY TRUST - 20th June, 2011 | NPF | Due Process | 10th November, 2011 | M/s Anit Synergy Global Co. Ltd. | 2011 | 2011 | 2011-2013 | 11672110.3 | 30000000 | Nil | 2011-2013
34 | UPGRADE OF FACILITIES IN POLICE TRAINING INSTITUTIONS (POLICE COLLEGE IKEJA, KADUNA, MAIDUGURI, OJI-RIVER, POLICE TRAINING SCHOOLS IPERU, IBADAN, NONWA-TAI P/HARCOURT, OYIN-AKOKO, PMF TRAINING SCHOOLS GWOZA AND ILA-OROGUN | FEDERAL TENDERS JOURNAL of 27-June-2011 to 10-July-2011 THE PUNCH & DAILY TRUST - 20th June, 2011 | NPF | Due Process | 10th November, 2011 | M/s Crownage Multi Access Nigeria Ltd., M/s Rordav Concept, M/s Shehu Malamri Nig. Ltd., M/s Julyem Integraged Concept, M/s El-falaki Nig. Ltd, M/s KWAPACHI (NIG.) LTD., M/s Shehu Malamri Nig. Ltd., M/s Daranijo Integrated Services Ltd., M/s Omep Omai Investment Ltd., M/s Shehu Malamri Nig. Ltd., M/s Zain Zailane | 2011 | 2011 | 2011-2013 | 420043247.69 | 116778615 | Nil | 2011-2013
35 | REHABILITATION OF POLICE DETECTIVE COLLEGE, ENUGU | FEDERAL TENDERS JOURNAL Vol. 6 No. 5 of Monday, March 8 – Sunday, March 21, 2010; and two National Dailies – Punch and Daily Trust of March 8, 2010 | NPF | Due Process | Tuesday 13th July, 2010 | M/s Miracle Abund Enterprises, M/s Sensors & Safety Ltd, M/s Ogama Ltd, M/s MJK & MJK Ltd, M/s Toffy Ventures Ltd, M/s Kurtmet Integrated Services Ltd | 2010 | 2010 | On-going | 104336027.91 | 47640490 | Nil | 2010-2012
36 | REHABILITATION OF POLICE BAND BUILDINGS IN 10 LOCATIONS; KANO, KADUNA, SOKOTO, MAIDUGURI, YOLA, IBADAN, IKEJA, PORTHARCOURT, CALABAR, ENUGU, OWERRI AND MAKURDI | FEDERAL TENDERS JOURNAL Vol. 6 No. 5 of Monday, March 8 – Sunday, March 21, 2010; and two National Dailies – Punch and Daily Trust of March 8, 2010 | NPF | Due Process | Tuesday 13th July, 2010 | M/s Winnet Ltd, M/s Waco Impex Nig. Ltd., M/s Hans Investments Ltd., M/s Blazing Stars Ltd., M/s Matem Ventures Ltd | 2010 | 2010 | On-going | 99000000 | 21604664 | Nil | 2010-2012
1 | Procurement of 15Nos HP Desktop Computers | 20/6/2011 in Punch, Vanguard & Dawn N/Papers | FHQ Tenders Board | Open Competitive Bidding | 27/9/2011 | Vodaro Nig Ltd | 16/11/10 | 18/11/2011 | SIX WEEKS | 1779750 | N37,851,672 | NIL | 31/12/2011 | 100 % Completed | Delayed Payment
2 | Purchase of 15Nos DSTV Decoder | “ ” | “ ” | “ ” | “ ” | Mazif Support Inv. Ltd | 16/11/11 | 18/11/2011 | “ ” | 1732500 | N37,851,672 | NIL | 31/12/2011 | 100 % Completed | “ ”
3 | Purchase of 15Nos Toshiba Laptop Computer | “ ” | “ ” | “ ” | “ ” | Satogam Nig. Ltd | 16/11/11 | 18/11/2011 | “ ” | 2520000 | N37,851,672. | NIL | 31/12/2011 | 100 % Completed | “ ”
4 | Supply of 10Nos Dell Projector | “ ” | “ ” | “ ” | “ ” | Sazab Global Ent. | 16/11/11 | 18/11/2011 | “ ” | 2152500 | N37,851,672 | NIL | 31/12/2011 | 100 % Completed | “ ”
5 | Supply of 20Nos HP Laptop Computer | “ ” | “ ” | Open Competitive Bidding | 27/9/2011 | Satogam Nig Ltd | 16/11/11 | 18/11/2011 | “ ” | 3360000 | N37,851,672 | NIL | 31/12/2011 | 100 % Completed | “ ”
6 | Purchase of 3Nos Video Camera | “ ” | “ ” | “ ” | “ ” | Dynamo Concept Ltd | 16/11/11 | 18/11/2011 | “ ” | 3654000 | N37,851,672 | NIL | 31/12/2011 | 100 % Completed | “ ”
7 | Purchase of 2No Sharp Digital Photocopier | “ ” | “ ” | “ ” | “ ” | MAGAT Nig Ltd | 16/11/11 | 18/11/2011 | “ ” | 4935000 | N37,851,672 | NIL | 31/12/2011 | 100 % Completed | “ ”
8 | Supply of 8No Nikon Photo Cameras | “ ” | “ ” | “ ” | “ ” | Dad’s Pride Nig Ltd | 16/11/11 | 18/11/2011 | “ ” | 2568000 | N37,851,672 | NIL | 31/12/2011 | 100 % Completed | “ ”
9 | Supply of Books & Library Materials | “ ” | “ ” | “ ” | “ ” | Satogam Nig Ltd | 16/11/11 | 18/11/2011 | “ ” | 3307080 | N37,851,672 | NIL | 31/12/2011 | 100 % Completed | “ ”
10 | Supply of 25Nos Laser-Jet Colour Photo Printers | “ ” | “ ” | Open Competitive Bidding | 27/9/2011 | Chris-Dennis Commercial Companies Nig Ltd | 16/11/11 | 18/11/2011 | “ ” | 1562500 | N37,851,672 | NIL | 31/12/2011 | 100 % Completed
11 | Conduct of 3-Day Workshop | “ ” | FHQ Tenders Board | Open Competitive Bidding | 27/9/2011 | Media Concept Int’l Ltd | 2016-11-11 | 18/11/2011 | SIX WEEKS | 10145000 | “ ” | NIL | 31/12/2011 | NOT Executed for Lack of FUND | NOT FUND
16 | Purchase of EOD Equiupment | Nil | 11,756,492.00 | Contract | 21/09/2011 | Stiches Prints Nig. Ltd. | 2011 | Jan 2011 | 30 days | 7128192 | 11,756,492.00 | Nil | Dec 2011 | Nil | Money not yet release
| Purchase of Eod Demolition Stores |  |  |  |  | Ashland Security Ltd |  |  |  | 4628300
1 | Establishment and Deployment | "The Nation", Daily | IGP FHQ Tenders | Bidding | 2011-09-22 | Komat Nigeria Ltd | 15/11/2011 | 15/11/2011 | 4 Weeks | 9993375 | 91937840 |  | 31/12/2011 | 90%
| of Police Management Information | Trust & Federal Tender | Board
| Technology System in Police | Journal dated June
| Formations, Commands & Training Institutions | 20 - 25, 2011
2 | Establishment and Deployment | "The Nation", Daily | IGP FHQ Tenders | Bidding | 2011-09-22 | Sem-Luk Ventures Ltd | 15/11/2011 | 15/11/2011 | 4 Weeks | 10687500 | 91937840 |  | 31/12/2011 | 90%
| of Police Management Information | Trust & Federal Tender | Board
| Technology System in Police | Journal dated June
| Formations, Commands & Training Institutions | 20 - 25, 2011
3 | Establishment and Deployment | "The Nation", Daily | IGP FHQ Tenders | Bidding | 2011-09-22 | Hamilton & Sons | 15/11/2011 | 15/11/2011 | 4 Weeks | 3000000 | 91937840 |  | 31/12/2011 | 90%
| of Police Management Information | Trust & Federal Tender | Board
| Technology System in Police | Journal dated June
| Formations, Commands & Training Institutions | 20 - 25, 2011
4 | Establishment and Deployment | "The Nation", Daily | IGP FHQ Tenders | Bidding | 2011-09-22 | Rosy-Jey Ventures | 15/11/2011 | 15/11/2011 | 4 Weeks | 1000000 | 91937840 |  | 31/12/2011 | 90%
| of Police Management Information | Trust & Federal Tender | Board |  |  | Ent. Ltd
| Technology System in Police | Journal dated June
| Formations, Commands & Training Institutions | 20 - 25, 2011
5 | Establishment and Deployment | "The Nation", Daily | IGP FHQ Tenders | Bidding | 2011-09-22 | Dad-Pride Inter. Ltd | 15/11/2011 | 15/11/2011 | 4 Weeks | 4236750 | 91937840 |  | 31/12/2011 | 90%
| of Police Management Information | Trust & Federal Tender | Board
| Technology System in Police | Journal dated June
| Formations, Commands & Training Institutions | 20 - 25, 2011
6 | Establishment and Deployment | "The Nation", Daily | IGP FHQ Tenders | Bidding | 2011-09-22 | Blazing Stars Ltd | 15/11/2011 | 15/11/2011 | 4 Weeks | 4998000 | 91937840 |  | 31/12/2011 | 90%
| of Police Management Information | Trust & Federal Tender | Board
| Technology System in Police | Journal dated June
| Formations, Commands & Training Institutions | 20 - 25, 2011
7 | Establishment and Deployment | "The Nation", Daily | IGP FHQ Tenders | Bidding | 2011-09-22 | Modamak Ltd | 15/11/2011 | 15/11/2011 | 4 Weeks | 1307250 | 91937840 |  | 31/12/2011 | 90%
| of Police Management Information | Trust & Federal Tender | Board
| Technology System in Police | Journal dated June
| Formations, Commands & Training Institutions | 20 - 25, 2011
8 | Establishment and Deployment | "The Nation", Daily | IGP FHQ Tenders | Bidding | 2011-09-22 | Kemat Investment Ltd | 15/11/2011 | 15/11/2011 | 4 Weeks | 7008750 | 91937840 |  | 31/12/2011 | 90%
| of Police Management Information | Trust & Federal Tender | Board
| Technology System in Police | Journal dated June
| Formations, Commands & Training Institutions | 20 - 25, 2011
9 | Establishment and Deployment | "The Nation", Daily | IGP FHQ Tenders | Bidding | 2011-09-22 | Bodmak Ltd | 15/11/2011 | 15/11/2011 | 4 Weeks | 6804000 | 91937840 |  | 31/12/2011 | 90%
| of Police Management Information | Trust & Federal Tender | Board
| Technology System in Police | Journal dated June
| Formations, Commands & Training Institutions | 20 - 25, 2011
10 | Establishment and Deployment | "The Nation", Daily | IGP FHQ Tenders | Bidding | 2011-09-22 | Magat Nig. Ltd | 15/11/2011 | 15/11/2011 | 4 Weeks | 4173750 | 91937840 |  | 31/12/2011 | 90%
| of Police Management Information | Trust & Federal Tender | Board
| Technology System in Police | Journal dated June
| Formations, Commands & Training Institutions | 20 - 25, 2011
11 | Establishment and Deployment | "The Nation", Daily | IGP FHQ Tenders | Bidding | 2011-09-22 | Ansari Nig Ltd | 15/11/2011 | 15/11/2011 | 4 Weeks | 7108500 | 91937840 |  | 31/12/2011 | 90%
| of Police Management Information | Trust & Federal Tender | Board
| Technology System in Police | Journal dated June
| Formations, Commands & Training Institutions | 20 - 25, 2011
12 | Establishment and Deployment | "The Nation", Daily | IGP FHQ Tenders | Bidding | 2011-09-22 | Stac Nig Ltd | 15/11/2011 | 15/11/2011 | 4 Weeks | 1499994 | 91937840 |  | 31/12/2011 | 90%
| of Police Management Information | Trust & Federal Tender | Board
| Technology System in Police | Journal dated June
| Formations, Commands & Training Institutions | 20 - 25, 2011
13 | Establishment and Deployment | "The Nation", Daily | IGP FHQ Tenders | Bidding | 2011-09-22 | Wood-Etai | 15/11/2011 | 15/11/2011 | 4 Weeks | 997491 | 91937840 |  | 31/12/2011 | 90%
| of Police Management Information | Trust & Federal Tender | Board
| Technology System in Police | Journal dated June
| Formations, Commands & Training Institutions | 20 - 25, 2011
14 | Establishment and Deployment | "The Nation", Daily | IGP FHQ Tenders | Bidding | 2011-09-22 | Oakfield Ltd | 15/11/2011 | 15/11/2011 | 4 Weeks | 9429000 | 91937840 |  | 31/12/2011 | 90%
| of Police Management Information | Trust & Federal Tender | Board
| Technology System in Police | Journal dated June
| Formations, Commands & Training Institutions | 20 - 25, 2011
1 | PROPAGATION AND PROCUREMENT OF EQUIPMENT FOR POLICE SERVICE DELIVERY INITIATIVES IN FORMATIONS AND COMMANDS(SERVICOM) | FHQ ABUJA/15 POLICE COMMAND HQTRS | SERVICOM THE PRESIDENCY UMULAW NIGERIA LIMITED | AGMT: NO: SERV /002/ 2011. AGMT:NO:SERV/OO1/2011 | 2011-01-01 | 31/03/2012 | 42032152 | 42032152 | NIL | 33398532 | NIL
1 | PURCHASE OF CAMCOPTER (SCHIEBEL BRAND) | (Daily Trust) 20/06/11 | FHQ | Restricted | 27/10/11 | Newell Perspective Limited | 30/11/2011 | 02/12/2011 | 01/01/2011 - 31/12/2011 | 48550000 | 700000000 | Nill | 28/12/2011 | 100% | Payment yet to be effected
Purchase of FLIR MkII for 5N-PAW
2 | Purchase of Nightsun with 40m Candlelight Capacity for 5N-PAW | (Daily Trust) 20/06/11 | " | Restricted | 27/10/11 | Beta Transformator Co. Nig. Ltd | " | 02/12/2011 | 01/01/2011 - 31/12/2011 | 33300000 |  | Nill | 28/12/2011 | 100% | Payment yet to be effected
3 | Purchase of SLASS and Surveillance Accessories for Installation on 5N-PAW | (Daily Trust) 20/06/11 | " | Restricted | 27/10/11 | Nelrigral Enterprises Ltd | " | 02/12/2011 | 01/01/2011 - 31/12/2012 | 46650000 |  | Nill | 28/12/2011 | 100% | Payment yet to be effected
4 | Installation of Night Vision and Surveillance Equipment on Helicopter Bell 427 with Registration 5N-PAW | (Daily Trust) 20/06/11 | " | Restricted | 27/10/11 | Eglobegree Int'l Nig. Ltd | " | 02/12/2011 | 01/01/2011 - 31/12/2012 | 41850000 |  | Nill | 29/12/2011 | 100% | Payment yet to be effected
5 | Purchase of Forward Looking Infrared Camera for 5N-POL | (Daily Trust) 20/06/11 | " | Restricted | 27/10/11 | P. S. I. International Co. Ltd | " | 02/12/2011 | 01/01/2011 - 31/12/2012 | 49330000 |  | Nill | 28/12/2011 | 100% | Payment yet to be effected
6 | Purchase of Spectrolab SX-16 Nightsun for 5N-POL | (Daily Trust) 20/06/11 | " | Restricted | 27/10/11 | Simidia S & I Int'l Company Ltd | " | 01/12/2011 | 01/01/2011 - 31/12/2012 | 34198000 |  | Nill | 29/12/2011 | 100% | Payment yet to be effected
7 | Purchase of Avoinics Mission and Surveillance Equipment with Accessories for Installation on 5N-POL | (Daily Trust) 20/06/11 | " | Restricted | 27/10/11 | Beta Transformator Co. Nig. Ltd | " | 02/12/2011 | 01/01/2011 - 31/12/2012 | 47185000 |  | Nill | 28/12/2011 | 100% | Payment yet to be effected
8 | Installation of Surveillance and Upgrade of Avionics and Communication of Equipment for 5N-POL | (Daily Trust) 20/06/11 | " | Restricted | 27/10/11 | Unibright Engineering Ltd | " | 02/12/2011 | 01/01/2011 - 31/12/2012 | 43520000 |  | Nill | 28/12/2011 | 100% | Payment yet to be effected
9 | Purchase and Installation of Rappelling Kit for Bell 427 5N-SGE | (Daily Trust) 20/06/11 | " | Restricted | 27/10/11 | Eglobegree Int'l Nig. Ltd | " | 02/12/2011 | 01/01/2011 - 31/12/2012 | 48850000 |  | Nill | 29/12/2011 | 100% | Payment yet to be effected
10 | Purchase and Installation of Rappelling Kit for 5N-FHQ | (Daily Trust) 20/06/11 | " | Restricted | 27/10/11 | Newell Perspective Limited | " | 02/12/2011 | 01/01/2011 - 31/12/2012 | 48320000 |  | Nill | 29/12/2011 | 100% | Payment yet to be effected
11 | Purchase of Ultra 8500 Forward Looking Intra Red Camera for 5N-LEH | (Daily Trust) 20/06/11 | " | Restricted | 27/10/11 | Simidia S & I Int'l Company Ltd | " | 01/12/2011 | 01/01/2011 - 31/12/2012 | 49590000 |  | Nill | 28/12/2011 | 100% | Payment yet to be effected
12 | Installation of SpectroLab SX-16 Nightsun and Accessories for 5N-LEH | (Daily Trust) 20/06/11 | " | Restricted | 27/10/11 | Unibright Engineering Ltd | " | 02/12/2011 | 01/01/2011 - 31/12/2012 | 44300000 |  | Nill | 28/12/2011 | 100% | Payment yet to be effected
13 | Purchase of Honeywell MFRD and Installation on 5N-LEH Coupling Radar and GPS for Terrain Flying | (Daily Trust) 20/06/11 | " | Restricted | 27/10/11 | Eglobegree Int'l Nig. Ltd | " | 02/12/2011 | 01/01/2011 - 31/12/2012 | 36210000 |  | Nill | 28/12/2011 | 100% | Payment yet to be effected
14 | Purchase of Ultra 8500 FLIR for 5N-KSH | (Daily Trust) 20/06/11 | " | Restricted | 27/10/11 | P. S. I. International Co. Ltd | " | 02/12/2011 | 01/01/2011 - 31/12/2012 | 49380000 |  | Nill | 28/12/2011 | 100% | Payment yet to be effected
15 | Installation of SpectroLab SX-16 Nightsun and Accessories with 40m Candlelight for 5N-KSH | (Daily Trust) 20/06/11 | " | Restricted | 27/10/11 | Nelrigral Enterprises Ltd | " | 02/12/2011 | 01/01/2011 - 31/12/2012 | 44220000 |  | Nill | 29/12/2011 | 100% | Payment yet to be effected
16 | Purchase of Honeywell MFRD and Installation on 5N-KSH Coupling Radar and GPS for Terrain Flying | (Daily Trust) 20/06/11 | " | Restricted | 27/10/11 | Simidia S & I Int'l Company Ltd | " | 01/12/2011 | 01/01/2011 - 31/12/2012 | 34200000 |  | Nill | 29/12/2011 | 100% | Payment yet to be effected
|  |  | TOTAL | [7 empty] | 700000000
1 | PROCUREMENT OF SECURITY/CRIMINAL INTELLIGENCE EQUIPMENTS | For security reasons their war no advertisment T | IGP | SELECTIVE | selective tendering | Boardmark Limited, 6, Lekki Close,Garki-Abuja. | 2011-11-30 | January to December | January to December | 74863626 | ₦74,863,626 | payment process in progress | 2011-12-01 | 100%
DCS Security Systems Ltd Plot 61-A, Road 3, VGC Ajah-Lekki, Lagos-Nigeria
Setronics International Nig. Ltd, No. 44, Oyemekun Road Akure, Ondo State.
Assured Security Equipment & Service Ltd Suit D1 Kebbi House, 10 Kur Mohammed Way, Central Business District, Abuja.
1 | Neighbourhood Policing/ Partnerships |  | Nigeria Police Force Tenders Board | Fixed Budget Small Assingment Lump-Sum for Consultancy jobs | 2011-08-05 | Femmac Business Solutions Ltd | 2011-11-16 | 2011-11-16 | Jan to Dec, 2011 | 12000000 | 12000000 | NIL | 2011-12-31 | 100%
2 | Divisional Management Capacity building Batch 1 |  | Nigeria Police Force Tenders Board | Fixed Budget Small Assingment Lump-Sum for Consultancy jobs | 2011-08-05 | Project Support Services Consultants Ltd | 2011-11-16 | 2011-11-16 | Jan to Dec, 2011 | 10000000 | 10000000 | NIL | 2011-12-31 | 100%
3 | Divisional Management Capacity building Batch 2 |  | Nigeria Police Force Tenders Board | Fixed Budget Small Assingment Lump-Sum for Consultancy jobs | 2011-08-05 | Bright Projects Services Ltd | 2011-11-16 | 2011-11-16 | Jan to Dec, 2011 | 10000000 | 10000000 | NIL | 2011-12-31 | 100%
4 | Divisional Management Capacity building Batch 3 |  | Nigeria Police Force Tenders Board | Fixed Budget Small Assingment Lump-Sum for Consultancy jobs | 2011-08-05 | Bright Projects Services Ltd | 2011-11-16 | 2011-11-16 | Jan to Dec, 2011 | 10000000 | 10000000 | NIL | 2011-12-31 | 100%
5 | Problem Solving Tools/Manuals |  | Nigeria Police Force Tenders Board | Fixed Budget Small Assingment Lump-Sum for Consultancy jobs | 2011-08-05 | Glacier Nig Ltd | 2011-11-16 | 2011-11-16 | Jan to Dec, 2011 | 3091000 | 3091000 | NIL | 2011-12-31 | 100%
6 | Divisional Management Capacity Building Batch 4 |  | Nigeria Police Force Tenders Board | Fixed Budget Small Assingment Lump-Sum for Consultancy jobs | 2011-08-05 | Bright Projects Services Ltd | 2011-11-30 | 2011-11-30 | Jan to Dec, 2011 | 10000000 | 10000000 | NIL | 2011-12-31 | 100%
7 | Safer Schools Project |  | Nigeria Police Force Tenders Board | Fixed Budget Small Assingment Lump-Sum for Consultancy jobs | 2011-08-05 | Project Development Support Services Ltd | 2011-11-30 | 2011-11-30 | Jan to Dec, 2011 | 12000000 | 12000000 | NIL | 2011-12-31 | 100%
8 | Divisional Patrol Officers Course |  | Nigeria Police Force Tenders Board | Fixed Budget Small Assingment Lump-Sum for Consultancy jobs | 2011-08-05 | Hamilton and Sons Ltd | 2011-11-30 | 2011-11-30 | Jan to Dec, 2011 | 7000000 | 7000000 | NIL | 2011-12-31 | 100%
1 | Procurement of BMW Motorcycles configured to Police Specification including Rider's Kit. | 20/6/2011 | FHQ - TB. | Request for Quotation | N/A. | (1) Coscharis Motors Ltd (2) Mani & Brothers Ent. Nigeria Ltd./Tomson Automobile Works Ltd. | 2011 | JAN. 2011 | 12 Months | 61535632 | 61535632 | Nil | DEC. 2011 | 100%
2 | MPA/Proc/Cap/1787/Vol.1/27DD Ford Rangers | 20/6/2011 | MTB & FHQ. TB | Request for Quotation | N/A. | (1) Coscharis Motors Ltd (2) Ispat Steel Nig. Ltd. (3) Ozonic Global Concept Ltd. | 2010 | 2010 | 12 Months | 600000000 | 600000000 | Nil | DEC. 2011 | 100%
3 | Purchase of Patrol Vehicles (Pick-ups, Patrol Jeeps, Patrol Cars, Canine Patrol Vans) with installed Communication Equipment. | 20/6/2011 | FHQ - TB. | Request for Quotation | N/A. | (1) Bestford Motors Ltd. (2) Parco Ent. (Nig.) Ltd. (3) Raswas Nigeria Ltd. (4) Toraq Nigeria Ent. Ltd (5) Marcon Tech. Co. Ltd. | 2011 | JAN. 2011 | 12 Months | 168520765 | 168520765 | Nil | DEC. 2011 | 100%
4 | Purchase of Scene of Crime Vehicle (4x4 V8 5.4 Litres engine) | 20/6/2011 | MTB. | Direct Procurement | N/A. | (1) Hamdala Int. Serv.Ltd (2) O.A.U. Universal Concept Limited. (3) V & V Nigeria Limited | 2011 | JAN. 2011 | 12 Months | 73227403 | 73227403 | Nil | DEC. 2011 | 100%
5 | Procurement of Armoured Personnel Carriers (APCs) | 20/6/2011 | MTB. | Direct Procurement | N/A. | Sanusi Ahmed Motors International Limited. | 2011 | JAN. 2011 | 12 Months | 21605664 | 21605664 | Nil | DEC. 2011 | 100%
6 | Police Armored Typhoon on ford F-150/350 Pick-up Chassis. | 20/6/2011 | MTB. | Direct Procurement | N/A. | (1) Toffy Ventures Ltd. (2) Ogama Limited (3) Blazing Stars Ltd (4) Bodmak Agencies (5) Oakfield Limited (6) Kemat Limited (7) Recitals Limited (8) Modmak Limited (9) Dads-Pride Int. Ltd. (10) Unifit Nigeria Ltd. (11) Bodmak Limited (12)Sensors & Safety Ltd (13) Magat Nigeria Ltd. | 2011 | JAN. 2011 | 12 Months | 1739306915 | 1739306915 | Nil | DEC. 2011 | 0% | Expected Delivery period is 2nd Week of March, 2012
7 | Procurement of Armoured Patrol Vans (APVs). | 20/6/2011 | FHQ - TB. | Emergency Procurement | N/A. | Megapoint Automobiles Ltd. | 2011 | JAN. 2011 | 12 Months | 192866321 | 192866321 | Nil | DEC. 2011 | 100%
8 | Purchase of Operational Vehicles (Specialized) - Lorries, Unimog Trucks, Mobile Workshop Vehicles, H/Duty Recovery Vehicles, Comms. Maintenance Vehicles, Ambulances, Veterinary Ambulatory Van. | 20/6/2011 |  | Request for Quotation | N/A. | (1) Sem-Luk Ventures Ltd (2) Danfach Link Invest. Ltd. | 2011 | JAN. 2011 | 12 Months | 47413031 | 47413031 | Nil | DEC. 2011 | 100%
13754393699.85
PROCURING ENTITY (MDA): NPF
MINISTRY : POLICE AFFAIRS
FINANCIAL YEAR : 2011
DEPARTMENT EOD
| BASIC DATA |  |  |  |  | CONTACT AWARD | [5 empty] | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | ADVERTISE-MENT DATE & MEDIA | APPROVAL THRESHOLD | PROCURE-MENT METHOD | BID OPENING DATE | CONTRACTOR | DATE OF CONTRACT AWARD | DATE OF CONTRACT COMMENCE-MENT | CONTRACT PERIOD |  | BUDGETARY PROVISION (N) | AMOUNT PAID AS AT DEC 2011 | EXPECTED COMPLETION DATE | % OF COMPLE-TION AS AT DEC 2011 | REMARKS
16 | Purchase of EOD Equiupment | Nil | 11,756,492.00 | Contract | 21/09/2011 | Stiches Prints Nig. Ltd. | 2011 | Jan 2011 | 30 days | 7128192 | 11,756,492.00 | Nil | Dec 2011 | Nil | Money not yet release
| Purchase of Eod Demolition Stores |  |  |  |  | Ashland Security Ltd |  |  |  | 4628300
PROCUREMENT RECORDS
| PROCURING ENTITY (MDS): | FORCE COMPUTER FHQ ABUJA
| MINISTRY | NPF
| FISCAL YEAR: | 2011
|  | BASIC DATA |  |  |  |  | CONTRACT AWARD | [5 empty] | CONTRACT IMPEMENTATION
S/NO | CONTRACT DESCRIPTION | ADVERTISMENT , | APPROVAL | PROCUREMENT | BID | CONTRACTOR | DATE OF CONTRACT | DATE OF CONTRACT | CONTRACT |  | BUDGETARY | AMOUNT PAID | EXPECTED | % OF | REMARK
|  | DATE & MEDIA | THRESHOLD | METHOD | OPENING |  | AWARD | COMMENCEMENT | PERIOD |  | PROVISION | AS AT | COMPLETION | COMPLETION
[5 empty] | DATE | [5 empty] | (N) |  | DATE | AS AT
1 | Establishment and Deployment | "The Nation", Daily | IGP FHQ Tenders | Bidding | 2011-09-22 | Komat Nigeria Ltd | 15/11/2011 | 15/11/2011 | 4 Weeks | 9993375 | 91937840 |  | 31/12/2011 | 90%
| of Police Management Information | Trust & Federal Tender | Board
| Technology System in Police | Journal dated June
| Formations, Commands & Training Institutions | 20 - 25, 2011
2 | Establishment and Deployment | "The Nation", Daily | IGP FHQ Tenders | Bidding | 2011-09-22 | Sem-Luk Ventures Ltd | 15/11/2011 | 15/11/2011 | 4 Weeks | 10687500 | 91937840 |  | 31/12/2011 | 90%
| of Police Management Information | Trust & Federal Tender | Board
| Technology System in Police | Journal dated June
| Formations, Commands & Training Institutions | 20 - 25, 2011
3 | Establishment and Deployment | "The Nation", Daily | IGP FHQ Tenders | Bidding | 2011-09-22 | Hamilton & Sons | 15/11/2011 | 15/11/2011 | 4 Weeks | 3000000 | 91937840 |  | 31/12/2011 | 90%
| of Police Management Information | Trust & Federal Tender | Board
| Technology System in Police | Journal dated June
| Formations, Commands & Training Institutions | 20 - 25, 2011
4 | Establishment and Deployment | "The Nation", Daily | IGP FHQ Tenders | Bidding | 2011-09-22 | Rosy-Jey Ventures | 15/11/2011 | 15/11/2011 | 4 Weeks | 1000000 | 91937840 |  | 31/12/2011 | 90%
| of Police Management Information | Trust & Federal Tender | Board |  |  | Ent. Ltd
| Technology System in Police | Journal dated June
| Formations, Commands & Training Institutions | 20 - 25, 2011
5 | Establishment and Deployment | "The Nation", Daily | IGP FHQ Tenders | Bidding | 2011-09-22 | Dad-Pride Inter. Ltd | 15/11/2011 | 15/11/2011 | 4 Weeks | 4236750 | 91937840 |  | 31/12/2011 | 90%
| of Police Management Information | Trust & Federal Tender | Board
| Technology System in Police | Journal dated June
| Formations, Commands & Training Institutions | 20 - 25, 2011
6 | Establishment and Deployment | "The Nation", Daily | IGP FHQ Tenders | Bidding | 2011-09-22 | Blazing Stars Ltd | 15/11/2011 | 15/11/2011 | 4 Weeks | 4998000 | 91937840 |  | 31/12/2011 | 90%
| of Police Management Information | Trust & Federal Tender | Board
| Technology System in Police | Journal dated June
| Formations, Commands & Training Institutions | 20 - 25, 2011
7 | Establishment and Deployment | "The Nation", Daily | IGP FHQ Tenders | Bidding | 2011-09-22 | Modamak Ltd | 15/11/2011 | 15/11/2011 | 4 Weeks | 1307250 | 91937840 |  | 31/12/2011 | 90%
| of Police Management Information | Trust & Federal Tender | Board
| Technology System in Police | Journal dated June
| Formations, Commands & Training Institutions | 20 - 25, 2011
8 | Establishment and Deployment | "The Nation", Daily | IGP FHQ Tenders | Bidding | 2011-09-22 | Kemat Investment Ltd | 15/11/2011 | 15/11/2011 | 4 Weeks | 7008750 | 91937840 |  | 31/12/2011 | 90%
| of Police Management Information | Trust & Federal Tender | Board
| Technology System in Police | Journal dated June
| Formations, Commands & Training Institutions | 20 - 25, 2011
9 | Establishment and Deployment | "The Nation", Daily | IGP FHQ Tenders | Bidding | 2011-09-22 | Bodmak Ltd | 15/11/2011 | 15/11/2011 | 4 Weeks | 6804000 | 91937840 |  | 31/12/2011 | 90%
| of Police Management Information | Trust & Federal Tender | Board
| Technology System in Police | Journal dated June
| Formations, Commands & Training Institutions | 20 - 25, 2011
10 | Establishment and Deployment | "The Nation", Daily | IGP FHQ Tenders | Bidding | 2011-09-22 | Magat Nig. Ltd | 15/11/2011 | 15/11/2011 | 4 Weeks | 4173750 | 91937840 |  | 31/12/2011 | 90%
| of Police Management Information | Trust & Federal Tender | Board
| Technology System in Police | Journal dated June
| Formations, Commands & Training Institutions | 20 - 25, 2011
11 | Establishment and Deployment | "The Nation", Daily | IGP FHQ Tenders | Bidding | 2011-09-22 | Ansari Nig Ltd | 15/11/2011 | 15/11/2011 | 4 Weeks | 7108500 | 91937840 |  | 31/12/2011 | 90%
| of Police Management Information | Trust & Federal Tender | Board
| Technology System in Police | Journal dated June
| Formations, Commands & Training Institutions | 20 - 25, 2011
12 | Establishment and Deployment | "The Nation", Daily | IGP FHQ Tenders | Bidding | 2011-09-22 | Stac Nig Ltd | 15/11/2011 | 15/11/2011 | 4 Weeks | 1499994 | 91937840 |  | 31/12/2011 | 90%
| of Police Management Information | Trust & Federal Tender | Board
| Technology System in Police | Journal dated June
| Formations, Commands & Training Institutions | 20 - 25, 2011
13 | Establishment and Deployment | "The Nation", Daily | IGP FHQ Tenders | Bidding | 2011-09-22 | Wood-Etai | 15/11/2011 | 15/11/2011 | 4 Weeks | 997491 | 91937840 |  | 31/12/2011 | 90%
| of Police Management Information | Trust & Federal Tender | Board
| Technology System in Police | Journal dated June
| Formations, Commands & Training Institutions | 20 - 25, 2011
14 | Establishment and Deployment | "The Nation", Daily | IGP FHQ Tenders | Bidding | 2011-09-22 | Oakfield Ltd | 15/11/2011 | 15/11/2011 | 4 Weeks | 9429000 | 91937840 |  | 31/12/2011 | 90%
| of Police Management Information | Trust & Federal Tender | Board
RE: PROCUREMENT RECORDS FOR 2011 FINANCE YEAR
VETERINARY SERVICES FHQ.ABUJA
NAME OF MINISTRY/AGENCY: |  | NIGERIA POLICE |  |  | POLICE FORMATIONS &COMMAND: |  |  |  | SECTOR: SECURITY
S/NO | Contract Description | Advantisement Date and Media | ApprovalThreshold | Procurement method | Bid Opening Date | Contractor | Date of Contract Award | Date of contract commenncement | contract period |  | Budgetary Provision | Amount Paid as at | Expected completion date | % completion as at | Remarks
1 | Establishment and Equipping of Veterinary Clinics in Six Locations (kaduna, Enugu, Jos, Sokoto, Ilorin and Port-Harcourt) | Daily Trust 20th June 2011 | IGP Threshold | open Method | 24th November 2011 | Toyin Investment Ltd, Tunsoye & Son, Eto Inter Bis, Mode Ventures, Nicotina Invest. Nig. Ltd and Cynthia Odiase Ent. | 16th November,2011 | 2011 project 1/1/2011 to 3 1/12/2011 | On-Going Project | 16744390 | 1198000 | payment documents forwarded through the Minister of police Affairs Capital Payments | 2013 | 100% completed | Inadeguate funfing
2 | Establishment /Development of Police Veterinary Dogs Breeding Centre FHQ Abuja | Daily Trust 20th June 2011 | IGP Threshold | open Method | 24th November 2011 | Toyin Investment Ltd, Tunsoye & Son, Eto Inter Bis, Mode Ventures, Nicotina Invest. Nig. Ltd and Cynthia Odiase Ent. | 16th November,2011 | 2011 project 1/1/2011 to 3 1/12/2011 | On-Going Project | 10802832 | 168000000 | payment documents forwarded through the Minister of police Affairs Capital Payments | 2013 | 100% completed | Inadeguate funfing
3 | Establishment /Development of Police Veterinary Diagnostic Laboratory /Radiology FHQ Abuja | Daily Trust 20th June 2011 | IGP Threshold | open Method | 24th November 2011 | Toyin Investment Ltd, Tunsoye & Son, Eto Inter Bis, Mode Ventures, Nicotina Invest. Nig. Ltd and Cynthia Odiase Ent. | 16th November,2011 | 2011 project 1/1/2011 to 3 1/12/2011 | On-Going Project | 15123965 | 165000000 | payment documents forwarded through the Minister of police Affairs Capital Payments | 2013 | 100% completed | Inadeguate funfing
AIG, STEPHEN D. HART DR.
ASSISTANT INSPECTOR GEN. OF POLICE
B' DEPT. (VETERINARY) FHQ ABJ
RE: PROCUREMENT RECORDS FOR 2011 FINANCE YEAR
MOUNTED TROOP SECTION FHQ.ABUJA
NAME OF MINISTRY/AGENCY: |  | NIGERIA POLICE |  |  | POLICE FORMATIONS &COMMAND: |  |  |  | SECTOR: SECURITY
S/NO | Contract Description | Advantisement Date and Media | ApprovalThreshold | Procurement method | Bid Opening Date | Contractor | Date of Contract Award | Date of contract commenncement | contract period |  | Budgetary Provision | Amount Paid as at | Expected completion date | % completion as at | Remarks
1 | Horses feeds and part payment of 2010 Capital Projects liability | Daily Trust 20th June 2011 | IGP Threshold | open Method | 24th November 2011 | 2011 contractor M/S Cynthia Odiase Ent. 2010 Liability contractors M/S Toyin Invest Ltd. 2.) Fullfilled Nig. Ltd. | 16th November,2011 | 2011 project 1/1/2011 to 3 1/12/2011 2010 liability project 1/1/2010 to 31/12/2010 | On-Going Project | 26640324 | 26640324 | All payments are in progress through the Minister of police Affairs Capital Payments | 2011 project 3 1/12/2011 2010 liability project 31/12/2010 | 100% completed | Inadequate funds Details: 0n 30th April, 2010 N100,000,000.00 was appropriated to Mounted Troop Section. Base on this amount, contract was awarded and executed. On 7/9/2010 amendment appropriation of N49,500,000.00 was released, now we are indebted to the tune of N50,500,000.00 balance refer to ON-GOING PROJECTS IN 2012.
SP . Victor Akaya
Force Equitation Officer
‘B’ Department (Mounted )
Force Headquarters - Abuja.
PROCUREMENT ENTRY (MDA): |  | NIGERIA POLICE FORCE (ATS)
MINISTRY: |  | POLICE AFFAIRS.
FINANCIAL YEAR: |  | 2011
| BASIC DATA |  |  |  |  | CONTRACT AWARD | [5 empty] | CONTRACT IMPLEMENTATION
S/NO | CONTRACT DISCREPTION | ADVERTISEMENT DATE AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | CONTRACTOR | DATE OF CONTRACT AWARD | DATE OF CONTRACT COMMENCEMENT | CONTRACT PERIOD |  | BUDGETARY PROVISION (N) | AMOUNT PAID AS AT | EXPECTED COMPLETION DATE | % OF COMPLETION AS AT | REMARKS
1 | Equiping the Anti-Terrorism Squad |  | IGP/FHQ | SELECTIVE TENDERING | 17/10/2011 | messrs Magat Nig. Ltd. | 16/11/2011 | 17/11/2011 | 8 weeks | 2,249,998,00 | 73842759 | NIL | DEC. 2011 | 100% | Payment not effected yet.
2 | do |  | do | do | do | Messrs Fodacis Technical c. Ltd. | do | do | do | 16957025 | do | do | do | do | do
3 | do |  | do | do | do | do | do | do | do | 29792475 | do | do | do | do | do
4 | do |  | do | do | do | messrs Magat Nig. Ltd. | do | do | do | 3809520 | do | do | do | do | do
5 | do |  | do | do | do | messrs Magat Nig. Ltd. | do | do | do | 3069990 | do | do | do | do | do
6 | do |  | do | do | do | messrs matem ventures Ltd | do | do | do | 799,963,00 | do | do | do | do | do
7 | do |  | do | do | do | messrs Magat Nig. Ltd. | do | do | do | 3499650 | do | do | do | do | do
8 | do |  | do | do | do | do | do | do | do | 4099725 | do | do | do | do | do
9 | do |  | do | do | do | do | do | do | do | 3599820 | do | do | do | do | do
10 | do |  | do | do | do | do | do | do | do | 3227795 | do | do | do | do | do
PROCURING ENTITY (MDA):
MINISTRY:
FINANCIAL YEAR:
| BASIC DATA |  |  |  |  | CONTRACT AWARD | [5 empty] | CONTRACT IMPLEMENTATION
S/NO. | CONTRACT DESCRIPTION | ADVERTISEMENT DATE AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE |  | DATE OF CONTRACT AWARD | DATE OF CONTRACT COMMENCMNT | CONTRACT PERIOD |  | BUDGETARY PROVISION (₦) | AMOUNT PAID AS AT ₦ | EXPECTED COMPLETN DATE | % OF COMPLETN DATE | REMARKS
1 | Yanmar Marine Engine Sterndrive (STP -300MX) |  | FHQ | Selective | 2011-11-14 | Messrs Toyin Investment Nig. Ltd | 16 November, 2011 | 16 November, 2011 | 2011 | 41010000 | 63928438 | Nil | March, 2012 | 100% | Payment processing in progress at MPA
2 | Man - diesel Marine Engine Sterndrive (STP -400H) |  | FHQ | Selective |  | Messrs Sem – Luk Ventures Ltd., |  |  |  | 22915800
3 | Purchase of various Horse Power Yamaha Outboard Engines |  | FHQ | Selective | 1 December, 2011 | M/s Trackstel Nig. Ltd. | 15 December, 2011 | 15 December, 2011 | 2011 | 40640000 | 177285319 | Nil | March, 2012 | 100% | Payment documentation in progress
4 |  |  | FHQ | Selective |  | M/s Silver Team Ltd. |  |  |  | 48255000
5 |  |  | FHQ | Selective |  | M/s Cox Projects Ltd. |  |  |  | 47747000
6 |  |  | FHQ | Selective |  | M/s Chobs Nig. Ltd. |  |  |  | 40640000
| BASIC DATA |  |  |  |  | CONTRACT AWARD | [5 empty] | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | ADVERTISEMENT DATE AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | CONTRACTOR | DATE OF CONTRACT AWARD | DATE OF CONTRACT COMMENCEMENT | CONTRACT PERIOD |  | BUDGETARY PROVISION (N) | AMOUNT PAID AS AT | EXPECTED COMPLETION DATE | % OF COMPLETION AS AT | REMARKS
1 | INSTALLATION OF Digital security surveillance system. | Under the Ministry of Police Affairs procurement process is ongoing | Ministerial Threshold | Procurement process is on going | Procurement process is on going | Procurement process is on going | Procurement process is on going | Procurement process is on going | Jan to Dec, 2011 | 245794500 | 146835867 | Procurement process is on going | Procurement process is on going | Procurement process is on going
2 | Procurement of 28 Nos Digital UHF Motorola Base Radio Transceiver (3401) | 27th June, 2011- 10th July,2011 Federal Tenders Journal | Force Headqurters Threshold | Open biding | 2nd Nov, 2011 | Messrs Isiuwa General Ventures | 16th Nov, 2011 | 17th Nov, 2011 | Jan to Dec, 2011 | 8775900 | 69532623 | Payment still in process | March, 2012 | 98
3 | Procurement of 100 Nos 30 AMP Battery Chargers | 27th June, 2011- 10th July,2011 Federal Tenders Journal | Force Headqurters Threshold | Open biding | 2nd Nov, 2011 | Messrs Fast Track Engineering Ltd | 16th Nov, 2011 | 17th Nov, 2011 | Jan to Dec, 2011 | 5250000 | 69532623 | Payment still in process | March, 2012 | 98
4 | Procurement of 70 Nos Charge Controllers | 27th June, 2011- 10th July,2011 Federal Tenders Journal | Force Headqurters Threshold | Open biding | 2nd Nov, 2011 | Mesrs Vodaro Nigeria Ltd | 16th Nov, 2011 | 17th Nov, 2011 | Jan to Dec, 2011 | 2058000 | 63532623 | Payment still in process | March, 2012 | 98
5 | Procurement of 350 Nos of ICOM spare chargers | 27th June, 2011- 10th July,2011 Federal Tenders Journal | Force Headqurters Threshold | Open biding | 2nd Nov, 2011 | Messrs Benaebi Ventures Ltd | 16th Nov, 2011 | 17th Nov, 2011 | Jan to Dec, 2011 | 3999995 | 63532623 | Payment still in process | March, 2012 | 98
6 | Supply of 15 Nos AATRA Digital Telephone | 27th June, 2011- 10th July,2011 Federal Tenders Journal | Force Headqurters Threshold | Open biding | 2nd Nov, 2011 | Messrs Kankesifa Nigeria Ltd | 16th Nov, 2011 | 17th Nov, 2011 | Jan to Dec, 2011 | 1890000 | 63532623 | Payment still in process | March, 2012 | 98
7 | Supply of 40 Nos 200 Amp/Hr Deep Cycle Batteries | 27th June, 2011- 10th July,2011 Federal Tenders Journal | Force Headqurters Threshold | Open biding | 2nd Nov, 2011 | Messrs Jesse Jordan Investment Company Ltd | 16th Nov, 2011 | 17th Nov, 2011 | Jan to Dec, 2011 | 4011000 | 65532623 | Payment still in process | March, 2012 | 98
8 | Procurement of 50 Nos Battery Tester | 27th June, 2011- 10th July,2011 Federal Tenders Journal | Force Headqurters Threshold | Open biding | 2nd Nov, 2011 | Messrs Toyin Investment Ltd | 16th Nov, 2011 | 17th Nov, 2011 | Jan to Dec, 2011 | 5145000 | 63532623 | Payment still in process | March, 2012 | 98
9 | Procurement of 35 Nos Digital Motorola UHF Base Radios (3601) with all its accessories and the procurement of 10 Nos of CODAN HF Base Voice only with its accessories | 27th June, 2011- 10th July,2011 Federal Tenders Journal | Force Headqurters Threshold | Open biding | 2nd Nov, 2011 | Messrs Ringim Gadanci Nigeria Ltd | 16th Nov, 2011 | 17th Nov, 2011 | Jan to Dec, 2011 | 29742000 | 50869456 | Payment still in process | March, 2012 | 98
10 | Supply of 15 Nos ICOM HF Transceiver with its accessories | 27th June, 2011- 10th July,2011 Federal Tenders Journal | Force Headqurters Threshold | Open biding | 2nd Nov, 2011 | Messrs Grammercathy Ent. Ltd | 16th Nov, 2011 | 17th Nov, 2011 | Jan to Dec, 2011 | 9922500 | 50869456 | Payment still in process | March, 2012 | 98
11 | Procurment of 55 Nos Digital Power Supply Unit with Accessories procurement of 500 Nos Kenwood spare Chargers | 27th June, 2011- 10th July,2011 Federal Tenders Journal | Force Headqurters Threshold | Open biding | 2nd Nov, 2011 | Messrs Asmoy Resources Ltd | 16th Nov, 2011 | 17th Nov, 2011 | Jan to Dec, 2011 | 10106250 | 50869456 | Payment still in process | March, 2012 | 100
'D' DEPARTMENT (FORENSIC)
PROCUREMENT RECORDS
PROCURING ENTITY (MDA); |  |  | NIGERIA POLICE FORCE
MINISTRY: |  |  | MINISTRY OF POLICE AFFAIRS
FINANCIAL YEAR: |  | JANUARY TO DECEMBER 2011
S/N | CONTRACT DESCRIPTION | ADVERTISEMENT DATE AND MIDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | CONTRACTOR | DATE OF CONTRACT AWARD | DATE OF CONTRACT COMMENCEMENT | CONTRACT PERIOD |  | BUDGETARY PROVISION (N) | AMOUNT PAID AS AT OCT. 2011 | EXPECTED COMPLETION DATE | % OF COMPLETION REMARKS | REMARKS
1 | AUTOMATED FINGERPRINT IDENTIFICATION SYSYTEM TRACKER | 16TH MARCH, 2010 IN FEDERAL JORNAL | IG THRESHOLD | SELECTIVE TENDER | 2011-11-30 | TELEMOBILE NIG. LTD. | 2011-12-20 | 2011-12-20 | 2011 | 25,294,077,25 | 25,294,077,25 | 19153941 | WITHIN 2WEEKS (JAN) 2012 | - | INADEAQUATE FUNDING
2A | PROVISION OF DNA TEST LABORATORY | FEDERAL JOURNAL MARCH 2010 | IG THRESHOLD | SELECTIVE TENDERING | 2011-11-29 | TOYIN INVESTMENT LTD | 30/11/2011 | 2011-11-30 | 2011 | 49880054 | 67517701 | 49,88,054 | WITHIN 2WEEKS (DEC) 2011 | -
2B | PROVISION OF DNA TEST LABORATORY PEAGENTS AND KITS | FEDERAL JOURNAL MARCH 2010 | IG THRESHOLD | SELECTIVE TENDERING | 2011-11-30 | SKYVIEW INTEGRATE MULTI CONCEPT LTD | 30/11/2011 | 2011-11-30 | 2011 | 17637647 |  | 17637647 | DEC. 2011
3A | SUPPLY OF FORENSIC EQUIPMENT | FEDERAL JOURNAL MARCH 2010 | IG THRESHOLD | SELECTIVE TENDERING | 2011-12-01 | GRACE LAND GLOBAL LTD | 30/11/2011 | 2011-11-30 | 2011 | 14223003 | 54446274 | - | 2011-11-30
3B | SUPPLY OF FORENSIC EQUIPMENT CRIME SCENE SUITES etc. | FEDERAL JOURNAL MARCH 2010 | IG THRESHOLD | SELECTIVE TENDERING | 2011-11-30 | SEM LUX LTD | 30/11/2011 | 2011-11-30 | 2011 | 40223273 | - | 40223273
DCP. OVIE OYKOMINO
DEPUTY COMMISSIONER OF POLICE (FORENSIC)
FOR: COMMISSIONER OF POLICE
D' DEPT. FHQ ABUJA
SECTION:………'B' Dept. Transport……………………….
PROCUREMENT RECORDS FOR 2011 FINANCIAL YEAR
|  | NAME OF MINISTRY/AGENCY: POLICE FORMATION & COMMAND | [5 empty] | SECTOR:____SECURITY______
S/N | PROJECT TITLE | PROJECT LOCATION | CONTRACTOR | CONTRACT NO. | DATE PROJECT COMMENCED | PLANNED COMPLETION DATE | TOTAL PROJECT EST. COST | APPROPRIATION IN 2011 BUDGET | COST VARIATION (IF ANY) | TOTAL AMOUNT RELEASE IN 2011 | TOTAL AMOUNT COMMITTED TO DATE
1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 8 | 9 | 10 | 11
1 | Procurement of BMW Motorcycles configured to Police Specification including Rider's Kit. | FHQ. Abuja | (1) Coscharis Motors Ltd (2) Mani & Brothers Ent. Nigeria Ltd./Tomson Automobile Works Ltd. | TPT/116/2011, TPT/96/2011 | JAN. 2011 | DEC. 2011 | 61535632 | 61535632 | NIL. | 45460681 | 61535632
2 | MPA/Proc/Cap/1787/Vol.1/27DD Ford Rangers | FHQ. Abuja | (1) Coscharis Motors Ltd (2) Ispat Steel Nig. Ltd. (3) Ozonic Global Concept Ltd. | TPT/118/2011, TPT/138/2011 | 2010 | DEC. 2011 | 600000000 | 600000000 | NIL. | 443262017 | 600000000
3 | Purchase of Patrol Vehicles (Pick-ups, Patrol Jeeps, Patrol Cars, Canine Patrol Vans) with installed Communication Equipment. | FHQ. Abuja | (1) Bestford Motors Ltd. (2) Parco Ent. (Nig.) Ltd. (3) Raswas Nigeria Ltd. (4) Toraq Nigeria Ent. Ltd (5) Marcon Tech. Co. Ltd. | TPT/94/2011, TPT/109/2011, TPT/112/2011, TPT/93/2011, TPT/110/2011 | JAN. 2011 | DEC. 2011 | 168520765 | 168520765 | NIL. | 124498090 | 168520765
4 | Purchase of Scene of Crime Vehicle (4x4 V8 5.4 Litres engine) | FHQ. Abuja | (1) Hamdala Int. Serv.Ltd (2) O.A.U. Universal Concept Limited. (3) V & V Nigeria Limited | TPT/99/2011, TPT/122/2011, TPT/121/2011. | JAN. 2011 | DEC. 2011 | 73227403 | 73227403 | NIL. | 54098211 | 73227403
5 | Procurement of Armoured Personnel Carriers (APCs) | FHQ. Abuja | Sanusi Ahmed Motors International Limited. | TPT/100/2011 | JAN. 2011 | DEC. 2011 | 21605664 | 21605664 | NIL. | 15961617 | 21605664
6 | Police Armored Typhoon on ford F-150/350 Pick-up Chassis. | FHQ. Abuja | (1) Toffy Ventures Ltd. (2) Ogama Limited (3) Blazing Stars Limited (4) Bodmak Agencies (5) Oakfield Limited (6) Kemat Limited (7) Recitals Limited (8) Modmak Limited (9) Dads-Pride Int. Ltd. (10) Unifit Nigeria Ltd. (11) Bodmak Limited (12) Sensors & Safety Ltd (13) Magat Nigeria Ltd. | TPT/135/2011, TPT/86/2011, TPT/137/2011, TPT/124/2011, TPT/130/2011, TPT/128/2011, TPT/91/2011, TPT/87/2011, TPT/90/2011, TPT/134/2011, TPT/131/2011, TPT/126/2011, TPT/136/2011 | JAN. 2011 | DEC. 2011 | 1739306915 | 1739306915 | NIL. | 1284947819 | 1739306915
7 | Procurement of Armoured Patrol Vans (APVs). | FHQ. Abuja | Greenpractika Nig. Ltd. |  | JAN. 2011 | DEC. 2011 | 192866321 | 192866321 | NIL. | 142483857 | 192866321
8 | Purchase of Operational Vehicles (Specialized) - Lorries, Unimog Trucks, Mobile Workshop Vehicles, H/Duty Recovery Vehicles, Comms. Maintenance Vehicles, Ambulances, Veterinary Ambulatory Van. | FHQ. Abuja | (1) Sem-Luk Ventures Ltd (2) Danfach Link Invest. Ltd. | TPT/132/2011, TPT/96/2011. | JAN. 2011 | DEC. 2011 | 47413031 | 47413031 | NIL. | 35027327 | 35027327
Name & Signature of the Officer Authenticating Returns:… YUSUF C. USMAN………………………………………………..
Rank/Disgnation:…………CSP.……………………………………………..……….
Date:…………14/02/2012…………………………………………………………………
Note: Returns to be rendered in hard and soft copies using Microsoft Excel
MDAs that have Donor Related Project/Programmes should reflect such in a separate Template/Sheet
FINANCIAL YEAR: |  | 2011
| BASIC DATA |  |  |  |  | CONTRACT AWARD | [5 empty] | CONTRACT IMPLEMENTATION
S/N. | CONTRACT DESCRIPTION | ADVERTISEMENT DATE AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | CONTRACTOR | DATE OF CONTRACT AWARD | DATE OF CONTRACT COMMENCEMENT | CONTRACT PERIOD |  | BUDGETARY PROVISION (N) | AMOUNT PAID AS AT FEB 2012 | EXPECTED COMPLETION DATE | % OF COMPLETION AS AT FEB 2012 | REMARKS
1 | PROCUREMENT OF HOSPITAL EQUIPMENT (DIAGNOSTIC & THERAPEUTIC ITEMS) | 27 June 2011, Federal Tenders' Journal | 50000000 | Open Tender | 2011-08-11 | To be finalised | To be finalised | N/A | Jan 2011-Mar 2012 |  | 113594921 | Nil | 2012-03-01 | 0% | To be completed by March 2012
DR. DAX UZU (AIG)
ASSISTANT INSPECTOR-GENERAL OF POLICE
MEDICAL
PROCUREMENT RECORDS
PROCURING ENTITY (MDA):
MINISTRY:
FINANCIAL YEAR:
| BASIC DATA |  |  |  |  | CONTRACT AWARD | [5 empty] | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | ADVERTISEMENT DATE AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | CONTRACTOR | DATE OF CONTRACT AWARD | DATE OF CONTRACT COMMENCEMENT | CONTRACT PERIOD |  | BUDGETARY PROVISION (N) | AMOUNT PAID AS AT | EXPECTED COMPLETION DATE | % OF COMPLETION AS AT | REMARKS
1 | LAND SURVEY, COMPENSATION, VALUATION OF LANDED AND FIXED ASSESTS INCLUDING OUTSTANDING LIABILITIES | FEDERAL TENDERS JOURNAL of 27-June-2011 to 10-July-2011 THE PUNCH & DAILY TRUST - 20th June, 2011 | NPF | Due Process |  | M/s Simon Okeke & Associate |  |  |  | 74264304.5 | 45371895 | Nil | 2011-2013
2 | COMPLETION/CONSTRUCTION OF OFFICE COMPLEX FOR NIGERIA POLICE CENTER FOR POLICY, PLANNING AND RESEARCH (CPPR) OBIAKPU, EGBEMA, IMO STATE | FEDERAL TENDERS JOURNAL Vol. 6 No. 5 of Monday, March 8 – Sunday, March 21, 2010; and two National Dailies – Punch and Daily Trust of March 8, 2010 | NPF | Due Process | Tuesday 13th July, 2010 | M/s Dutse-Alah Constr. Company, M/s Kenfort Constr. Company Ltd., M/s Bodmak Agencies | 2010 | 2010 | On-going | 174697076.9 | 108028321 | Nil | 2010-2012
3 | CONSTRUCTION OF POLICE COLLEGE OF INFORMATION TECHNOLOGY ABEOKUTA (2ND PHASE) | FEDERAL TENDERS JOURNAL Vol. 6 No. 5 of Monday, March 8 – Sunday, March 21, 2010; and two National Dailies – Punch and Daily Trust of March 8, 2010 | NPF | Due Process | Tuesday 13th July, 2010 | Messrs Tunjums (Nig.) Ltd. | 2010 | 2010 | On-going | 50015694.23 | 34569063 | Nil | 2010-2012
4 | CONSTRUCTION OF WORKS TRAINNING SCHOOL, DEIDEI-ABUJA | FEDERAL TENDERS JOURNAL Vol. 6 No. 5 of Monday, March 8 – Sunday, March 21, 2010; and two National Dailies – Punch and Daily Trust of March 8, 2010 | NPF | Due Process | Tuesday 13th July, 2010 | M/s Kemat Nigeria Ltd. | 2010 | 2010 | On-going | 148434122.59 | 58065223 | Nil | 2010-2012
5 | COMPLETION OF POLICE QUARTERS AND POST AT OWELLI AWGU, ENUGU STATE POLICE COMMAND | FEDERAL TENDERS JOURNAL of 27-June-2011 to 10-July-2011 THE PUNCH & DAILY TRUST - 20th June, 2011 | NPF | Due Process | 10th November, 2011 | M/s Trusty Investment Nig. Ltd., M/s Tonfraco Nig. Enterprises | 2011 | 2011 | 2011-2013 | 54175255 | 130000000 | Nil | 2011-2013
6 | ESTABLISHMENT OF NIGERIA POLICE PEACEKEEPING TRAINING SCHOOL DEI-DEI ABUJA |  | NPF | Due Process | 2009 | M/s Abay Construction | 2009 | 2009 | On-going | 47404990.95 | 43211328 | Nil | 2009-2012 | 50%
7 | ESTABLISHMENT AND EQUIPING OF VETERINARY CLINICS IN SIX LOCATIONS (KADUNA, ENUGU, JOS, SOKOTO, ILORIN AND YOLA) | FEDERAL TENDERS JOURNAL of 27-June-2011 to 10-July-2011 THE PUNCH & DAILY TRUST - 20th June, 2011 | NPF | Due Process | 2011 | Messrs. Sokud Enterprises | 2011 | 2011 | 2011-2013 | 19986530.38 | 16744390 | Nil | 2008-2012
8 | COMPLETION OF POLICE HOSPITAL AT LIFE CAMP, ABUJA INCLUDING PAYMENT OF OUTSTANDING LIABILITY |  | NPF | Due Process | 2005 | M/s Basilica Ltd. | 2005 | 2005 | On-going | 172812410.84 | 43211328 | Nil | 2005-2012 | 50%
9 | CONSTRUCTION OF POLICE PRIMARY AND SECONDARY SCHOOLS | FEDERAL TENDERS JOURNAL Vol. 6 No. 5 of Monday, March 8 – Sunday, March 21, 2010; and two National Dailies – Punch and Daily Trust of March 8, 2010 | NPF | Due Process | Tuesday 13th July, 2010 | M/S Alliance Logistics Ltd., M/s Channel Engineering Co. Ltd., M/s First Construction Co. Ltd. | 2010 | 2010 | On-going | 430000000 | 114780091 | Nil | 2010-2012 | 60%
10 | POLICE COLLEGE WUDIL | FEDERAL TENDERS JOURNAL of 27-June-2011 to 10-July-2011 THE PUNCH & DAILY TRUST - 20th June, 2011 | NPF | Due Process | 10th November, 2011 | M/s Patok General Construction Ltd., M/s T. Tience Nig. Ent., M/s Hamdala Inter. Serv. Ltd., M/s Radio Sounders Nig. Ltd., M/s Okiky Invest. Ltd., M/s Yamsa Invest. & Property Ltd. | 2011 | 2011 | 2011-2013 | 224380000 | 300000000 | Nil | 2011-2013
11 | CONSTRUCTION/REHABILITATION OF STAFF QUARTERS & BARRACKS | FEDERAL TENDERS JOURNAL of 27-June-2011 to 10-July-2011 THE PUNCH & DAILY TRUST - 20th June, 2011 | NPF | Due Process | 10th November, 2011 | See Appendix 'A' | 2011 | 2011 | 2011-2013 | 3791601514.65 | 92637919 | Nil | 2011-2013
12 | PROVISION OF OBSERVATION POSTS ALONG MAJOR HIGHWAYS NATIONWIDE | FEDERAL TENDERS JOURNAL of 27-June-2011 to 10-July-2011 THE PUNCH & DAILY TRUST - 20th June, 2011 | NPF | Due Process | 10th November, 2011 | M/s Glory Engr. Resources Ltd., M/s Treasure Achievers Tech. Ltd. | 2011 | 2011 | 2011-2013 | 13019596.97 | 34569063 | Nil | 2011-2013
13 | CONSTRUCTION OF OFFICE ACCOMMODATION AND POLICE STATIONS NATIONWIDE | FEDERAL TENDERS JOURNAL of 27-June-2011 to 10-July-2011 THE PUNCH & DAILY TRUST - 20th June, 2011 | NPF | Due Process | 10th November, 2011 | See Appendix 'B' | 2011 | 2011 | 2011-2013 | 1430552693.92 | 100266496 | Nil | 2011-2013
14 | CONSTRUCTION OF MOBILE POLICE BARRACKS IN LAFIA, NASARAWA STATE | [9 empty] | 75619825 | Nil
15 | CONSTRUCTION OF 48 PMF BARRACKS AT OKWUZU EGBEMA, RIVERS STATE | FEDERAL TENDERS JOURNAL Vol. 6 No. 5 of Monday, March 8 – Sunday, March 21, 2010; and two National Dailies – Punch and Daily Trust of March 8, 2010 | NPF | Due Process | Tuesday 13th July, 2010 | M/s Tyse Ltd., M/s Chikorie Enterprises, M/s Matem Ventures Ltd., M/s Ponzeal Investment | 2010 | 2010 | On-going | 145712715.98 | 32408496 | Nil | 2010-2013 | 30%
16 | CONSTRUCTION OF MOUNTED TROOP PERSONNEL BARRACKS, OFFICES, STABLES, FURNISHING AND INFRASTRUCTURE - FHQ ABUJA | FEDERAL TENDERS JOURNAL Vol. 6 No. 5 of Monday, March 8 – Sunday, March 21, 2010; and two National Dailies – Punch and Daily Trust of March 8, 2010 | NPF | Due Process | Tuesday 13th July, 2010 | M/s Al-has Global Vent. Nig. Ltd., M/s Drairose Nig. Ltd. | 2010 | 2010 | On-going | 186508354.95 | 49693028 | Nil
17 | CONSTRUCTION OF FORCE HEADQUARTERS DOG SECTION BARRACKS, OFFICES, KENNELS, FURNISHING AND INFRASTRUCTURE (INCLUDING PERIMETER FENCING) ABUJA | FEDERAL TENDERS JOURNAL Vol. 6 No. 5 of Monday, March 8 – Sunday, March 21, 2010; and two National Dailies – Punch and Daily Trust of March 8, 2010 | NPF | Due Process | Tuesday 13th July, 2010 | M/s Al-has Global Vent. Nig. Ltd., M/s Remove Nig. Ltd. | 2010 | 2010 | On-going | 104824832.03 | 51853594 | Nil | 2010-2012
18 | UPGRADING OF POLICE BARRACKS AT DEI-DEI INCLUDING PROVISION OF INFRASTRUCTURAL FACILITIES, ROAD NETWORK, WATER, ELECTRICTY, ETC. | FEDERAL TENDERS JOURNAL Vol. 6 No. 5 of Monday, March 8 – Sunday, March 21, 2010; and two National Dailies – Punch and Daily Trust of March 8, 2010 | NPF | Due Process | Tuesday 13th July, 2010 | M/s Modmak Ltd, M/s Abay Construction | 2010 | 2010 | On-going |  | 111931777 | Nil | 2010-2012
19 | CONSTRUCTION OF HELIPAD IN 6 LOCATIONS: OTUKPO, FUGAR, YOLA, RINGIM,ABEOKUTA AND ELEWERAN OBALUFE WITH INFRASTUCTURES AND BRIDGES. | FEDERAL TENDERS JOURNAL Vol. 6 No. 5 of Monday, March 8 – Sunday, March 21, 2010; and two National Dailies – Punch and Daily Trust of March 8, 2010 | NPF | Due Process | Tuesday 13th July, 2010 | M/s J.B Maye Property Dev. Ltd., M/s Cordquote Engineering Ltd., M/s Sia Salon Nig. Ltd. | 2010 | 2010 | On-going | 540000000 | 400000000 | Nil | 2010-2012
20 | POLICE STATIONS AND BARRACK | [9 empty] | 177285319 | Nil
21 | NAFADA POLICE BARRACKS | FEDERAL TENDERS JOURNAL Vol. 6 No. 5 of Monday, March 8 – Sunday, March 21, 2010; and two National Dailies – Punch and Daily Trust of March 8, 2010 | NPF | Due Process | Tuesday 13th July, 2010 | M/S Adveron International, M/S Adebec Ventures | 2010 | 2010 | On-going | 82500000 | 98891967 | Nil | 2010-2012
22 | DUKKU POLICE STATION | FEDERAL TENDERS JOURNAL Vol. 6 No. 5 of Monday, March 8 – Sunday, March 21, 2010; and two National Dailies – Punch and Daily Trust of March 8, 2010 | NPF | Due Process | Tuesday 13th July, 2010 | M/S Rova Divine Resourcess Ltd, M/s Raov Ventures | 2010 | 2010 | On-going | 82500000 | 44321330 | Nil | 2010-2012
23 | CONSTRUCTION OF JETTIES AT MAKURDI IN BENUE, YAURI IN KEBBI, BAGA IN BORNO AND LOKOJA IN KOGI | FEDERAL TENDERS JOURNAL of 27-June-2011 to 10-July-2011 THE PUNCH & DAILY TRUST - 20th June, 2011 | NPF | Due Process | 10th November, 2011 | M/s Tee Pama Nig. Ltd., M/s Abog Engr. Ltd. | 2011 | 2011 | 2011-2013 | 189462275.5 | 89663506 | Nil | 2011-2013
24 | COMPLETION OF STATE HQ COMPLEX IN DAMATURU YOBE STATE, DUTSE JIGAWA STATE, JALINGO TARABA STATE, ZONE 4 HQ MAKURDI AND ZONE 9 HQ UMUAHIA | [9 empty] | 100639184 | Nil | 2011-2013
25 | REHABILITATION AND CONSTRUCTION OF INDOOR SHOOTING RANGES | FEDERAL TENDERS JOURNAL Vol. 6 No. 5 of Monday, March 8 – Sunday, March 21, 2010; and two National Dailies – Punch and Daily Trust of March 8, 2010 | NPF | Due Process | Tuesday 13th July, 2010 | M/S Olaniyi Popoola Nigeria Ltd., M/S Puristic Adherent Co. | 2010 | 2010 | On-going | 24850870.5 | 25926797 | Nil | 2010-2012
26 | ESTABLISHMENT OF NIGERIA POLICE VOCATIONAL AND RESETTLEMENT TRAINING CENTRE, AKPUGO, ENUGU STATE | - | - | - | - | - | - | - | - | - | 74374474 | Nil | 2010-2012
27 | REHABILITATION AND UPGRADE OF POLICE PRINTING PRESS IN LAGOS | FEDERAL TENDERS JOURNAL of 27-June-2011 to 10-July-2011 THE PUNCH & DAILY TRUST - 20th June, 2011 | NPF | Due Process | 10th November, 2011 | M/s Titan Integrated Services Ltd | 2011 | 2011 | 2011-2013 | 38865890.7 | 39676642 | Nil | 2011-2013
28 | REHABILITATION OF POLICE QUARTERS OWODE YEWA | FEDERAL TENDERS JOURNAL Vol. 6 No. 5 of Monday, March 8 – Sunday, March 21, 2010; and two National Dailies – Punch and Daily Trust of March 8, 2010 | NPF | Due Process | Tuesday 13th July, 2010 | Messrs. Bojavic Global Resources | 2010 | 2010 | On-going | 9573025 | 26592798 | Nil | 2010-2012
29 | REHABILITATION AND CONSTRUCTION OF POLICE COTTAGE HOSPITAL 20 BEDS (BUNGALOW TYPE) INCLUDING THE PROVISION OF MEDICAL EQUIPMENT AND FENCING OF EXISTING POLICE HOSPITALS | FEDERAL TENDERS JOURNAL Vol. 6 No. 5 of Monday, March 8 – Sunday, March 21, 2010; and two National Dailies – Punch and Daily Trust of March 8, 2010 | NPF | Due Process | Tuesday 13th July, 2010 | M/s. Kemat Investment Ltd, M/s Nne-Edak Tech. Co., M/s MJK & MJK Ltd., | 2010 | 2010 | On-going | 54541337.46 | 54850300 | Nil | 2010-2012
30 | REHABILITATION / REPAIRS - POLICE STATIONS / BARRACKS | - |  | - | - | - | - | - | - | - | 156991249 | Nil | 2011-2013
31 | UPGRADE AND REHABILITATION OF JETTIES AT ORON IN AKWA-IBOM, CALABAR IN CROSS-RIVER STATE, OKITIPUPA IN ONDO AND ONIKAN IN LAGOS STATE | - | - | - | - | - | - | - | - | - | 106991249 | Nil | 2011-2013
32 | UPGRADE OF OKUN OWA POLICE STATION OGUN EAST SENATORIAL DISTRICT, OGUN STATE | FEDERAL TENDERS JOURNAL of 27-June-2011 to 10-July-2011 THE PUNCH & DAILY TRUST - 20th June, 2011 | NPF | Due Process | 10th November, 2011 | M/s BOF Multidynamic Ltd. | 2011 | 2011 | 2011-2013 | 11650990.9 | 20000000 | Nil | 2011-2013
33 | UPGRADE OF IDOWU POLICE STATION OGUN EAST SENATORIAL DISTRICT, OGUN STATE | FEDERAL TENDERS JOURNAL of 27-June-2011 to 10-July-2011 THE PUNCH & DAILY TRUST - 20th June, 2011 | NPF | Due Process | 10th November, 2011 | M/s Anit Synergy Global Co. Ltd. | 2011 | 2011 | 2011-2013 | 11672110.3 | 30000000 | Nil | 2011-2013
34 | UPGRADE OF FACILITIES IN POLICE TRAINING INSTITUTIONS (POLICE COLLEGE IKEJA, KADUNA, MAIDUGURI, OJI-RIVER, POLICE TRAINING SCHOOLS IPERU, IBADAN, NONWA-TAI P/HARCOURT, OYIN-AKOKO, PMF TRAINING SCHOOLS GWOZA AND ILA-OROGUN | FEDERAL TENDERS JOURNAL of 27-June-2011 to 10-July-2011 THE PUNCH & DAILY TRUST - 20th June, 2011 | NPF | Due Process | 10th November, 2011 | M/s Crownage Multi Access Nigeria Ltd., M/s Rordav Concept, M/s Shehu Malamri Nig. Ltd., M/s Julyem Integraged Concept, M/s El-falaki Nig. Ltd, M/s KWAPACHI (NIG.) LTD., M/s Shehu Malamri Nig. Ltd., M/s Daranijo Integrated Services Ltd., M/s Omep Omai Investment Ltd., M/s Shehu Malamri Nig. Ltd., M/s Zain Zailane | 2011 | 2011 | 2011-2013 | 420043247.69 | 116778615 | Nil | 2011-2013
35 | REHABILITATION OF POLICE DETECTIVE COLLEGE, ENUGU | FEDERAL TENDERS JOURNAL Vol. 6 No. 5 of Monday, March 8 – Sunday, March 21, 2010; and two National Dailies – Punch and Daily Trust of March 8, 2010 | NPF | Due Process | Tuesday 13th July, 2010 | M/s Miracle Abund Enterprises, M/s Sensors & Safety Ltd, M/s Ogama Ltd, M/s MJK & MJK Ltd, M/s Toffy Ventures Ltd, M/s Kurtmet Integrated Services Ltd | 2010 | 2010 | On-going | 104336027.91 | 47640490 | Nil | 2010-2012
36 | REHABILITATION OF POLICE BAND BUILDINGS IN 10 LOCATIONS; KANO, KADUNA, SOKOTO, MAIDUGURI, YOLA, IBADAN, IKEJA, PORTHARCOURT, CALABAR, ENUGU, OWERRI AND MAKURDI | FEDERAL TENDERS JOURNAL Vol. 6 No. 5 of Monday, March 8 – Sunday, March 21, 2010; and two National Dailies – Punch and Daily Trust of March 8, 2010 | NPF | Due Process | Tuesday 13th July, 2010 | M/s Winnet Ltd, M/s Waco Impex Nig. Ltd., M/s Hans Investments Ltd., M/s Blazing Stars Ltd., M/s Matem Ventures Ltd | 2010 | 2010 | On-going | 99000000 | 21604664 | Nil | 2010-2012
PROCUREMENT RECORDS
PROCUREMENT ENTITY (MDA) |  |  |  | NIGERIA POLICE FORCE
MINISTRY: |  |  |  | MINISTRY OF POLICE AFFAIRS
FINANCIAL YEAR: |  |  |  | 2011
| BASIC DATA | [5 empty] | CONTRACT AWARDS | [5 empty] | CONTRACT IMPLENTATION
S/N | CONTRACT DESCRIPTION | Advert Date & Media | Approval Threshold |  | Procurement Method | Bid Opening Date | contractor | Date of Contract Award | Date of Contract Commencement | Contract Period | Contract Value (N) | Budgetary Provision | Amount Paid as At 14/2/2012 | Expected Completion Date | % of Completion as At | Remarks
(N)
1 | Procurement of 15Nos HP Desktop Computers | 20/6/2011 in Punch, Vanguard & Dawn N/Papers | FHQ Tenders Board |  | Open Competitive Bidding | 27/9/2011 | Vodaro Nig Ltd | 2016-11-11 | 18/11/2011 | SIX WEEKS | 1779750 | N37,851,672 | NIL | 31/12/2011 | 100 % Completed | Delayed Payment
2 | Purchase of 15Nos DSTV Decoder | “ ” | “ ” |  | “ ” | “ ” | Mazif Support Inv. Ltd | 16/11/11 | 18/11/2011 | “ ” | 1732500 | N37,851,672 | NIL | 31/12/2011 | 100 % Completed | “ ”
3 | Purchase of 15Nos Toshiba Laptop Computer | “ ” | “ ” |  | “ ” | “ ” | Satogam Nig. Ltd | 16/11/11 | 18/11/2011 | “ ” | 2520000 | N37,851,672. | NIL | 31/12/2011 | 100 % Completed | “ ”
4 | Supply of 10Nos Dell Projector | “ ” | “ ” |  | “ ” | “ ” | Sazab Global Ent. | 16/11/11 | 18/11/2011 | “ ” | 2152500 | N37,851,672 | NIL | 31/12/2011 | 100 % Completed | “ ”
5 | Supply of 20Nos HP Laptop Computer | “ ” | “ ” |  | Open Competitive Bidding | 27/9/2011 | Satogam Nig Ltd | 16/11/11 | 18/11/2011 | “ ” | 3360000 | N37,851,672 | NIL | 31/12/2011 | 100 % Completed | “ ”
6 | Purchase of 3Nos Video Camera | “ ” | “ ” |  | “ ” | “ ” | Dynamo Concept Ltd | 16/11/11 | 18/11/2011 | “ ” | 3654000 | N37,851,672 | NIL | 31/12/2011 | 100 % Completed | “ ”
7 | Purchase of 2No Sharp Digital Photocopier | “ ” | “ ” |  | “ ” | “ ” | MAGAT Nig Ltd | 16/11/11 | 18/11/2011 | “ ” | 4935000 | N37,851,672 | NIL | 31/12/2011 | 100 % Completed | “ ”
8 | Supply of 8No Nikon Photo Cameras | “ ” | “ ” |  | “ ” | “ ” | Dad’s Pride Nig Ltd | 16/11/11 | 18/11/2011 | “ ” | 2568000 | N37,851,672 | NIL | 31/12/2011 | 100 % Completed | “ ”
9 | Supply of Books & Library Materials | “ ” | “ ” |  | “ ” | “ ” | Satogam Nig Ltd | 16/11/11 | 18/11/2011 | “ ” | 3307080 | N37,851,672 | NIL | 31/12/2011 | 100 % Completed | “ ”
10 | Supply of 25Nos Laser-Jet Colour Photo Printers | “ ” | “ ” |  | Open Competitive Bidding | 27/9/2011 | Chris-Dennis Commercial Companies Nig Ltd | 16/11/11 | 18/11/2011 | “ ” | 1562500 | N37,851,672 | NIL | 31/12/2011 | 100 % Completed
11 | Conduct of 3-Day Workshop | “ ” | FHQ Tenders Board |  | Open Competitive Bidding | 27/9/2011 | Media Concept Int’l Ltd | 2016-11-11 | 18/11/2011 | SIX WEEKS | 10145000 | “ ” | NIL | 31/12/2011 | NOT Executed for Lack of FUND | NOT FUND
[5 empty] | SECTION:…………………………………………………. |  | Servicom, 'F' Department
PROCUREMENT RECORDS FOR 2011 FINANCIAL YEAR
NAME OF MINISTRT/AGENCY: POLICE FORMATIONS & COMMAND SECCTOR: SECURITY
S/N0 | PROJECT TITLE | PROJECT LOCATION | CONTRACTOR | CONTRACT NO. | DATE PROJECT COMMENCED | PLANNED COMPLETION DATE | TOTAL PROJECT EST. COST | APPROPRIATION IN THE 2011 BUDGET | COST VARIATION (IF ANY) | TOTAL AMOUNT RELEASE IN 2011 | TOTAL AMOUNT COMMITTED TO DATE
1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 8 | 9 | 10 | 11
| PROPAGATION AND PROCUREMENT OF EQUIPMENT FOR POLICE SERVICE DELIVERY INITIATIVES IN FORMATIONS AND COMMANDS(SERVICOM) | FHQ ABUJA/15 POLICE COMMAND HQTRS | SERVICOM THE PRESIDENCY UMULAW NIGERIA LIMITED | AGMT: NO: SERV /002/ 2011. AGMT:NO:SERV/OO1/2011 | 2011-01-01 | 31/03/2012 | 42032152 | 42032152 | NIL | 33398532 | NIL
|  | Name & Signature of the Officer Authenticating |  |  |  | Steven Esimaje
Returns………………………………………………………………………………………………..
|  | Rank/Designation ……………………………………………………………………………………………… |  | ACP
|  | Date………………………………………… | 2012-10-03
Note: Returns to be randered in hard and solf copies using Microsofty Excel
MDAs that have Donor Related Project /Programmes should reflect such in a separate Template / sheet.
PROCURMENT RECORDS
| PROCURING ENTITY (MDA): | Airwing
| MINISTRY: | NIGERIA POLICE FORCE
| FINANCIAL YEAR: | 2011
| BASIC DATA |  |  |  |  | CONTRACT AWARD | [5 empty] | CONTRACT IMPLEMENTATION
S/NO. | CONTRACT DESCRIPTION | ADVERTISEMENT DATE AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | CONTRACTOR | DATE OF CONTRACT AWARD | DATE OF CONTRACT COMMENCEMENT | CONTRACT PERIOD | CONTRACT VALUE (N) | BUDGETARY PROVISION (N) | AMOUNT PAID AS AT | EXPECTED COMPLETION DATE | % OF COMPLETION AS AT | REMARKS
1 | PURCHASE OF CAMCOPTER (SCHIEBEL BRAND) | (Daily Trust) 20/06/11 | FHQ | Restricted | 27/10/11 | Newell Perspective Limited | 30/11/2011 | 02/12/2011 | 01/01/2011-31/12/2011 | 48550000 | 700000000 | Nill | 28/12/2011 | 100% | Payment yet to be effected
Purchase of FLIR MkII for 5N-PAW
2 | Purchase of Nightsun with 40m Candlelight Capacity for 5N-PAW | (Daily Trust) 20/06/11 | " | Restricted | 27/10/11 | Beta Transformator Co. Nig. Ltd | " | 02/12/2011 | 01/01/2011-31/12/2011 | 33300000 |  | Nill | 28/12/2011 | 100% | Payment yet to be effected
3 | Purchase of SLASS and Surveillance Accessories for Installation on 5N-PAW | (Daily Trust) 20/06/11 | " | Restricted | 27/10/11 | Nelrigral Enterprises Ltd | " | 02/12/2011 | 01/01/2011-31/12/2011 | 46650000 |  | Nill | 28/12/2011 | 100% | Payment yet to be effected
4 | Installation of Night Vision and Surveillance Equipment on Helicopter Bell 427 with Registration 5N-PAW | (Daily Trust) 20/06/11 | " | Restricted | 27/10/11 | Eglobegree Int'l Nig. Ltd | " | 02/12/2011 | 01/01/2011-31/12/2012 | 41850000 |  | Nill | 29/12/2011 | 100% | Payment yet to be effected
5 | Purchase of Forward Looking Infrared Camera for 5N-POL | (Daily Trust) 20/06/11 | " | Restricted | 27/10/11 | P. S. I. International Co. Ltd | " | 02/12/2011 | 01/01/2011-31/12/2012 | 49330000 |  | Nill | 28/12/2011 | 100% | Payment yet to be effected
6 | Purchase of Spectrolab SX-16 Nightsun for 5N-POL | (Daily Trust) 20/06/11 | " | Restricted | 27/10/11 | Simidia S & I Int'l Company Ltd | " | 01/12/2011 | 01/01/2011-31/12/2012 | 34198000 |  | Nill | 29/12/2011 | 100% | Payment yet to be effected
7 | Purchase of Avoinics Mission and Surveillance Equipment with Accessories for Installation on 5N-POL | (Daily Trust) 20/06/11 | " | Restricted | 27/10/11 | Beta Transformator Co. Nig. Ltd | " | 02/12/2011 | 01/01/2011-31/12/2012 | 47185000 |  | Nill | 28/12/2011 | 100% | Payment yet to be effected
8 | Installation of Surveillance and Upgrade of Avionics and Communication of Equipment for 5N-POL | (Daily Trust) 20/06/11 | " | Restricted | 27/10/11 | Unibright Engineering Ltd | " | 02/12/2011 | 01/01/2011-31/12/2012 | 43520000 |  | Nill | 28/12/2011 | 100% | Payment yet to be effected
9 | Purchase and Installation of Rappelling Kit for Bell 427 5N-SGE | (Daily Trust) 20/06/11 | " | Restricted | 27/10/11 | Eglobegree Int'l Nig. Ltd | " | 02/12/2011 | 01/01/2011-31/12/2011 | 48850000 |  | Nill | 29/12/2011 | 100% | Payment yet to be effected
10 | Purchase and Installation of Rappelling Kit for 5N-FHQ | (Daily Trust) 20/06/11 | " | Restricted | 27/10/11 | Newell Perspective Limited | " | 02/12/2011 | 01/01/2011-31/12/2012 | 48320000 |  | Nill | 29/12/2011 | 100% | Payment yet to be effected
11 | Purchase of Ultra 8500 Forward Looking Intra Red Camera for 5N-LEH | (Daily Trust) 20/06/11 | " | Restricted | 27/10/11 | Simidia S & I Int'l Company Ltd | " | 01/12/2011 | 01/01/2011-31/12/2012 | 49590000 |  | Nill | 28/12/2011 | 100% | Payment yet to be effected
12 | Installation of SpectroLab SX-16 Nightsun and Accessories for 5N-LEH | (Daily Trust) 20/06/11 | " | Restricted | 27/10/11 | Unibright Engineering Ltd | " | 02/12/2011 | 01/01/2011-31/12/2012 | 44300000 |  | Nill | 28/12/2011 | 100% | Payment yet to be effected
13 | Purchase of Honeywell MFRD and Installation on 5N-LEH Coupling Radar and GPS for Terrain Flying | (Daily Trust) 20/06/11 | " | Restricted | 27/10/11 | Eglobegree Int'l Nig. Ltd | " | 02/12/2011 | 01/01/2011-31/12/2012 | 36210000 |  | Nill | 28/12/2011 | 100% | Payment yet to be effected
14 | Purchase of Ultra 8500 FLIR for 5N-KSH | (Daily Trust) 20/06/11 | " | Restricted | 27/10/11 | P. S. I. International Co. Ltd | " | 02/12/2011 | 01/01/2011-31/12/2012 | 49380000 |  | Nill | 28/12/2011 | 100% | Payment yet to be effected
15 | Installation of SpectroLab SX-16 Nightsun and Accessories with 40m Candlelight for 5N-KSH | (Daily Trust) 20/06/11 | " | Restricted | 27/10/11 | Nelrigral Enterprises Ltd | " | 02/12/2011 | 01/01/2011-31/12/2012 | 44220000 |  | Nill | 29/12/2011 | 100% | Payment yet to be effected
16 | Purchase of Honeywell MFRD and Installation on 5N-KSH Coupling Radar and GPS for Terrain Flying | (Daily Trust) 20/06/11 | " | Restricted | 27/10/11 | Simidia S & I Int'l Company Ltd | " | 01/12/2011 | 01/01/2011-31/12/2012 | 34200000 |  | Nill | 29/12/2011 | 100% | Payment yet to be effected
|  |  | TOTAL | [6 empty] | 699653000 | 700000000
SECTION: FORCE INTELLIGENCE BUREAU
PROCUREMENT RECORDDS FOR 2011 FINANCIAL YEAR.
THE NIGERIA POLICE, FORCE HEADQUARTERS ABUJA. SECTOR: INTELLIGENCE
S/NO | PROJECT TITLE | PROJECT LOCATION | CONTRACTOR | CONTRACT NO. | DATE PROJECT COMMENCED | PLANNED COMPLETION DATE | TOTAL PROJECT EST. COST | APPROPRIATION IN THE 2011 BUDGET | COST VARIATION (IF ANY) | TOTAL AMOUNT RELEASE IN 2011 | TOTAL AMOUNT COMMITED TO DATE
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
a) | PROCUREMENT OF SECURITY/CRIMINAL INTELLIGENCE EQUIPMENTS | FHQ Abuja, 36 States Headquarters and 12 Zones. | Boardmark Limited, 6, Lekki Close,Garki-Abuja. | 23010128 | 01/2011. | 12/2011. | N1,575,190,000 | ₦74,863,626 | Nil | ₦74,863,626 | ₦74,863,626
b) |  |  | DCS Security Systems Ltd Plot 61-A, Road 3, VGC Ajah-Lekki, Lagos-Nigeria | 23010128
c) |  |  | Setronics International Nig. Ltd, No. 44, Oyemekun Road Akure, Ondo State. | 23010128
d) |  |  | Assured Security Equipment & Service Ltd Suit D1 Kebbi House, 10 Kur Mohammed Way, Central Business District, Abuja. | 23010128
PROCUREMENT RECORDS FOR FORCE INTELLIGENCE BUREAU
PROCURING ENTITY (MDA)
MINISTRY: THE NIGERIA POLICE
FINANCIAL YEAR: 2011
S/NO | CONTRACT DESCRIPTION | ADVERT. DATE | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | CONTRACTOR | DATE OF CONTRT. AWARD | DATE OF CONTRT. COMMENCEMENT. | CONTRACT PERIOD | CONTRACT VALUE | BUDGETARY PROVISION | AMOUNT PAID AS AT | EXPECTED COMPLETION DATE | 0/0 OF COMPLETION AS AT | REMARKS
1 | PROCUREMENT OF SECURITY/CRIMINAL INTELLIGENCE EQUIPMENTS | For security reasons their war no advertisment T | IGP | SELECTIVE | selective tendering | Boardmark Limited, 6, Lekki Close,Garki-Abuja. | 2011-11-30 | January to December | January to December | ₦74,863,626.00 | ₦74,863,626 | payment process in progress | 2011-12-01 | 100%
DCS Security Systems Ltd Plot 61-A, Road 3, VGC Ajah-Lekki, Lagos-Nigeria
Setronics International Nig. Ltd, No. 44, Oyemekun Road Akure, Ondo State.
Assured Security Equipment & Service Ltd Suit D1 Kebbi House, 10 Kur Mohammed Way, Central Business District, Abuja.
The Nigeria Police
The Ministry of Police Affairs
2011

## National Boundary .C
PROCUREMENT RECORDS
PROCURING ENTITY (MDA): |  | NATIONAL BOUNDARY COMMISSION
MINISTRY: |  | THE PRESIDENCY
FINANCIAL YEAR: |  | 2011
| BASIC DATA |  |  |  |  | CONTRAT AWARD | [6 empty] | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | ADVERTISEMENT DATE AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | CONTRACTOR | DATE OF CONTRACT AWRAD | CONTRACTOR | DATE OF CONTRACT COMMNCEMENT | CONTRACT PERIOD | CONTRACT VALUE (N) | BUDGETARY PROVISSION | AMOUNT PAID AS AT 31/12/11 | EXPECTED COMPLETION DATE | % OF COMPLETION AS AT | REMARKS
1 | Printing of letter headed paper | 2/12/2011 NBC Notice Boards | Below N 2.5 Million | Contract | 16/11/11 | Ujeady Nig. Ltd | 23/12/11 |  | 23/12/11 | 2 Weeks | 2493000 | 10072131 | Nil | 2012-06-01 | 100
2 | Supply of Photocy paper | 28/11/11 NBC Notice Boards | Below N 2.5 Million | Contract | 2011-12-12 | K .C . Integrated Enterprises Co. | 15/12/11 |  | 15/12/11 | 2 Weeks | 999000 | 10072131 | 999000 | 29/12/11 | 100
3 | Supply of Photocy paper | 28/11/11 NBC Notice Boards | Below N 2.5 Million | Contract | 2011-12-12 | M. Babikir & Co. | 15/12/11 | 15/12/11 | 15/12/11 | 2 Weeks | 999000 | 10072131 | 999000 | 29/12/11 | 100
4 | Supply of Office Equipment | 10/11/2011NBC Notice Boards | Below N 2.5 Million | Contract | 24/11/11 | Service Quotient Ltd | 2011-07-12 |  | 13/12/11 | 2 Weeks | 1559925 | 10072131 | 1559925 | 27/12/2011 | 100
5 | Maintenace work on Block B | 5/1/2012 NBC Notice Boards | Below N 2.5-N50 Million | Contract | 19/01/12 | Avalon Design Konsult | 25/01/12 | Avalon Design Konsult | 2012-01-02 | 2 Weeks | 9890345 | 19980993 | 9395827.75 | 15/2/12 | 100
15941270

## OAG
PROCUREMENT RECORDS
PROCURING ENTITY (MDA): |  |  | OFFICE OF THE ACCOUNTANT-GENERAL OF THE FEDERATION
MINISTRY: |  |  | FEDERAL MINISTRY OF FINANCE
FINANCIAL YEAR: |  |  | 2011
|  | BASIC DATA |  |  |  |  | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | ADVERTISEMENT | APPROVAL | PROCUREMENT | BID | CONTRACTOR | DATE OF | DATE OF | CONTRACT | CONTRACT | BUDGETARY | AMOUNT | EXPECTED | % OF
|  | DATE AND MEDIA | THRESHOLD | METHOD | OPENING |  | CONTRACT | CONTRACT | PERIOD | VALUE (N) | PROVISION | PAID AS AT | COMPLETION | COMPLETION | REMARKS
[5 empty] | DATE |  | AWARD | COMMENCEMENT | Weeks |  | (N) | 31/12/11 | DATE | AS AT 31/12
1 | Construction of FPO | 30/5/11 - The | MTB | NCB | 13/6/11 | Allianz Dev. Co. | 2011-04-07 | 18/7/11 | 24
| Gusau, Zamfara State. | Nation , F.T.J & | [6 empty] | (168 days) | 120555487.5 | 15504720.16 | 18080323.12 | 2012-06-01 | 15%
Leadership
2 | Constrution of FPO | 30/5/11 - The | MTB | NCB | 13/6/11 | Coxmartinz Eng.
| Uyo, Akwa Ibom State | Nation , F.T.J & |  |  |  | Service Ltd. | 2011-04-07 | 18/7/11 | 24
|  | Leadership | [6 empty] | (168 days) | 121685978.06 | 15504720.16 | 18252896.7 | 2012-06-01 | 15%
3 | Construction of FPO | 30/5/11 - The | MTB | NCB | 13/6/11 | Jamec West
| Umuahia, Abia State | Nation , F.T.J & |  |  |  | Africa Ltd | 2011-04-07 | 18/7/11 | 32
|  | Leadership | [6 empty] | (224 days) | 121428893 | 15504720.16 | - | 2012-02-03 | 25%
4 | Construction of FPO | 30/5/11 - The | MTB | NCB | 13/6/11 | Dogon Ruwa
| Bauchi, Bauchi State | Nation , F.T.J & |  |  |  | Nig. Ltd | 2011-04-07 | 18/7/11 | 24
|  | Leadership | [6 empty] | (168 days) | 120746843.07 | 15504720.16 | - | 2012-06-01 | 5%
5 | Rehabilitation of FPO | 30/5/11 - The | MTB | NCB | 13/6/11 | Water Fall Prime
| Maiduguri, Borno State | Nation , F.T.J & |  |  |  | Trust Ltd | 2011-04-07 | 18/7/11 | 6
|  | Leadership | [6 empty] | (42 days) | 20674788 | 16433628.71 | 19641100.84 | 2011-02-09 | 100%
6 | Rehabilitation of FPO | 30/5/11 - The | MTB | NCB | 13/6/11 | Kaoldesh Nig. Ltd | 2011-04-07 | 18/7/11 | 6
| Kano, Kano State | Nation , F.T.J & | [6 empty] | (42 days) | 20102707.01 | 16433628.71 | - | 2011-02-09 | 10%
7 | Rehabilitation of FPO | Leadership
| Dutse, Jigawa State. | 30/5/11 - The | MTB | NCB | 13/6/11
|  | Nation , F.T.J & |  |  |  | Prestige Nig. Ltd | 2011-04-07 | 18/7/11 | 6
|  | Leadership | [6 empty] | (42 days) | 20441867.96 | 16433628.71 | 15106667.3 | 2011-02-09 | 100%
PROCUREMENT RECORDS
PROCURING ENTITY (MDA): |  |  | OFFICE OF THE ACCOUNTANT-GENERAL OF THE FEDERATION
MINISTRY: |  |  | FEDERAL MINISTRY OF FINANCE
FINANCIAL YEAR: |  |  | 2011
|  | BASIC DATA |  |  |  |  | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | ADVERTISEMENT | APPROVAL | PROCUREMENT | BID | CONTRACTOR | DATE OF | DATE OF | CONTRACT |  | BUDGETARY | AMOUNT | EXPECTED | % OF
|  | DATE AND MEDIA | THRESHOLD | METHOD | OPENING |  | CONTRACT | CONTRACT | PERIOD |  | PROVISION | PAID AS AT | COMPLETION | COMPLETION | REMARKS
[5 empty] | DATE |  | AWARD | COMMENCEMENT | Weeks |  | (N) | 31/12/11 | DATE | AS AT 31/12
8 | Rehabilitation of FPO | 30/5/11 - The | MTB | NCB | 13/6/11
| Akure, Ondo State | Nation , F.T.J & |  |  |  | TAAD Const. Co. |  |  | 6
|  | Leadership |  |  |  | Ltd | 2011-04-07 | 18/7/11 | (42 days) | 20931823.5 | 16433628.71 | - | 2011-02-09 | 10%
9 | Rehabilitation of FPO | 30/5/11 - The | MTB | NCB | 13/6/11
| Benin, Edo State | Nation , F.T.J & |  |  |  | Enomas |  |  | 6
|  | Leadership |  |  |  | Computers Ltd | 2011-04-07 | 18/7/11 | (42 days) | 20528823.94 | 16433628.71 | 14969601.77 | 2011-02-09 | 100%
10 | Rehabilitation of FPO | 30/5/11 - The | MTB | NCB | 13/6/11
| Asaba, Delta State | Nation , F.T.J & |  |  |  | Zaftig Ltd | 2011-04-07 | 18/7/11 | 6
|  | Leadership | [6 empty] | (42 days) | 20203821.79 | 16433628.71 | 19193630.7 | 2011-02-09 | 100%
11 | Rehabilitation of FPO | 30/5/11 - The | MTB | NCB | 13/6/11 | Demski Nigeria
| Lagos II, Lagos State | Nation , F.T.J & |  |  |  | Ltd | 2011-04-07 | 18/7/11 | 6
|  | Leadership | [6 empty] | (42 days) | 20487397.39 | 16433628.71 | 15000000 | 2011-02-09 | 100%
12 | Furnishing of FPO | 30/5/11 - The | MTB | NCB | 13/6/11
| Maiduguri, Borno State | Nation , F.T.J & |  |  |  | D@ech Nig. | 2011-04-07 | 18/7/11 | 3
|  | Leadership |  |  |  | Ltd |  |  | (21 days) | 16663936.25 | 13503540.16 | 16663936.25 | 2011-12-08 | 100%
13 | Furnishing of FPO Kano, | 30/5/11 - The | MTB | NCB | 13/6/11 | Boltop Golden
| Kano State. | Nation , F.T.J & |  |  |  | Heritage | 2011-04-07 | 18/7/11 | 3
|  | Leadership | [6 empty] | (21 days) | 16663936.25 | 13503540.16 | 16663936.25 | 2011-12-08 | 100%
PROCUREMENT RECORDS
PROCURING ENTITY (MDA): |  |  | OFFICE OF THE ACCOUNTANT-GENERAL OF THE FEDERATION
MINISTRY: |  |  | FEDERAL MINISTRY OF FINANCE
FINANCIAL YEAR: |  |  | 2011
|  | BASIC DATA |  |  |  |  | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | ADVERTISEMENT | APPROVAL | PROCUREMENT | BID | CONTRACTOR | DATE OF | DATE OF | CONTRACT |  | BUDGETARY | AMOUNT | EXPECTED | % OF
|  | DATE AND MEDIA | THRESHOLD | METHOD | OPENING |  | CONTRACT | CONTRACT | PERIOD |  | PROVISION | PAID AS AT | COMPLETION | COMPLETION | REMARKS
[5 empty] | DATE |  | AWARD | COMMENCEMENT | Weeks |  | (N) | 31/12/11 | DATE | AS AT 31/12
14 | Furnishing of FPO | 30/5/11 - The | MTB | NCB | 13/6/11 | Hi-Mansion
| Dutse, Jigawa State | Nation , F.T.J & |  |  |  | Allied and | 2011-04-07 | 18/7/2011 | 3
|  | Leadership |  |  |  | Services |  |  | (21 days) | 16542750 | 13503540.16 | 10000000 | 2011-12-08 | 100%
15 | Furnishing of FPO Akure, | 30/5/11 - The | MTB | NCB | 13/6/11 | Fadze Global |  |  | 3
| Ondo State | Nation , F.T.J & |  |  |  | Concept Ltd | 2011-04-07 | 18/7/2011 | (21 days) | 16542750 | 13503540.16 | 16542750 | 2011-12-08 | 100%
Leadership
16 | Furnsishing of FPO | 30/5/11 - The | MTB | NCB | 13/6/11 | Adatech
| Benin, Edo State | Nation , F.T.J & |  |  |  | Integrated |  |  | 3
|  | Leadership |  |  |  | Services Ltd | 2011-04-07 | 18/7/2011 | (21 days) | 16663750 | 13503540.16 | 16663750 | 2011-12-08 | 100%
17 | Furnishing of FPO Asaba, | 30/5/11 - The | MTB | NCB | 13/6/11 | Matsogi Nig.
| Delta State | Nation , F.T.J & |  |  |  | Ltd | 2011-04-07 | 18/7/2011 | 3
|  | Leadership | [6 empty] | (21 days) | 16663750 | 13503540.16 | 10000000 | 2011-12-08 | 100%
18 | Furnishing of FPO | 30/5/11 - The | MTB | NCB | 13/6/11 | Frank Tech
| Calabar, Cross River | Nation , F.T.J & |  |  |  | Global |  |  | 3
| State | Leadership |  |  |  | Resources Ltd | 2011-04-07 | 18/7/2011 | (21 days) | 17036250 | 13503540.16 | 17036250 | 2011-12-08 | 100%
19 | Furnishing of FPO | 30/5/11 - The | MTB | NCB | 13/6/11 | Mirabel Global
| Lagos I, Lagos State | Nation , F.T.J & |  |  |  | Resources Ltd | 2011-04-07 | 18/7/2011 | 3
|  | Leadership | [6 empty] | ((21 days) | 16542750 | 13503540.16 | 16542750 | 2011-12-08 | 100%
PROCUREMENT RECORDS
PROCURING ENTITY (MDA): |  | OFFICE OF THE ACCOUNTANT-GENERAL OF THE FEDERATION
MINISTRY: |  | FEDERAL MINISTRY OF FINANCE
FINANCIAL YEAR: |  | 2011
|  | BASIC DATA |  |  |  |  | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | ADVERTISEMENT | APPROVAL | PROCUREMENT | BID | CONTRACTOR | DATE OF | DATE OF | CONTRACT |  | BUDGETARY | AMOUNT | EXPECTED | % OF
|  | DATE AND MEDIA | THRESHOLD | METHOD | OPENING |  | CONTRACT | CONTRACT | PERIOD |  | PROVISION | PAID AS AT | COMPLETION | COMPLETION | REMARKS
[5 empty] | DATE |  | AWARD | COMMENCEMENT |  |  | (N) | 31/12/11 | DATE | AS AT 31/12
20 | Furnishing of FPO | 30/5/11 - The | MTB | NCB | 13/6/11 | Royaltech | 2011-04-07 | 18/7/2011 | 3
| Lagos II, Lagos State | Nation , F.T.J & |  |  |  | Management |  |  | (21 days) | 16542750 | 13503540.16 | 16542750 | 2011-12-08 | 100%
|  | Leadership |  |  |  | Sevices Ltd
21 | Furnishing of FPO | 30/5/11 - The | MTB | NCB | 13/6/11 | Unisoft
| Lokoja, Kogi State | Nation , F.T.J & |  |  |  | Network Ltd | 2011-04-07 | 18/7/2011 | 3
|  | Leadership | [6 empty] | (21 days) | 16668750 | 13503540.16 | 16668750 | 2011-12-08 | 100%
22 | Furnishing of FPO | 30/5/11 - The | MTB | NCB | 13/6/11 | Timsi Global
| Yenagoa, Bayelsa | Nation , F.T.J & |  |  |  | Resources Ltd | 2011-04-07 | 18/7/2011 | 3
| State | Leadership | [6 empty] | (21 days) | 17261296.5 | 13503540.16 | 9163649.41 | 2011-12-08 | 95%
23 | Furnishing of Classroom | 30/5/11 - The | MTB | NCB | 13/6/11 | Martex
| at FTA Orozo | Nation , F.T.J & |  |  |  | Integrated | 2011-04-07 | 18/7/2011 | 6
|  | Leadership |  |  |  | Concept Ltd |  |  | (42 days) | 30082500 | 13503540.12 | 25000000 | 2011-02-09 | 100%
24 | Provision of Equipment | 30/5/11 - The | MTB | NCB | 13/6/11 | Edgab | 2011-04-07 | 18/7/2011 | 6
| for Admin Block at | Nation , F.T.J & |  |  |  | Construction |  |  | (42 days) | 17876240.55 | 13503540.12 | 17870240.55 | 2011-02-09 | 95%
| FTA Orozo | Leadership |  |  |  | Ltd
25 | Provision of Equipment | 30/5/11 - The | MTB | NCB | 13/6/11 | Ndeya Nig. Ltd | 2011-04-07 | 18/7/2011 | 6
| Library Block at FTA, | Nation , F.T.J & | [6 empty] | (42 days) | 15714430 | 13503540.12 | - | 2011-02-09 | 5%
| Orozo, Abuja | Leadership
PROCUREMENT RECORDS
PROCURING ENTITY (MDA): |  |  | OFFICE OF THE ACCOUNTANT-GENERAL OF THE FEDERATION
MINISTRY: |  |  | FEDERAL MINISTRY OF FINANCE
FINANCIAL YEAR: |  |  | 2011
|  | BASIC DATA |  |  |  |  | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | ADVERTISEMENT | APPROVAL | PROCUREMENT | BID | CONTRACTOR | DATE OF | DATE OF | CONTRACT |  | BUDGETARY | AMOUNT | EXPECTED | % OF
|  | DATE AND MEDIA | THRESHOLD | METHOD | OPENING |  | CONTRACT | CONTRACT | PERIOD |  | PROVISION(N) | PAID AS AT | COMPLETION | COMPLETION | REMARKS
[5 empty] | DATE |  | AWARD | COMMENCEMENT |  |  | (N) | 31/12/11 | DATE | AS AT 31/12
26 | Provision of Equipment | 30/5/11 - The | MTB | NCB | 13/6/11 | Filakay | 2011-04-07 | 18/7/2011 | 6
| for Clinic Block at | Nation , F.T.J & |  |  |  | Ventures |  |  | (42 days) | 8650000 | 13503540.12 | 8650000 | 2011-02-09 | 100%
| FTA Orozo, Abuja | Leadership
27 | Purchase of Statutory | 30/5/11 - The | MTB | NCB | 13/6/11 | Donwell Hinds |  |  | 3
| Verification Stamps | Nation , F.T.J & |  |  |  | Integrated Ltd | 2011-04-07 | 18/7/2011 | (21 days) | 11950000 | 35175905.4 | 11950000 | 2011-12-09 | 100%
Leadership
28 | Provision of Bore Hole | 30/5/11 - The | MTB | NCB | 13/6/11 | Al-Jumeira
| at FPO Jalingo, Taraba | Nation , F.T.J & |  |  |  | Global Ltd | 2011-04-07 | 18/7/2011 | 6
| State. | Leadership | [6 empty] | (42 days) | 15750000 | 35175905.4 | 7000000 | 2011-12-08 | 70%
29 | Provision of Bore Hole | 30/5/11 - The | MTB | NCB | 13/6/11 | Sammya Nigeria
| at FPO Ilorin, Abeokuta, | Nation , F.T.J & |  |  |  | Ltd | 2011-04-07 | 18/7/2011 | 6
| Oshogbo, Ado-Ekiti | Leadership | [6 empty] | (42 days | 25750000 | 35175905.4 | 12000000 | 2011-02-09 | 75%
and Ibadan
30 | Provision of Bore Hole | 30/5/11 - The | MTB | NCB | 13/6/11 | Abumado Inv.
| at FPO Awka, Calabar | Nation , F.T.J & |  |  |  | Ltd | 2011-04-07 | 18/7/2011 | 6
| and Yenagoa | Leadership | [6 empty] | (42 days) | 14450000 | 35175905.4 | 7980000 | 2011-02-09 | 80%
31 | Provision of Bore Hole | 30/5/11 - The | MTB | NCB | 13/6/11 | Kagaad
| at Lokoja | Nation , F.T.J & |  |  |  | Associate | 2011-04-07 | 18/7/2011 | 6
|  | Leadership | [6 empty] | (42 days) | 5450000 | 35175905.4 | - | 2011-02-09 | 5%
PROCUREMENT RECORDS
PROCURING ENTITY (MDA): |  |  | OFFICE OF THE ACCOUNTANT-GENERAL OF THE FEDERATION
MINISTRY: |  |  | FEDERAL MINISTRY OF FINANCE
FINANCIAL YEAR: |  |  | 2011
|  | BASIC DATA |  |  |  |  | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | ADVERTISEMENT | APPROVAL | PROCUREMENT | BID | CONTRACTOR | DATE OF | DATE OF | CONTRACT |  | BUDGETARY | AMOUNT | EXPECTED | % OF
|  | DATE AND MEDIA | THRESHOLD | METHOD | OPENING |  | CONTRACT | CONTRACT | PERIOD |  | PROVISION(N) | PAID AS AT | COMPLETION | COMPLETION | REMARKS
[5 empty] | DATE |  | AWARD | COMMENCEMENT |  |  | (N) | 31/12/11 | DATE | AS AT 31/12
32 | Replacement of Broken | 30/5/11 - The | MTB | NCB | 13/6/11 | Muson |  |  | 12
| Tiles in Treasury House | Nation , F.T.J & |  |  |  | Construction | 2011-04-07 | 18/7/2011 | (84 days) | 30045200 | 18004720.33 | 20976560 | 14/10/2011 | 100%
Leadership
33 | Rehabilitation of Fence | 30/5/11 - The | MTB | NCB | 13/6/11 | Hollamarc
| Gate House & Kerbs | Nation , F.T.J & |  |  |  | Integrated | 2011-04-07 | 18/7/2011 | 12 | 12000000 | 18004720.33 | 7000000 | 14/10/2011 | 100%
| round OAGF | Leadership |  |  |  | Service |  |  | (84 days)
34 | Furnishing of FPO | 27/6/11 - The | MTB | NCB | 2011-11-07 | Rencon PDC | 14/9/2011 | 28/9/2011 | 3 | 16548000 | 13503540.16 | 12105125 | 25/10/2011 | 100%
| Abeokuta, Ogun State | Nation , F.T.J & |  |  |  | Ltd |  |  | (21 days)
Leadership
35 | Furnishing of FPO | 27/6/11 - The | MTB | NCB |  | Danzinger Nig.
| Birnin Kebbi, Kebbi | Nation , F.T.J & |  |  |  | Ltd | 14/9/2011 | 28/9/2011 | 3
| State | Leadership | [6 empty] | (21 days) | 16386200 | 13503540.16 | 11943376 | 25/10/11 | 100%
36 | Furnishing of FPO Ado | 27/6/11 - The | MTB | NCB | 2011-11-07 | Summa Cum
| Ekiti, Ekiti State | Nation , F.T.J & |  |  |  | Laude | 14/9/2011 | 28/9/2011 | 3
|  | Leadership | [6 empty] | (21 days) | 16275000 | 13503540.16 | 11832376 | 25/10/11 | 85%
37 | Provision of Books & | 27/6/11 - The | MTB | NCB | 2011-11-07 | The Book Co.
| Reference Materials | Nation , F.T.J & |  |  |  | Ltd | 14/9/2011 | 28/9/2011 | 3
| of OAGF Library | Leadership | [6 empty] | (21 days) | 5227293.75 | 25007080.33 | 5227293.75 | 25/10/11 | 100%
PROCUREMENT RECORDS
PROCURING ENTITY (MDA): |  |  | OFFICE OF THE ACCOUNTANT-GENERAL OF THE FEDERATION
MINISTRY: |  |  | FEDERAL MINISTRY OF FINANCE
FINANCIAL YEAR: |  |  | 2011
|  | BASIC DATA |  |  |  |  | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | ADVERTISEMENT | APPROVAL | PROCUREMENT | BID | CONTRACTOR | DATE OF | DATE OF | CONTRACT |  | BUDGETARY | AMOUNT | EXPECTED | % OF
|  | DATE AND MEDIA | THRESHOLD | METHOD | OPENING |  | CONTRACT | CONTRACT | PERIOD |  | PROVISION(N) | PAID AS AT | COMPLETION | COMPLETION | REMARKS
[5 empty] | DATE |  | AWARD | COMMENCEMENT |  |  | (N) | 31/12/11 | DATE | AS AT 31/12
38 | Provision of Library | 27/6/11 - The | MTB | NCB | 2011-11-07 | First Aralac | 14/9/2011 | 28/9/2011 | 3 | 16609963.6 | 25007080.33 | 16609963 | 25/10/2011 | 100%
| Furniture & Tools for | Nation , F.T.J & |  |  |  | Global Ltd |  |  | (21 days)
| OAGF Library | Leadership
39 | Provision of Library | 27/6/11 - The | MTB | NCB | 2011-11-07 | Solid Frame | 14/9/2011 | 28/9/2011 | 3
| Automation | Nation , F.T.J & |  |  |  | Nig. Ltd |  |  | (21 days) | 14491317.75 | 25007080.33 | 14491317.75 | 25/10/11 | 100%
Leadership
1084837245.87

## Neuropsychiatric Aro Abeokuta
PROCUREMENT RECORDS
PROCURING ENTITY (MDA): |  |  | NEUROPSYCHIATRIC HOSPITAL, ARO, ABEOKUTA
MINISTRY: |  |  | FEDERAL MINISTRY OF HEALTH
FINANCIAL YEAR: |  |  | 1ST JANUARY - 31ST DECEMBER, 2011
| BASIC DATA |  |  |  |  | CONTRACT AWARD | [5 empty] | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | ADVERTISEMENT DATE AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | CONTRACTOR | DATE OF CONTRACT AWARD | DATE OF CONTRACT COMMENCEMENT | CONTRACT PERIOD | CONTRACT VALUE (N) | BUDGETARY PROVISION (N) | AMOUNT PAID AS AT DECEMBER, 2011 | EXPECTED COMPLETION DATE | % OF COMPLETION AS AT | REMARKS
1 | Installation of 33 KVA Line at Aro | Punch Newspaper of Wednesday, June 01, 2011 and Federal Tenders Journal of Monday, June 13 - Sunday, June 26, 2011. |  | Open tendering | 6th Sept, 2011 | Tommy Toak Enterprises Limited | 21st Sept, 2011 | 23rd Sept, 2011 | 6 Weeks | 24107000 | 28078957 | 18296302.5 | 3rd Nov, 2011 | 100%
2 | Re-construction of 2nd Gate with Gate House at Lantoro Annexe | Punch Newspaper of Wednesday, June 01, 2011 and Federal Tenders Journal of Monday, June 13 - Sunday, June 26, 2011. |  | Open tendering | 6th Sept, 2011 | Paul Ogunrinade Enterprises Limited | 21st Sept, 2011 | 23rd Sept, 2011 | 10 Weeks | 12061681.07 | 15443426 | 9318439.6 | 30th Nov, 2011 | 100%
3 | Re-roofing and Re-furbishing of EEG/ECT Building including the drainage system | Punch Newspaper of Wednesday, June 01, 2011 and Federal Tenders Journal of Monday, June 13 - Sunday, June 26, 2011. |  | Open tendering | 6th Sept, 2011 | Solid Gold Limited | 21st Sept, 2011 | 23rd Sept, 2011 | 6 Weeks | 13269000 | 14039478 | 8740047.5 | 3rd Nov, 2011 | 100%
4 | Equipping of the New Multi-purpose Lecture/Conference Hall at Lantoro | Punch Newspaper of Wednesday, June 01, 2011 and Federal Tenders Journal of Monday, June 13 - Sunday, June 26, 2011. |  | Open tendering | 13th Feb, 2012 | (i) Sun-Smadeko Enterprises | 15th Feb, 2012 | 15th Feb, 2012 | 2 Weeks | 475000 | 15549348 | 9045929.31 | 28th Feb, 2012 | 20%
[6 empty] | (ii) Softpedal Nigeria Limited | 15th Feb, 2012 | 15th Feb, 2012 | 2 Weeks | 960750 |  |  | 28th Feb, 2012
[6 empty] | (iii) Muyiwa Bamgboye Enterprises Limited | 16th Feb, 2012 | 16th Feb, 2012 | 2 Weeks | 2800000 |  |  | 29th Feb, 2012
[6 empty] | (iv) Akins and Smith Limited | 20th Feb, 2012 | 20th Feb, 2012 | 2 Weeks | 5121513.16 |  |  | 5th March, 2012
[6 empty] | (v) Studio 7 Production | 21st Feb, 2012 | 21st Feb, 2012 | 2 Weeks | 1536400 |  |  | 5th March, 2012
60331344.23

## FMI
FEDERAL MINISTRY OF INFORMATION
PROCUREMENT DEPARTMENT
PROCUREMENT RECORDS FOR 2O11 FINANCIAL YEAR (CAPITAL)
S/N | PROJECT/ITEM PROCURED | BUDGET ALLOCATION | PROCUREMENT METHOD | AMOUNT | CONTRACT AWARDEE | DEPT. | DATE OF AWARD | DATE OF | REMARK
|  |  |  | AWARDED |  |  |  | COMPLETION
1 | Purchase of Vans | 36395850.23
| Mobile AB Vans | 24850000 | Single Source | 24850000 | Asian Cica Hall Nig | Public | 2011-12-21 | 31/12/11
[5 empty] | Ltd | Communication
| Equipment of Vans |  | NCB | 6322000 | Ahamiks | Public | 21/12/11
[6 empty] | Communication |  | On-going
| Plate numbering | 11545850 | NCB | 1328900 | PATS Peugeot Enterprises | Public | 20/12/11 | 0n-going
Communication
2 | Purchase of Office Furniture & | Nill
Fittings
Ongoing Projects
3 | Purchase of Fire Fighting | 3780991
Equipment
Ongoing Projects
| Procurement and Installation of anti fire Device | 3780991 | NCB | 2575000 | Tran-femmy Nig Ltd | HRM | 2011-12-01 | 5/1/12 | Completed
4 | Purchase of Library Books & | 51257596
Equipment
| Ongoing Projects |  |  |  |  | .
| Production of Publications | 3621718 | NCB | 3375000 | Pinkaso Good Printing Ltd | Res & Production | 2011-12-06 | 2011-12-23 | Completed
| Production of Publication of Documentaries | 3621748 | NCB | 3280000 | Selok Ventures Ltd | PRPD | 2011-12-07 | 2012-01-23 | Completed
| Digitization of Archives | 22007080 | NCB | 3816190 | Digital Insight Tech | NA | 2011-12-23 | 31/1/12 | Completed
| Installation of Digital Equipment | 22007080 | NCB | 16095238 | Quadrant Global Concept Ltd | NA | 2011-01-24 | 2012-02-23 | Completed
NEW PROJECTS
5 | Purchase of Industrial | 34675945
Equipment
Ongoing Projects
| IRMS Infrastructure Development (Radio Monitoring Stations) | 14486873 |  |  |  | FMCT
| Pilot Project-Video conference | 14756027 | NCB | 14041580 | NAJ Global Engr Ltd | IT | 2012-01-24 | 2012-02-23 | Completed
Facility
| Development of Audio Visual and Public Enlightenment Training Centres | 5432845 | NCB | 4590000 | PENCO Multi | PC | 2011-12-12 | 22/12/11 | Completed
Concepts LTD
NEW PROJECTS
6 | Construction/Provision of Office | 33211328
Buildings
Ongoing Projects
Completion of Firc Ado-Ekiti Zonal Federal Information Resource Centre, Ado- Ekiti
Nill
| Sokoto Zonal Resources Centre | 33211328
| Construction |  |  | 27287233.05 | Ivory Link Int Nig Ltd | PC | 2012-02-02 | On-going
| Consultancy Services |  |  | 3500000 | Paldoated Nig Ltd | PC | 2011-12-29 | On-going
| Monitoring |  |  | 2424095 | Monitoring Team | Procurement
7 | Construction/Provision of Hospitals/Health Centres | 2700708
Ongoing Projects
| Progression of works at NIPI Clinic | 2700708 |  | 2700708 | Maigale Ventures | NIPI | 2001-10-25 | On-going
8 | Rehabilitation/Repairs-Housing | 5401416
Ongoing Projects
| Complete renovation of the Female Hostel | 5401406 |  | 3136875 | Haso Integrated Ltd | NIPI | 2011-12-01 | 0n-going
| Furnishing of Hostel |  |  | 2246917 | Golden Qualities Ltd | NIPI | 2011-11-18 | 0n-going
9 | Rehabilitation/Repairs-Library(Stocking of lib) | 3780991 |  | 2202375 | Adazhiyi Nig. Ltd | NIPI | 2011-12-14 | 2011-12-14 | Completed
Ongoing Projects
| Complete renovation of Institute Library, |  |  | 1572824 | Golden Qualities Ltd | NIPI | 2011-11-09 | 18/12/11 | Completed
| Procurement of Equipment & Stocking of Library |  |  | 2208110 | Adahiyi Nig Ltd | NIPI | 2011-12-11 | 2011-12-18 | Completed
10 | Research and Development | 47082338 |  |  |  | FMCT
Ongoing Projects
| Test and Measurements | 5432578 |  |  |  | FMCT
| Telecommunications Policy | 5432578 |  |  |  | FMCT
Implementation for National Rural Telephony Projects and Regional Programmes
| Nigeria-Niger-Algeria Terrestrial Cable (Feasibility Study & Consultancy) | 14486873 |  |  |  | FMCT
| Hosting of the National Portal and Management of Ministry’s network at Headquarters and IPPIS Platform | 9054296 |  | 7665581.02 | Cingular Information | IT | 2012-01-29 | 2012-02-08 | Completed
System Ltd
| Consultancy for the Rebranding project | 3621717
| Production/Airing of Radio and TV Programs and Commercial Jingles as well as documentaries on the rebranding campaign, news paper and magazine adverts and supplements | 5432577 | NCB | 2000000 | Sign 8 and Concepts Nig. Ltd | Re- Branding | 2011-12-29 | 2012-02-02 | Completed
| Collaboration with Organization (MDA,NGO,CSO)on various aspects of the rebranding campaign | 3621718
| One- Day Sensitization Programme on Rebranding |  | NCB | 1490000 | Marvelous M Press Nig. Ltd | Re- Branding | 2011-12-29 | 2012-01-20 | Completed
| Packaging of Interactive meeting on rebranding project |  | NCB | 1390000 | Mercy Trust Nig. Ltd | Re- Branding | 2011-12-29 | 32/1/12 | Completed
11 | Computer Software Acquisition | 7512590
Ongoing Projects
| Computerization of Accounting operations software creation Management, Procurement and Installation | 7512590 | NCB | 6434000 | Keez Global Nig. Ltd | DFA | 2011-12-15 | 23/12/11 | Completed
Summary:
| Total Capital Appropriated for 2011 Capital releases from 1st to 4th quarters 2011 | N337,157,567
N226,068,449
| Deficit | N11,089,118
146532626.07

## Agriculture & Rural Development
PROCUREMENT RECORDS
PROCUREMENT ENTITY(MDA)
MINISTRY |  |  | Agriculture and Rural Development
FINANCIAL YEAR
BASIC DATA | [5 empty] | CONTRACT AWARD | [5 empty] | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | ADVERTISEMENT DATE & MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | CONTRACTOR | DATE OF CONTRACT AWARD | DATE OF CONTRACT COMMENCEMENT | CONTRACT PERIOD | CONTRACT VALUE(N) | BUDGETRY PROVISION (N) | AMOUNT PAID AS AT | EXPECTED COMPLETION DATE | % OF COMPLETION AS AT 1ST MARCH 2012 | REMARKS
1 | Construction of eighteen (18) One-Stop-Shop Agro-Input Centres, Kwara | 2011-10-03 | MTB | NCB | 2011-11-14 | Pheobus Associates Ltd | 2011-12-01 | Immediately after award | 16Wks | 64328437.04 | 1153705150.75 | Advance Payment Processed | 2012-04-01 | 65%
2 | Construction of eighteen (18) One-Stop-Shop Agro-Input Centres, FCT | 2011-10-03 | MTB | NCB | 2011-11-14 | Alan Saunders Nig. Ltd | 2011-12-01 | Immediately after award | 16Wks | 64589769.18 |  | Advance Payment Processed | 2012-04-01 | 75%
3 | Construction of eighteen (18) One-Stop-Shop Agro-Input Centres, Niger | 2011-10-03 | MTB | NCB | 2011-11-14 | Inter Global Logistics Ltd | 2011-12-01 | Immediately after award | 16Wks | 62455808.63 |  | Advance Payment Processed | 2012-04-01 | 72%
4 | Construction of eighteen (18) One-Stop-Shop Agro-Input Centres, Akwa Ibom | 2011-10-03 | MTB | NCB | 2011-11-14 | African Sineri Nig. Ltd | 2011-12-01 | Immediately after award | 16Wks | 63593676.04 |  | Nil | 2012-04-01 | 68%
5 | Construction of eighteen (18) One-Stop-Shop Agro-Input Centres, Edo | 2011-10-03 | MTB | NCB | 2011-11-14 | Squirrel Multi Services Ltd | 2011-12-01 | Immediately after award | 16Wks | 64126331.03 |  | Advance Payment Processed | 2012-04-01 | 70%
6 | Construction of eighteen (18) One-Stop-Shop Agro-Input Centres, Rivers | 2011-10-03 | MTB | NCB | 2011-11-14 | OKD Consult Ltd | 2011-12-01 | Immediately after award | 16Wks | 64973657.18 |  | Nil | 2012-04-01 | 60%
7 | Construction of eighteen (18) One-Stop-Shop Agro-Input Centres, Enugu | 2011-10-03 | MTB | NCB | 2011-11-14 | Mafash System & Energy Inv. Ltd | 2011-12-01 | Immediately after award | 16Wks | 64529270.93 |  | Nil | 2012-04-01 | 55%
8 | Construction of eighteen (18) One-Stop-Shop Agro-Input Centres, Abia | 2011-10-03 | MTB | NCB | 2011-11-14 | E.F. Project Limited | 2011-12-01 | Immediately after award | 16Wks | 64208789.93 |  | Nil | 2012-04-01 | 50%
9 | Construction of eighteen (18) One-Stop-Shop Agro-Input Centres, Imo | 2011-10-03 | MTB | NCB | 2011-11-14 | Bloomsprings Ventures Nig. Ltd | 2011-12-01 | Immediately after award | 16Wks | 61906156.74 |  | Nil | 2012-04-01 | 65%
10 | Construction of eighteen (18) One-Stop-Shop Agro-Input Centres, Anambra | 2011-10-03 | MTB | NCB | 2011-11-14 | MM & IF Integrated Nig. Ltd | 2011-12-01 | Immediately after award | 16Wks | 65351066.93 |  | Nil | 2012-04-01 | 68%
11 | Construction of eighteen (18) One-Stop-Shop Agro-Input Centres, Ekiti | 2011-10-03 | MTB | NCB | 2011-11-14 | Banicol Nig. Ltd | 2011-12-01 | Immediately after award | 16Wks | 64379194.43 |  | Advance Payment Processed | 2012-04-01 | 70%
12 | Construction of eighteen (18) One-Stop-Shop Agro-Input Centres, Ondo | 2011-10-03 | MTB | NCB | 2011-11-14 | Muntaid Nig. Ltd | 2011-12-01 | Immediately after award | 16Wks | 64529270.93 |  | Advance Payment Processed | 2012-04-01 | 74%
13 | Construction of eighteen (18) One-Stop-Shop Agro-Input Centres, Oyo | 2011-10-03 | MTB | NCB | 2011-11-14 | Kellas Global Services Ltd | 2011-12-01 | Immediately after award | 16Wks | 64262638.43 |  | Advance Payment Processed | 2012-04-01 | 62%
14 | Construction of eighteen (18) One-Stop-Shop Agro-Input Centres, Osun | 2011-10-03 | MTB | NCB | 2011-11-14 | F & K Inv. Co. Ltd | 2011-12-01 | Immediately after award | 16Wks | 64919324.93 |  | Advance Payment Processed | 2012-04-01 | 65%
15 | Construction of eighteen (18) One-Stop-Shop Agro-Input Centres, Ogun | 2011-10-03 | MTB | NCB | 2011-11-14 | Jim Paul Ind. Nig. Ltd | 2011-12-01 | Immediately after award | 16Wks | 63589377.61 |  | Advance Payment Processed | 2012-04-01 | 50%
16 | Construction of eighteen (18) One-Stop-Shop Agro-Input Centres, Adamawa | 2011-10-03 | MTB | NCB | 2011-11-14 | Sweet Crown Int. Ltd | 2011-12-01 | Immediately after award | 16Wks | 64026814.43 |  | Nil | 2012-04-01 | 55%
17 | Construction of eighteen (18) One-Stop-Shop Agro-Input Centres, Zamfara | 2011-10-03 | MTB | NCB | 2011-11-14 | Dinamiks Inv. Nig. Ltd | 2011-12-01 | Immediately after award | 16Wks | 64775249.15 |  | Nil | 2012-04-01 | 60%
18 | Construction of eighteen (18) One-Stop-Shop Agro-Input Centres, Katsina | 2011-10-03 | MTB | NCB | 2011-11-14 | Dinamiks Inv. Nig. Ltd | 2011-12-01 | Immediately after award | 16Wks | 63160317.21 |  | Nil | 2012-04-01 | 68%
19 | Rehabilitation of the Nigerian Institute for Oceanography and Marine Research Jetty at Victoria Island, Lagos | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Abys Dynamics Ltd | 2011-12-05 | Immediately after award | 8WKS | 475320508.58 |  | Nil | 2012-02-05 | 50%
20 | Soil Fertility evaluation in Iseyin and Iddo LGAs of Oyo State | 2011-10-03 | MTB | NCB | 2011-10-17 | Messrs Bora Agro Nigeria | 2011-12-05 | Immediately after award | 8WKS | 21780.5 | 25397953 | Nil | 2012-02-05 | 100%
21 | Soil Fertility evaluation in Toto and Nasarawa LGAs of Nasarawa State | 2011-10-03 | MTB | NCB | 2011-10-17 | Messrs Hevborn Solutions Nigeria Ltd | 2011-12-05 | Immediately after award | 8WKS | 20530775 | 24697954 | Advance Payment Processed | 2012-02-05 | 100%
22 | Sourcing and Acquisition of all Analogue Data on Soil Existing in Nigeria since 1945 (Phase 1)/Data Capturing, Processing, Harmonization and Storage for easy Retrieval, Map Preparation and Printing | 2011-10-03 | MTB | NCB | 2011-10-17 | Watadat Agro-Terrain & Environ | 2011-12-05 | Immediately after award | 8WKS | 25281475.12 | 27200000 | Nil | 2012-02-05 | 100%
23 | Capacity Building of Federal Dept. of Agricultural Land Resources (FDALR) Staff on Project Management, Monitoring & Supervision | 2011-10-03 | MTB | NCB | 2011-10-17 | Messrs David Consulting Engineers Limited | 2011-12-05 | Immediately after award | 2WKS | 7285134.54 | 5500000 | Nil | 2012-02-05 | 100%
24 | Design of Control Measures to Reclaim Eroded Agricultural Lands in the South East and West (Enugu & Oyo) | 2011-10-03 | MTB | NCB | 2011-10-17 | Messrs Emifan Services Ltd | 2011-12-05 | Immediately after award | 8WKS | 13536707.17 | 17867500 | Nil | 2012-02-05 | 100%
25 | Procurement and Installation of Geographical Information System (GIS)/Remote Sensing (RS) Software | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Support System Ltd | 2011-12-23 | Immediately after award | 8WKS | 12295496.75 | 12700000 | Advance Payment Processed | 2012-02-22 | 100%
26 | Supply of Global Positioning System (GPS) and Training of staff on its application/usage | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Kahmad Nigeria Ltd | 2011-12-22 | Immediately after award | 12WKS | 8000000 |  | Advance Payment Processed | 2012-03-22 | On-going
27 | Upgrade and Installation of Power Inverter/Design and Establishment of an Agricultural Land Resources Website | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Snotec Facilities Engineering Ltd | 2011-12-23 | Immediately after award | 12WKS | 6785000 |  | Nil | 2012-03-22 | 75%
28 | Supply of Conservation Agriculture (CA) Equipment & Ameliorative material | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Winteck Nig. Ltd | 2011-12-23 | Immediately after award | 8wkS | 6888000 | 10000000 | Nil | 2012-02-23 | 100%
29 | Promotion of Principles and Practices of Conservation Agriculture Technology in Nasarawa, Taraba and Sokoto States | 2011-10-03 | MTB | NCB | 2011-10-17 | Messrs Alice Fullness Engineering Services | 2011-12-23 | Immediately after award | 12WKS | 42157131 |  | Advance Payment Processed | 2012-03-23 | 75%
30 | Promotion of Principles and Practices of Conservation Agriculture Technology in Akwa Ibom, Ondo and Imo States | 2011-10-03 | MTB | NCB | 2011-10-17 | Messrs Pedoquasphere Int’l Ltd | 2011-12-23 | Immediately after award | 12WKS | 39033555 |  | Nil | 2012-03-23 | 75%
31 | Capacity building on the Principles and Practices of Conservation Agriculture in Nigeria | 2011-10-03 | MTB | NCB | 2011-10-17 | Messrs Belma Integrated Resources Ltd | 2011-12-23 | Immediately after award | 12WKS | 7691660 |  | Nil | 2012-03-23 | 75%
32 | Construction of Model Fish-Trade Market at Yelwa – Yauri, Kebbi State under the Fish Trade Market Development Project of the Department | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Marydel Nig. Ltd |  | Immediately after award | 4WKS | 38368923 | 40000000 | Nil | 2012-03-23 | 75%
33 | Provision, supply and installation of Laboratory Equipment for the National Fisheries Laboratory, Victoria Island Office, Lagos | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Beachstone Ltd | 2011-12-05 | Immediately after award | 4WKS | 45448483.5 | 50000000 | Advance Payment Processed | 2012-01-05 | 100%
34 | Procurement, Deployment and Installation of FAO/ICCAT/FCWC Recommended Vessel Monitoring System (VMS) and Marine Surveillance Facilities at Calabar and Lagos States | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Millennium Global Technical & Engineering Services Ltd | 2011-12-05 | Immediately after award | 8WKS | 61908654 | 90000000 | Advance Payment Processed | 2012-02-05 | 60%
35 | Supply of Sprayers and Protective Wears | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Hemmor Ventures Nig. Ltd | 2011-12-19 | Immediately after award | 2WKS | 11394999 |  | Advance Payment Processed | 2012-01-03 | 100%
36 | Procurement of eighteen (18) Nos. of multi-purpose Grain Threshers for Cowpea, Soyabeans, Millet, Sorghum | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Springfield Agro Ltd | 2011-12-05 | Immediately after award | 3WKS | 17010000 | 17010000 | Nil | 2012-01-26 | 100%
37 | Procurement of 150 Nos. IITA-designed Rice Fan Threshers | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs El-Benak Nig. Ltd | 2011-12-05 | Immediately after award | 3WKS | 30712500 | 307125000 | Nil | 2012-01-26 | 100%
38 | Procurement of 250 units Aprotech super money maker treadle pumps for dry season farming | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs El-Benak Nig. Ltd | 2011-12-05 | Immediately after award | 3WKS | 10290000 | 10290000 | Nil | 2012-01-26 | 100%
39 | Production of 70,000 bundles (TME 419) and 87,960 bundles (TME 97) of certified and drought-resistant cassava | 2011-10-03 | MTB | NCB | 2011-11-14 | Root and Tuber Expansion Program (RTEP) | 2011-12-16 | Immediately after award | 8WKS | 44228800 | 44228800 | Nil | 2012-03-01 | 100%
40 | Production of (400,000) 18 Month Variety Cocoa Seedling of pest resistant stock for distribution to the 14 Cocoa Producing States | 2011-10-03 | MTB | NCB | 2011-11-14 | Tree Crop Unit, Ministry of Agriculture and Rural Development, Akure, Ondo State | 2011-12-20 | Immediately after award | 8WKS | 20000000 | 20000000 | Nil | 2012-02-20 | 100%
41 | Production of Certified Early, Extra Early and drought-resistant Rice Seeds (128.5 tons FARO 44) for the 2012 Planting Season | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Da-Allgreen Seeds Ltd | 2011-12-20 | Immediately after award | 8WKS | 30840000 | 30840000 | Nil | 2012-02-20 | 100%
42 | Production of Certified Early, Extra Early and drought-resistant Rice Seeds (128.5 tons FARO 52) for the 2012 Planting Season | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Premier Seeds Nig. Ltd | 2011-12-20 | Immediately after award | 8WKS | 30840000 | 30840000 | Nil | 2012-02-20 | 100%
43 | Production of Certified Early, Extra Early and drought-resistant Rice Seeds (128.5 tons FARO 55) for the 2012 Planting Season | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Savannah Seeds and Livestock Ltd | 2011-12-20 | Immediately after award | 8WKS | 30840000 | 30840000 | Nil | 2012-02-20 | 100%
44 | Construction of Office Complex, Classroom, Administrative Block at AMMOTRAC, Akure, Ondo State | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Ebentol Nig. Ltd | 2011-12-20 |  | 8WKS | 30460331.4 | 30000000 | Nil | 2012-02-20 | 75%
45 | Construction of Office Complex, Classroom, Administrative Block at AMMOTRAC, Misau, Bauchi State | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Bentars Nig. Ltd | 2011-12-20 | Immediately after award | 8WKS | 30893499.68 | 30000000 | Advance Payment Processed | 2012-02-20 | 68%
46 | Rehabilitation of Orakhuan-Emunekhua-Okhuesan Road (4Km) | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Funbay Mega Construction Ltd | 2011-12-19 | Immediately after award |  | 75008865.8 | 75346260 | Advance Payment Processed | 2012-03-01 | 75%
47 | Rehabilitation of Ede – Loogun Road, Osun State (2.34Km) | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Global Legend Integrated Concept Ltd | 2011-12-20 | Immediately after award |  | 40581310.53 |  | Nil | 2012-03-01 | 70%
48 | Rehabilitation of Idiori-Olukosi-Labanju-Orieran Road (3.5Km), Oyo State | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Layomadex Nig. Ltd | 2011-12-20 | Immediately after award |  | 59640000 | 65817175 | Nil | 2012-03-01 | 60%
49 | Rehabilitation of Ayigbiri-Osun-Iwonso-Magele Road (3.41Km) Oyo State | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Ras-Kol & Company Ltd | 2011-12-20 | Immediately after award | 8WKS | 58403238.82 | 60000000 | Advance Payment Processed | 2012-02-20 | 65%
50 | Rehabilitation of Idiaraba-Alorunu-Aeesade-Ilofe road (4.21Km), Imo State | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Barbeach Phina Nigeria Ltd | 2011-12-20 | Immediately after award | 8WKS | 76510769.74 | 79778395 | Nil | 2012-02-20 | 70%
51 | Supply of Environmental Chemicals | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Shafana Enterprise Ltd | 2011-12-20 | Immediately after award | 3Months | 18305000 |  | Nil | 2012-03-20 | 100%
52 | Supply of 130mt of Storage Chemicals (Coopex) | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Sabiti Nig. Ltd | 2011-12-16 | Immediately after award | 3Months | 97500000 | 300000000 | Nil | 2012-03-16 | 100%
53 | Supply of 250 Cartons of Storage Chemicals (Phostoxin) | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Eden Plus Spectrum Nig. Ltd | 2011-12-16 | Immediately after award | 3Months | 22395000 |  | Advance Payment Processed | 2012-03-16 | 100%
54 | Supply of 10 nos. Phosphine Meters | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Murola Investment Nig. Ltd | 2011-12-16 | Immediately after award | 3WKS | 7500000 |  | Nil | 2012-01-07 | 100%
55 | Rehabilitation of 25,000mt Silo Complex at Ezillo, Ebonyi State | 2011-10-03 | MTB | NCB | 2011-11-14 | OKD Construction Limited | 2011-12-16 | Immediately after award | 3Mnths | 241072818 | 400000000 | Nil | 2012-03-16 | 65%
56 | Construction of a 200-Room Students’ Hostel at the Federal College of Agricultural Land Resources Technology Permanent Site, Oforola, Imo State | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Goodworth International Ltd | 2011-12-16 | Immediately after award | 3WKS | 85550000 |  | Nil | 2012-01-07 | 100%
57 | Construction of Spray Race Facility, Holding Yard/ Inspection Gallery with a Crush at Sheda, Abuja | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Sumeng Nig Ltd | 2011-12-16 | Immediately after award | 3WKS | 22007315 |  | Nil | 2012-01-07 | 100%
58 | Construction of 20 units of Stables in Animal Quarantine Station Sheda, Abuja | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Ateda Ventures Ltd | 2011-12-16 | Immediately after award | 3WKS | 33302332.14 |  | Nil | 2012-01-07 | 100%
59 | Supply, Installation and Networking of Equipment in Databank and the Conference Centre | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs. Datakumms Ltd | 2011-12-16 | Immediately after award | 3WKS | 36374783.36 |  | Nil | 2012-01-07 | 100%
60 | Consultancy for the development of Software and Migration Platform for the harmonization and validation of Farmers Database in Nigeria | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Knowledge Based Services Ltd | 2011-12-16 | Immediately after award |  | 23460014.6 |  | Nil |  | 100%
61 | Rehabilitation of Maiturare – Wuro – Dole Road (3km) in Adamawa | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Blackstone Construction Ltd | 2011-12-16 | Immediately after award | 12WKS | 52640089.9 |  | Advance Payment Processed | 2012-03-16 | 75%
62 | Rehabilitation of Pulka – Ngoshe Kughum Road (4.52km) in Gwoza LGA of Borno State | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs G & G Construction Company Ltd | 2011-12-19 | Immediately after award | 8WKS | 83766900 |  | Advance Payment Processed | 2012-02-19 | 60%
63 | Rehabilitation of Enclave Project Road (3km) in Oredo LGA of Edo State | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Ojking Company Ltd | 2011-12-19 | Immediately after award | 8Wks | 55138636.74 |  | Advance Payment Processed | 2012-02-19 | 65%
64 | Rehabilitation of Udi Etiti – Amokwe Road (3km) in Udi LGA of Enugu State | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Jalingo Ltd | 2011-12-19 | Immediately after award | 8WKS | 57157735.53 |  | Advance Payment Processed | 2012-02-19 | 80%
65 | Rehabilitation of Machika – Dungu Road (3km) in Kebbi State | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Dinal Global Ventures Ltd | 2011-12-19 | Immediately after award | 8WKS | 58546158.93 |  | Nil | 2012-02-19 | 60%
66 | Rehabilitation of Mustapha A. – Dangi Road (3km) in Niger State | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Tinka Point Ltd | 2011-12-19 | Immediately after award |  | 49118055.26 |  | Nil | 2012-02-19 | 60%
67 | Rehabilitation of Ipokia Muan – Ita Egbe – Erodo – Iweke Road (2.5km) in Yewa South LGA of Ogun State | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Motef Engineering Ltd | 2011-12-19 | Immediately after award | 8WKS | 66427180.11 |  | Advance Payment Processed | 2012-02-19 | 70%
68 | Rehabilitation of Iyaoje – Byiro – Iyelu – Egbede Road (7.5km) in Surulere LGA of Oyo State | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Mubarak Real Solid Ltd | 2011-12-19 | Immediately after award | 8WKS | 74541677.37 |  | Advance Payment Processed | 2012-02-19 | 70%
69 | Rehabilitation of Olorunda – Omidoyin Road (3km) in Oyo State | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Decency Associate Ltd | 2011-12-19 | Immediately after award | 8WKS | 57988637.47 |  | Advance Payment Processed | 2012-03-19 | 70%
70 | Rehabilitation of 0.5km Kaliari Road (Kauda – Polo Road) in Borno State | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Barmar Global Resources Nig. Ltd | 2011-12-19 | Immediately after award | 8WKS | 12959147.57 |  | Advance Payment Processed | 2012-03-19 | 60%
71 | Rehabilitation of Igumale – Ulayi – Jigban Road ( 2.2 km) in Ado LGA of Benue State | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Rhino Maritime Services | 2011-12-19 | Immediately after award | 12WKS | 35054538.75 |  | Advance Payment Processed | 2012-03-19 | 75%
72 | Rehabilitation of Oshigbudu- Obagaji -Okokolo Road (2.24km) in Agatu LGA of Benue State | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Ell Services Nig Ltd | 2011-12-22 | Immediately after award | 8Wks | 35768114.24 |  | Nil | 2012-03-22 | 70%
73 | Rehabilitation of Ugbokpo Edikwu Opaha Road in Apa L.G.A. of Benue State (2.71 km) | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs I. B. Marvin International Ltd | 2011-12-22 | Immediately after award | 12WKS | 35655685.37 |  | Advance Payment Processed |  | 30%
74 | Rehabilitation of Adum East – Ohuma - Ojuo Road (2.21km) in Obi LGA of Benue State | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Aswalit Ventures Ltd | 2011-12-22 | Immediately after award | 12WKS | 32261685.75 |  | Nil | 2012-03-22 | 75%
75 | Rehabilitation of Oju – Ebenta – Uwokwu Road (2.5km) in Oju LGA of Benue State | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Mertai Multi Services Nig Ltd | 2011-12-22 | Immediately after award | 12Wks | 35368696.13 |  | Nil | 2012-03-22 | 75%
76 | Rehabilitation of Ukwo-Aho Owukpa Road (2.2 Km) in Ogbadigbo LGA of Benue State Road | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Ismasol Construction Ltd | 2011-12-22 | Immediately after award | 12WKS | 33509178.28 |  | Advance Payment Processed | 2012-03-22 | 70%
77 | Rehabilitation of Okpudu-Idiri Ikomija Road (3.96 km) in Okpokwu LGA of Benue State | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Alma Essence Ltd | 2011-12-22 | Immediately after award | 12WKS | 30735495 |  | Advance Payment Processed | 2012-03-22 | 70%
78 | Rehabilitation of Ochobo - Agadagba - Onyagede Road (2.04 km) in Ohimini LGA of Benue State | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Rafjaf Nig. Ltd | 2011-12-22 | Immediately after award | 8WKS | 30209395 |  | Advance Payment Processed | 2012-02-22 | 90%
79 | Rehabilitation of Adoka - Umogidi - Opaha Road (2.52km) in Otukpo LGA of Benue State | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Embay International Biz Ltd | 2011-12-22 | Immediately after award | 12WKs | 34635811.48 |  | Nil | 2012-03-22 | 65%
80 | Rehabilitation of (3km) Kebbe Junction – Margari Primary School Gaddace Road in kebbe LGA of Sokoto State | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Wellworth Ltd | 2011-12-22 | Immediately after award | 12WKS | 74051479.68 |  | Advance Payment Processed | 2012-03-22 | 75%
81 | Rehabilitation of Orita - Odanbon – Oniyan-Ilogbo-Itemu Road Extension (5km) Surulere, Oyo State | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Status Global Services Limited | 2011-12-23 | Immediately after award | 12WKS | 72336450.3 |  | Nil | 2012-03-23 | 75%
82 | Construction of Livestock Service Centre at Damau Grazing Reserve, Kaduna State | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Faida Eng. Services Ltd | 2011-12-22 | Immediately after award | 3Months | 23313937.91 | 156356291 | Nil | 2012-03-22 | 85%
83 | Construction of Livestock Service Centre at Wasinmi Grazing Reserve, Oyo State | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs D.B.K. Ltd | 2011-12-16 | Immediately after award | 3Months | 19527207.58 | 150000000 | Nil | 2012-03-16 | 85%
84 | Construction of Livestock Resting Point at Babbar Ruga, Niger State | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Black Gold | 2011-12-16 | Immediately after award | 3Months | 42823182.65 | 126316715 | Advance Payment Processed | 2012-03-16 | 90%
85 | Construction of Livestock Resting Point at Nvuma, Borno State | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs A. A. Suleiman & Sons Ltd | 2011-12-16 | Immediately after award | 3Months | 40319098.19 |  | Nil | 2012-03-16
86 | Rehabilitation and construction of additional facilities at the Cattle Breeding and Multiplication Centre, Oshiri, Ebonyi State | 2011-10-03 | MTB | NCB | 2011-11-14 | Messrs Vickos Ventures Nig. Ltd | 2011-12-16 | Immediately after award | 8WKS | 26164137.5 | N30,000,000.00 | Advance Payment Processed | 2012-02-16 | 85%
87 | Consultancy for the Design and implementation of Cooperative Advocacy, Publicity and Promotion, Cooperative Training Needs Analysis (TNA) and the Training Of Trainers (TOT), the development of appropriate training modules for different groups production line in Nigeria | Federal Tenders Journal,ThisDAY & Daily Trust News Paper of 26/10/2011 | MTB | NCB | 2011-11-15 | Messrs Agricultural Business Concepts Ltd | 2011-12-22 | Immediately after award | 3WKS | 14090450 |  | Nil | Completed | 100%
88 | Consultancy for the design, preparation and supervision of the Cooperative census, recertification and CODAS information system | Federal Tenders Journal,ThisDAY & Daily Trust News Paper of 26/10/2011 | MTB | NCB | 2011-11-15 | Messrs Information Explosion Systems Ltd | 2011-12-16 | Immediately after award | 3Months | 91120041.6 |  | Nil | 2012-03-16 | On-going
89 | Completion of a block of 8 Nos. 3 bedrooms flats at the National Cooperative Development Centre, NCDC, Sheda | 2011-10-03 | MTB | NCB |  | Messrs E. F Projects Ltd | 2011-12-16 | Immediately after award | 8Wks | 18645400.46 |  | Nil | 2012-03-16 | 90%
90 | Completion of the internal roads network, culverts and drainages at the National Cooperative Development Centre, NCDC, Sheda | 2011-10-03 | MTB | NCB |  | Messrs Aziz Hazan Nig. Ltd | 2011-12-20 | Immediately after award | 8Wks | 26927925.94 |  | Nil | 2012-02-20 | 90%
91 | Completion of the auditorium complex at the Federal Cooperative College, Oji-River | 2011-10-03 | MTB | NCB |  | Messrs Goldstix International Ltd | 2011-12-20 | Immediately after award | 8WKS | 15152775.69 |  | Advance Payment Processed | 2012-02-20 | 90%
92 | Provision of technology platform for the acquisition of fertilizers and seeds by farmers nationwide under the Growth Enhancement Support scheme | Federal Tenders Journal,ThisDAY & Daily Trust News Paper of 26/10/2011 | MTB | NCB | 2011-11-15 | Messrs Cellulant Nigeria Limited | 2011-12-19 | Immediately after award | 3Years | 1327199984 |  | Nil | 2014-12-19 | On-going
5812534903.36

## FMC Bida
FEDERAL MEDICAL CENTRE, BIDA
PROCUREMENT RECORDS
FEDERAL MINISTRY OF HEALTH
2011
BASIC DATA | [5 empty] | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
ADVERTISEMENT DATE AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | CONTRACTOR | DATE OF CONRACT AWARD | DATE OF CONTRACT COMMENCEMENT | CONTRACT PERIOD | CONTRACT Value | BUDGETARY PROVISION | AMOUNT PAID AS AT 31/12/2011 | EXPECTED COMPLETION DATE | % OF COMPLETION AS AT 31/12/2011 | REMARKS
31/05/10, Daily Trust & Punch | PTB | NCB | 2010-12-07 | [5 empty] | 17640357 | 0 |  | 0%
31/05/10, Daily Trust & Punch | PTB | NCB | 2010-12-07 | Cemya Medicals Nig. Ltd, ABJ Consolidated Nig Ltd. | 2010-05-11 | 2010-05-11 | 2010-2011 | 10970000 | 10529609 | 10529609 | 2011 | 100%
31/05/10, Daily Trust & Punch | PTB | NCB | 2010-12-07 | Mega Care International Services | 2010-05-11 |  |  | 2450000 | 10529609 | 0 |  | 0%
31/05/10, Daily Trust & Punch | PTB | NCB | 2010-12-07 | Hushill Nig Ltd | 2010-05-11 | 2010-05-11 | 2010-2011 | 14987782.8 | 7019739 | 7019739 | 2011 | 100%
31/05/10, Daily Trust & Punch | PTB | NCB | 2010-12-07 | [5 empty] | 14039478 | 0 | 2011 | 0%
31/05/10, Daily Trust & Punch | PTB | NCB | 2010-12-07 | Ambek Care Resourses Ltd. | 2010-05-11 | 2010-05-11 | 2010-2011 | 38000000 | 17059217 | 17059217 | 2011 | 100%
31/05/10, Daily Trust & Punch | PTB | NCB | 2010-12-07 | Osla System Nig. Ltd, Ambek Care Resourses Ltd. | 2010-05-11 | 2010-05-11 | 2010-2011 | 50000000 | 17549349 | 17549349 | 2011 | 100%
09/05/2009, Daily Trust & Punch | PTB | NCB | 30/06/2009 | Edusoko & Sons Nig. Ltd | 15/07/2009 | 15/07/2009 | 2010-2011 | 164,623,340,21 | 57217130 | 44629881.57 | 2012 | 78%
28/07/10, Daily Trust & Punch | PTB | NCB | 2010-12-07 | Jacinth Nig. Ltd | 2010-05-11 | 2010-05-11 | 2010-2011 | 63633887.15 | 21059217 | 21059217 | 2012 | 100%
31/05/10, Daily Trust & Punch | PTB | NCB | 2010-12-07 | [5 empty] | 7019739 | 0 |  | 0%
31/05/10, Daily Trust & Punch | PTB | NCB | 2010-12-07 | Setikdesigns Nig Ltd | 2010-05-11 | 2010-05-11 | 2010-2011 | 10530600 | 10529609 | 10529609 | 2011 | 100%
[8 empty] | 190572269.95 | 190193053 | 128376621.57

## Namide Azikiwe UTH
NNAMDI AZIKIWE UNIVERSITY TEACHING HOSPITAL
P M B 5025 NNEWI ANAMBRA STATE NIGERIA
PROCUREMENT RECORDS
PROCUREMENT ENTITY (MDA) |  | NNAMDI AZIKIWE UNIVERSITY TEACHING HOSPITAL
MINISTRY: |  | HEALTH
FINANCIAL YEAR |  | 2011
| BASIC DATA | [5 empty] | CONTRACT AWARD | [5 empty] | CONTRACT IMPLEMENTATION
S/N | Contract description |  | Advertisement Date And media | Approval Threshold | Procurement method | Bid Opening date | Contractor | Date of Contract Award | Date of contract Commencement | Contract Period | Contract Value (N) | Budgetary Provision (N) | Amount Paid as at | Expected Completion Period | % of Completion as at | Remarks
1 | Construction of Stores Building at NAUTH Permanent Site |  | *Federal Tender | Ministerial | Competitive | 2008-05-26 | Optimum Works Ltd | 2008-08-19 | 2009-06-18 | 24 weeks | 46512081 | 21059217 | 10276702.17 | 31/12/2012
|  |  | Journal 28/4/08 | Tender | Bidding | [7 empty] | As at 31/12/11 |  | 8% | Inadequate Budgetary Provision/ Late Release of Funds
|  |  | *Vanguard newspaper | Board | [10 empty] | As at 31/12/2011
2008-04-28
2 | Construction of Operating |  | *Federal Tender | Hospital | Competitive | 2009-03-19 | First Spil Investment Ltd | 2009-06-09 | 2009-04-18 | 24 weeks | 158497789.38 | 21059217 | 36000000 | 2012-12-31
| Theatre at NAUTH |  | Journal 26/1/09 | Tender | Bidding | [7 empty] | As at 31/12/11 |  | 20% | Inadequate Budgetary Provision/ Late Release of Funds
| Permanent Site |  | *Vanguard newspaper | Board | [10 empty] | As at 31/12/2011
2009-01-26
3 | Construction of Radiology Dept at NAUTH |  | *Federal Tender | Hospital | Competitive | 2009-03-19 | Churchgate Product Ltd | 2009-06-09 | 2009-04-18 | 32 weeks | 145037269.65 | 14039478 | 26128694 | 2012-12-31
| Permanent Site |  | Journal 26/1/09 | Tender | Bidding | [7 empty] | As at 31/12/11 |  | 20% | Inadequate Budgetary Provision/ Late Release of Funds
|  |  | *Vanguard newspaper | Board | [10 empty] | As at 31/12/2011
2009-01-26
4 | Construction of Specialty Clinic at NAUTH Permanent Site |  | *Federal Tender | Hospital | Competitive | 2009-03-19 | Jude Engr Nig. Ltd | 2009-06-09 | 2009-04-18 | 24 weeks | 203380485 | 20078957 | 75017214.81 | 2012-12-31
|  |  | Journal 26/1/09 | Tender | Bidding | [7 empty] | As at 31/12/11 |  | 80% | Inadequate Budgetary Provision/ Late Release of Funds
|  |  | *Vanguard newspaper | Board | [10 empty] | As at 31/12/2011
2009-01-26
5 | Construction of Accident and Emergency Block at NAUTH Permanent Site |  | *Federal Tender | Hospital | Competitive | 2009-03-19 | Zontal-Fobis (W.A) Ltd | 2009-06-09 | 2009-04-18 | 24 weeks | 99035316.45 | 14039478 | 12000000 | 2012-12-31
|  |  | Journal 26/1/09 | Tender | Bidding | [7 empty] | As at 31/12/11 |  | 18% | Inadequate Budgetary Provision/ Late Release of Funds
|  |  | *Vanguard newspaper | Board | [10 empty] | As at 31/12/2011
2009-01-26
6 | Construction of Internal Access Road Phase 1 at NAUTH Permanent Site |  | *Federal Tender | Hospital | Competitive | 2009-03-19 | Lonac International Ltd | 2009-06-09 | 2009-04-18 | 4 weeks | 27885396 |  | 12488195.05 | 2012-12-31
|  |  | Journal 26/1/09 | Tender | Bidding | [7 empty] | As at 31/12/11 |  | 95% | Inadequate Budgetary Provision/ Late Release of Funds
|  |  | *Vanguard newspaper | Board | [10 empty] | As at 31/12/2011
2009-01-26
7 | Construction of Fence Phase 1 |  | *Federal Tender | Hospital | Competitive | 2010-04-20 | Croyden Resoures Nig. Ltd | 2010-05-20 | 2010-07-05 | 26 weeks | 191458370.3 | 40138174 | 27841723.2 | 2012-12-31
| at NAUTH Permanent Site |  | Journal 22/2/10 | Tender | Bidding | [7 empty] | As at 31/12/11 |  | 30% | Inadequate Budgetary Provision/ Late Release of Funds
|  |  | *Vanguard/ Champion newspaper | Board | [10 empty] | As at 31/12/2011
2010-02-22
8 | Construction of G.O.P.D |  | *Federal Tender | Hospital | Competitive | 2010-04-20 | A.A. Calon Nig. Ltd | 2010-05-20 | 2010-07-24 | 30 weeks | 250000000 | 25098696 | 28000000 | 2012-12-31
| at NAUTH Permanent Site |  | Journal 22/2/10 | Tender | Bidding | [7 empty] | As at 31/12/11 |  | 12% | Inadequate Budgetary Provision/ Late Release of Funds
|  |  | *Vanguard/ Champion newspaper | Board
|  |  | 2010-02-22 | [11 empty] | As at 31/12/2011
9 | Construction of Renal Building at NAUTH Permanent Site |  | *Federal Tender | Hospital | Competitive | 2010-04-20 | Exotic Homes Ltd | 2010-05-20 | 2010-07-05 | 26 weeks | 120277741.5 | 28078957 | 32660942.67 | 2012-12-31
|  |  | Journal 22/2/10 | Tender | Bidding | [7 empty] | As at 31/12/11 |  | 20% | Inadequate Budgetary Provision/ Late Release of Funds
|  |  | *Vanguard/ Champion newspaper | Board
2010-02-22
As at 31/12/2011
10 | Construction of Obstetric Ward at NAUTH Permanent Site |  | *Federal Tender | Hospital | Competitive | 2010-04-20 | Tekno Concepts Construction Ltd | 2010-05-19 | 2010-07-05 | 16 weeks | 250000000 | 46157913 | 62870662 | 2012-12-31
|  |  | Journal 22/2/10 | Tender | Bidding | [7 empty] | As at 31/12/11 |  | 27% | Inadequate Budgetary Provision/ Late Release of Funds
|  |  | *Vanguard/ Champion newspaper | Board
2010-02-22
As at 31/12/2011
11.. | Construction of Male Surgical Ward at NAUTH Permanent Site |  | *Federal Tender | Hospital | Competitive | 2010-04-20 | Arcon Global Engr. Ltd | 2010-05-20 | 2010-07-05 | 28 weeks | 232077085 | 42118435 | 23000000 | 2012-12-31
|  |  | Journal 22/2/10 | Tender | Bidding | [7 empty] | As at 31/12/11 |  | 10% | Inadequate Budgetary Provision/ Late Release of Funds
|  |  | *Vanguard/ Champion newspaper | Board
2010-02-22
As at 31/12/2011
12 | Construction of Administration Block at NAUTH Permanent Site |  | *Vanguard/ Daily Champion newspaper | Hospital | Competitive | 2010-07-19 | Egraw Investment Nig. Ltd | 2010-07-26 | 2010-08-09 | 16 weeks | 228516592.5 | 63177652 | 63247827.22 | 2012-12-31
|  |  | 2010-06-08 | Tender | Bidding | [7 empty] | As at 31/12/11 |  | 20% | Inadequate Budgetary Provision/ Late Release of Funds
Board
As at 31/12/2011
1952678126.78

## FMC Gusau
PROCURING ENTITY(MDA) |  |  | FEDERAL MEDICAL CENTRE GUSAU
MINISTRY |  |  | HEALTH
FINANCIAL YEAR |  |  | 2011
PERFORMANCE/RESULTS-BASED 2012 FMOH OPERATIONAL WORKPLAN
CODE | PROGRAM/ |  |  | 2012 |  | NSHDP | NSHDP | ACTIVITIES |  | Disbursement Categories |  |  |  | Performance results
| PROJECT DESCRIPTION | CLASSIFICATION CODE | INITIATIVE/PROGRAMME/PROJECT | PROPOSAL/ APPROPRATION # | SOURCE OF FUNDING | Priority Area/Goal | Strategic objective (s) | REFERENCE TO FEDERAL SHDP | STATUS OF PROJECT: ON-GOING/NEW | Goods | Civil Works | Consultancy Services | Non-consulting Services (e.g.Programme, Training, logistics etc) | INPUTS | OUTPUTS | OUTCOMES | RESULTS MATRIX/INDICATOR | QUARTER | REMARKS
2 | 3 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
|  | 23010122 | Construction of Amenity Ward | 51262567.01 | Annual Budget | To Revitalize intergrated service delivery towards a quality, equitable and sustainable access to Health Care. | To improve the quality of Health Care Services. | Universal access to Essential Health Care Package Programme. | On-going |  | 40121666.48 | 11140902.53 |  | Contract No: FMC/TB/006/10 awarded to SOZEAL INT. NIG. LTD. | A completed Ameinity Ward with capacity for admission of 32 Nos Patient. | Reduction in risk of infection spread. | To strengthen specific communicable and non communicable disease control Programmes by 80% | Q1
|  | 23010122 | Construction of Pharmacy Department | 24250938.17 | Annual Budget | To Revitalize intergrated service delivery towards a quality, equitable and sustainable access to Health Care. | To improve the quality of Health Care Services. | Programme to Increase Access to Health Care Services for the Poor and Hard to Reach. | On-going |  | 18980275.74 | 5270662.43 |  | Contract No: FMC/TB/003/10 awarded to SIR ABDUL & ASSOCIATES LTD. | A completed Pharmacy Building that conform with Standard of Pharmaceutical Council of Nigeria. | Good, qualitative and other related Pharmaceutical services. | To ensure availability of Drugs and equipment at all levels. | Q1-Q2
|  | 23010122 | Construction of Gynae Ward | 10702721.31 | Annual Budget | To Revitalize intergrated service delivery towards a quality, equitable and sustainable access to Health Care. | To improve the quality of Health Care Services. | Universal access to Essential Health Care Package Programme. | On-going |  | 8377484.17 | 2325237.14 |  | Contract No: FMC/TB/004/10 awarded to ARID BUILDERS NIG. LTD. | A completed well ventileted Gynae Ward with capacity for admission of 36 patient. | Reduction in Maternal mortality rate. | To strengthen specific communicable and non communicable disease control Programmes. | Q1
|  | 23010122 | Construction of Drainages, works- ways, parkings and landscaping | 211067711.73 | Annual Budget | To Revitalize intergrated service delivery towards a quality, equitable and sustainable access to Health Care. | To increase access to Health Care Service. | Universal access to Essential Health Care Package Programme. | On-going |  | 203108613.01 | 7959098.72 |  | Contract No: FMC/TB/009/10 awarded to CALF PRESENTATION NIG. LTD. | Competed internal Drainages System, Walkways, Parkings and Landscaping. | Free out flow of sewage and enhancing the therapeutic performance of the Hospital building. |  | Q2-Q4
|  | 23020101 | Equipping of male and female surgical ward | 10002012 | Annual Budget | To Revitalize intergrated service delivery towards a quality, equitable and sustainable access to Health Care. | To provide an essential package of Care. | Universal access to Essential Health Care Package Programme. | On-going | 10002012 |  |  |  | To be awarded after budget approval. | Equipments for Surgical Ward i.e Hot air oven, wheel chairs, admission beds, Autoclaves instruments Oxygen concentrators etc. | Reduction of morbidity and mortality. | To strengthen specific communicable and non communicable disease control Programmes by 60% | Q1-Q3
|  | 23010122 | Equipping of Radiology dept. | 25556052.78 | Annual Budget | To Revitalize intergrated service delivery towards a quality, equitable and sustainable access to Health Care. | To provide an essential package of Care. | Programme to Increase Access to Health Care Services for the Poor and Hard to Reach. | On-going | 25556052.78 |  |  |  | To be awarded after budget approval. | Newly Procured Radiology equipment i.e floroscopy, CT scan and MRI machines etc. | Reduction in the number of unwanted operations, and improve in patients care | To improve geographical equity and access to Health Services to about 50% of Population within 30 minute walk or 5 kilometre distance. | Q1-Q3
[10 empty] | 35558064.78 | 270588039.4 | 26695900.82
332842005
PROCUREMENT JANUARY - MARCH, 2012
S/N | CONTRACT DESCRIPTION | ADVERTISEMENT DATE AND MEDIA | APPROVAL THREHOLD | PROCUREMENT METHOD | BID OPENING DATE | CONTRACTOR | DATE OF CONTRACT AWARD | DATE OF CONTRACT COMMENCEMENT | CONTRACT PERIOD | CONTRACT VALUE (N) | BUDGETARY PROVISION (N) | AMOUNT PAID AS AT 31/3/2012 | EXPECTED COMPLETION DATE | % OF COMPLETION AS AT 31/3/2012 | REMARKS
1 | Furnishing & Equipping of GOPD | Daily Trust & Daily Sun of 18/08/2011 | N50M | NCB | 2011-10-10 | Desert Med. Nig. Ltd | 2011-12-19 | 2011-12-19 | 4wks | 20677000 | 21059217 | 17575450 | 2012-01-16 | 100%
2 | Equipping of Pre- Natal Ward | Daily Trust & Daily Sun of 18/08/2011 | N50M | NCB | 2011-10-10 | Hosquip Nig Ltd | 2011-12-19 | 2011-12-19 | 4wks | 16442479 | 14039478 | 13976107.15 | 2012-01-16 | 100%
3 | Equipping of Post- Natal Wartd | Daily Trust & Daily Sun of 18/08/2011 | N50M | NCB | 2011-10-10 | Hosquip Nig Ltd | 2011-12-19 | 2011-12-19 | 4wks | 16742739 | 14039478 | 14231328.15 | 2012-01-16 | 100%
4 | Equipping of Neo-Natal Ward | Daily Trust & Daily Sun of 18/08/2011 | N50M | NCB | 2011-10-10 | Hosquip Nig Ltd | 2011-12-19 | 2011-12-19 | 4wks | 15640818 | 21059217 | 13294695.03 | 2012-01-16 | 100%
5 | Equipping of Male & Female Medical Wards | Daily Trust & Daily Sun of 18/08/2011 | N50M | NCB | 2011-10-10 | Unique Udok Nig Ltd | 2011-12-19 | 2011-12-19 | 4wks | 19527556 | 21059217 | 16598422.06 | 2012-01-16 | 100%
6 | Equipping of O & G Clinic | Daily Trust & Daily Sun of 18/08/2011 | N50M | NCB | 2011-10-10 | Bijo Surgical & Scientist | 2011-12-19 | 2011-12-19 | 4wks | 9768400 | 14039478 | 9768400 | 2012-01-16 | 100%
7 | Furnishing & Equipping of A& E | Daily Trust & Daily Sun of 18/08/2011 | N50M | NCB | 2011-10-10 | Hosquip Nig Ltd | 2011-12-19 | 2011-12-19 | 4wks | 19510150 | 21059217 | 16583627.05 | 2012-01-16 | 100%
8 | Furnishing of Laboratory Department | Daily Trust & Daily Sun of 18/08/2011 | N50M | NCB | 2011-10-10 | Toitel Ltd | 2011-12-19 | 2011-12-19 | 4wks | 13730427 | 25800670 | 11670862.95 | 2012-01-16 | 100%
9 | Supply of Radiology equipment | Daily Trust & Daily Sun of 18/08/2011 | N50M | NCB | 2011-10-10 | Polar Chemical & | 2011-12-28 | 2011-12-28 | 4wks | 11607386 | 85296087 | 9866278 | 2012-01-28 | 100%
10 | Equipping of Radiology Department | Daily Trust & Daily Sun of 18/08/2011 | N50M | NCB | 2011-10-10 | Polar Chemical & | 2012-03-19 | 2012-03-19 | 4wks | 65759680 |  | 65759680 | 2012-04-19 | 100%

## OHCSF
OFFICE OF THE HEAD OF THE CIVIL SERVICE OF THE FEDERATION
2011 PROCUREMENT RECORDS – CAPITAL
S/N | NAME OF CONTRACTOR | DATE OF AWARD | NATURE OF CONTRACT | VALUE OF CONTRACT | RECORD OF PROCUREMENT PROCEEDINGS
1 | M/S Geo tech. Technologies Ltd. | 2011-02-25 | Replacement and Upgrading of Intercom Equipment | ₦21,467,606.97 | MTB 1 APPROVAL
Vide file ref. No. HCSF/PSO/SWD/01/I
2 | National Identity Management Commission (NIMC) | 2011-06-21 | Installation of Card Based Access Control Gates System within the Federal Secretariat Complexes, Abuja | ₦353,246,706.00 | BPP No Objection ref. No. BPP/S.1/11/SP/Vol. II/102 dated June 17, 2011 and MTB 3 approval vide file no. NIMC/OHCSF/B10/I/005
3 | Federal Government Printing Press | 2011-06-21 | Printing of Federal List, Reference Books and Circulars | ₦ 47,300,000.00 | MTB 3 APPROVAL
Vide file ref. No. HCSF/SW/PD/13/III
4 | M/S De Product Technology Ltd | 2011-11-04 | Servicing & Maintenance of Photocopying Machines in the Office of the Head of the Civil Service of the Federation | ₦9,028,650.00 | MTB 4 APPROVAL Vide file ref. No. HCSF/CSO/PD/455.S.
5 | M/S Innosbee Communication Ltd | 2011-11-14 | Design & Upgrading of Website Content with animation, e-mail facilities | ₦9,130,000.00 | MTB 4 APPROVAL Vide file ref. No. HCSF/PRS/ICT/PRO/50/S.02
6 | M/S Five fingers Global Res. Ltd | 2011-11-14 | Supply & Installation of 30 set of Notebook HP Dell Core 2 | ₦9, 450,000.00 | MTB 4 APPROVAL Vide file ref. No. HCSF/PRS/ICT/PROC/56/S.04
7 | M/S Clet and Cletta nig. Ltd | 2011-11-14 | Supply &Installation of 300 packets of 1.5KVA mercury/Bluegate | ₦9,757,500.00 | MTB 4 APPROVAL Vide file ref. No. HCSF/PRS/ICT/PROC/56/S.05
8 | M/S Kleen Gee Concept Ltd | 2011-11-14 | Supply &Installation of 25 No. of HP 4015 printers | ₦8, 730,000.00 | MTB 4 APPROVAL Vide file ref. No. HCSF/PRS/ICT/PROC/56/S.06
9 | M/S Christec Computers Ltd | 2011-11-14 | Supply & Installation of 800 Eset Nod 32 Antivirus | ₦8,190,000.00 | MTB 4 APPROVAL Vide file ref. No. HCSF/PRS/ICT/PROC/56/S.07
10 | M/S Blessing Global | 2011-11-14 | Furnishing of 80 seats capacity ICT centre. | ₦9,945,200.00 | MTB 4 APPROVAL Vide file ref. No. HCSF/PRS/ICT/PROC/56/S.12
Services Nig. Ltd
11 | M/S Final Solutions Nig. Ltd | 2011-11-14 | Supply & Installation of Multi-media Equipment | ₦8,504,000.00 | MTB 4 APPROVAL Vide file ref. No. HCSF/PRS/ICT/PROC/56/S.13
12 | M/S Tolinz Global Resources Ltd | 2011-11-14 | Construction of 1 No. Block of Training Rooms, FTC, Lagos | ₦65,510,760.00 | MTB 5 APPROVAL Vide/file/ref. No. HCSF/CSO/PD/456/S.12184
13 | M/S Mo-osi Global Services Ltd | 2011-11-14 | Construction of 1 No. Block of Student Hostel, FTC, Lagos | ₦117, 378,421.65 | MTB 5 APPROVAL Vide file ref. No. HCSF/CSO/PD/456/S.13
14 | M/S Omonice Nig. Ltd | 2011-11-14 | Construction of 1 No. Proto-type Library, FTC, Lagos | ₦15,258,437.25 | MTB 5 APPROVAL
Vide file ref. No. HCSF/CSO/PD/456/S.14
15 | M/S First Konnectronic Ltd | 2011-11-14 | Establishment of e-Library, FTC, Lagos | ₦13,110,200.00 | MTB 5 APPROVAL Vide file ref. No. HCSF/CSO/PD/456/S.15
16 | M/S Conban Nig. Ltd | 2011-11-14 | Sinking/Rehabilitation of 2 Nos. Boreholes with Overhead Tank facilities, FTC, Kaduna | ₦12,377,035.71 | MTB 5 APPROVAL Vide file ref. No. HCSF/CSO/PD/456/S.16
17 | M/S Amso Investment Ltd | 2011-11-14 | Construction of 5 Class Rooms Block , FTC, Ilorin | ₦19,035,334.50 | MTB 5 APPROVAL Vide file ref. No. HCSF/CSO/PD/456/S.18
18 | M/S Asoas Nig. Ltd | 2011-11-14 | Construction of 1 No. Students Hostel, FTC, Ilorin | ₦110,938,066.15 | MTB 5 APPROVAL Vide file ref. No. HCSF/CSO/PD/456/S.18
19 | M/S Patona Brooks Ltd | 2011-11-14 | Construction of Fencing/Gate, FTC, Ilorin | ₦50,851,415.37 | MTB 5 APPROVAL Vide file ref. No. HCSF/CSO/PD/456/S.19
20 | M/S Tolinz Global Resources Ltd | 2011-11-14 | Construction of 8 Nos. Training Rooms, FTC, Ilorin | ₦60,410,377.20 | MTB 5 APPROVAL Vide file ref. No. HCSF/CSO/PD/456/S.20
21 | M/S Delsherkpan Int. Ltd | 2011-11-14 | Construction of Library Block, FTC, Ilorin | ₦40,781,134.80 | MTB 5 APPROVAL Vide file ref. No. HCSF/CSO/PD/456/S.23
22 | M/S Churchgate Nigeria Ltd | 2011-11-14 | Construction of 1 No. Hostel Block, FTC, Enugu | ₦23,970,198.00 | MTB 5 APPROVAL Vide file ref. No. HCSF/CSO/PD/456/S.22
23 | M/S Delsherkpan Int. Ltd | 2011-11-14 | Construction of 1 No. of Block of Class Rooms FTC ,Enugu | ₦23,091,559.50 | MTB 5 APPROVAL Vide file ref. No. HCSF/CSO/PD/456/S.23
24 | M/S Marto Global Link Ltd | 2011-11-14 | Repair & Renovation of Dilapidated structures, FTC, Calabar | ₦26,990,439.00 | MTB 5 APPROVAL Vide file ref. No. HCSF/CSO/PD/456/S.24
25 | M/S Gupasha venture Ltd | 2011-11-14 | Construction of Perimeter Fence/Gate, FTC, Calabar | ₦47,882,520.00 | MTB 5 APPROVAL Vide file ref. No. HCSF/CSO/PD/456/S.1
26 | M/S Lani &Baego Ltd | 2011-11-14 | Construction of 1 No.Block of Training Rooms, FTC, Calabar | ₦39,400,972.00 | MTB 5 APPROVAL Vide file ref. No. HCSF/CSO/PD/456/S.2
27 | M/S Lowel Ind. Nig. Ltd | 2011-11-14 | Construction of An Auditorium, FTC, Calabar | ₦46,936,706.00 | MTB 5 APPROVAL Vide file ref. No. HCSF/CSO/PD/456/S.3
28 | M/S G. I.M.P Investment Ltd | 2011-11-14 | Construction of 1 No. Library Block, FTC, Calabar | ₦25,145,249.85 | MTB 5 APPROVAL Vide file ref. No. HCSF/CSO/PD/456/S.4
29 | M/S Greenland Tech Logistic. Ltd | 2011-11-14 | Construction of a Block of Hostel, FTC, Calabar | ₦30,023,280.00 | MTB 5 APPROVAL Vide file ref. No. HCSF/CSO/PD/456/S.5
30 | M/S Becotech Intl. Ltd | 2011-11-14 | Construction of An 8 Class Rooms Block , FTC, Maiduguri | ₦71,467,428.02 | MTB 5 APPROVAL Vide file ref. No. HCSF/CSO/PD/456/S.6
31 | M/S Geroma Nig. Ltd | 2011-11-14 | Construction of An Auditorium, FTC, Maiduguri | ₦47,189,729.50 | MTB 5 APPROVAL Vide file ref. No. HCSF/CSO/PD/456/S.7
32 | M/S Attahir Intl. Enterprise Nig. Ltd | 2011-11-14 | Construction of 1 No. Library Block, FTC, Maiduguri | ₦28,975,177.00 | MTB 5 APPROVAL Vide file ref. No. HCSF/CSO/PD/456/S.8
33 | M/S Konkritek Intl. Ltd | 2011-11-14 | Construction of 1 No. Hostel Block, FTC, Maiduguri | ₦68,006,484.00 | MTB 5 APPROVAL Vide file ref. No. HCSF/CSO/PD/456/S.9
34 | M/S A.C. Magnate Investment Ltd | 2011-11-14 | Construction of 1 No. Warehouse, PSIN, Abuja. | ₦57,408,186.00 | MTB 5 APPROVAL Vide file ref. No. HCSF/CSO/PD/456/S.10
35 | M/S First Konnectronic Ltd | 2011-11-14 | Provision of e-Distance Learning, PSIN, Abuja. | ₦48,615,479.50 | MTB 5 APPROVAL Vide file ref. No. HCSF/CSO/PD/456/S.11
36 | M/S Total Facility Management Nig. Ltd | 2011-11-14 | Renewal of Retainership for Cleaning of Block A, Ground Floor -8th Floor, including Roof, Gardening and Fumigation | ₦19,797,023.61 | MTB 5 APPROVAL Vide file ref. No. HCSF/CSO/PD/479/1
37 | M/S De-John Peru Nig. Ltd | 2011-11-14 | Renewal of Retainership for Cleaning of Block B, Ground Floor 1-4th Floor, including Roof | ₦12,461,820.00 | MTB 5 APPROVAL Vide file ref. No. HCSF/CSO/PD/472/1
38 | M/S Tsapta Cleaners Ltd | 2011-11-14 | Renewal of Retainership for Cleaning of Block B, 5th Floor -11th Floor, including Roof | ₦12,232,501.00 | MTB 5 APPROVAL Vide file ref. No. HCSF/CSO/PD/460/1
39 | M/S Glengate Nig. Ltd | 2011-11-14 | Renewal of Retainership for Cleaning of Block C, Ground Floor 1-8th Floor, including Roof | ₦19,265,610.00 | MTB 5 APPROVAL Vide file ref. No. HCSF/CSO/PD/461/1
40 | M/S Yamokeen Ventures Ltd | 2011-11-14 | Renewal of Retainership for Cleaning of Block D, Ground Floor-8th Floor, including Roof | ₦18,286,506.00 | MTB 5 APPROVAL Vide file ref. No. HCSF/CSO/PD/462/1
41 | M/S Gil Offordile &Associates | 2011-11-14 | Renewal of Retainership for Cleaning of Block E, Ground Floor -4th Floor, including Roof | ₦11,399,010.00 | MTB 5 APPROVAL Vide file ref. No. HCSF/CSO/PD/463/1
42 | M/S Gapyil Global Concept Ltd | 2011-11-14 | Renewal of Retainership for Cleaning of Block E, 5th Floor -11th, including Roof | ₦12,131,694.80 | MTB 5 APPROVAL Vide file ref. No. HCSF/CSO/PD/456/1
43 | M/S Greensols Energy Revolution Nig. Ltd. | 2011-11-14 | Renewal of Retainership for Cleaning of Car Park, Phase II, Basement -6th Floors, including Roof | ₦6,415,378.20 | MTB 5 APPROVAL Vide file ref. No. HCSF/CSO/PD/464/1
44 | M/S Glengate Nig. Ltd | 2011-11-14 | Renewal of Retainership for Cleaning of Tower G, Phase III, Eleven(11) Floors, including Roof | ₦12,434,322.00 | MTB 5 APPROVAL Vide file ref. No. HCSF/CSO/PD/464/1
45 | M/S Zantax Cleaners Nig. Ltd | 2011-11-14 | Renewal of Retainership for Cleaning of Tower J, Phase III, Eleven(11) Floors, including Roof | ₦12,836,975.00 | MTB 5 APPROVAL Vide file ref. No. HCSF/CSO/PD/467/1
46 | M/S Nwapu Facility Managers Ltd | 2011-11-14 | Renewal of Retainer ship for Cleaning of Podia, Phase III, Front and Rear Podia(six Floors) including Roof | ₦12,520,323.00 | MTB 5 APPROVAL Vide file ref. No. HCSF/CSO/PD/468/1
47 | M/S Violet Parks & Premises Investment Ltd | 2011-11-14 | Renewal of Retainer ship for Cleaning of Phase III, Ground Floor, Basement and Garden | ₦15,159,144.00 | MTB 5 APPROVAL Vide file ref. No. HCSF/CSO/PD/469/1
48 | M/S A. J&C Integrated Ltd | 2011-11-14 | Renewal of Retainer ship for Cleaning of Offices and Garden, Karu Records Centre, Abuja. | ₦8,205,750.00 | MTB 5 APPROVAL Vide file ref. No. HCSF/CSO/PD/470/1
49 | M/S First Konnectronics technology Ltd | 2011-11-14 | Establishment of an e-Library at FTC, Lagos | ₦13,110,200.00 | MTB 5 APPROVAL Vide file ref. No. HCSF/CSO/PD/
50 | Bureau of Public Procurement (BPP) | 2011-12-28 | Painting of Federal Secretariat Complex, Phase II, Abuja | ₦76,893,993.75 | MTB 6 APPROVAL Vide file ref. No. HCSF/CSO/HRM/1184/VOL:1/120
51 | M/S Machiom Ventures | 2011-12-28 | Supply of 216 sets of Chairs and Tables to Federal training Centre, Ilorin | ₦5,400,000.00 | PS (MDO) APPROVAL Vide file ref. No.
S.D/Proc/2488/S.27/49
52 | M/S Foretec Investment Ltd. | 2011-12-28 | Supply and Installation of 76 nos. of HP 2055D Printers and accessories | ₦6,783,000.00 | MTB 6 APPROVAL Vide file ref. No. HCSF/PRS/ICT/PROC/56/S.08
53 | M/S Ani-Cee Global Concept Ltd. | 2011-12-29 | Supply of 27 Nos. Dell Desktop Computers | ₦4,995,000.00 | PS (MDO) APPROVAL Vide file ref. No. S.D/Proc/2488/S.2/17
54 | M/S Hecol Nigeria Ltd. | 2011-12-29 | Supply of office furniture, Federal Training Centre, Calabar | ₦2,700,000.00 | PS (MDO) APPROVAL Vide file ref. No. S.D/Proc/2488/S.20/24
55 | M/S Mirabel Global Resources Nig. Ltd | 2011-12-29 | Connection of Water Supply to the Permanent site, Federal Training Centre, Calabar | ₦4,053,222.60 | PS (MDO) APPROVAL Vide file ref. No. S.D/Proc/2488/S.17/19
56 | M/S Gupasha Ventures Ltd. | 2011-12-29 | Sinking of Bore hole at Federal Training Centre, Calabar | ₦7,237,897.40 | PS (MDO) APPROVAL Vide file ref. No. S.D/Proc/2488/S.19/17
57 | M/S Aligat Nigeria Ltd. | 2011-12-29 | Supply of Desktop Computers at Federal Training Centre, Maiduguri | ₦2,628,371.30 | PS (MDO) APPROVAL Vide file ref. No. SD/PROC/ 2488/S.23/40
58 | M/S Blueprint Marketing Services Ltd | 2011-12-29 | Supply of Library books for Federal Training Centre, Lagos | ₦2,709,921.00 | PS (MDO) APPROVAL Vide file ref. No. S.D/Proc/2488/S.5/23/38
59 | M/S Hi-Mansion Allied Services Ltd. | 2011-12-29 | Supply of Office Furniture, Federal Training Centre, Lagos | ₦2,700,000.00 | PS (MDO) APPROVAL Vide file ref. No. SD/PROC/2488/S.1/19
60 | M/S Abafi General Ventures Ltd. | 2011-12-29 | Supply of Office Furniture, Federal Training Centre, Ilorin | ₦2,540,000.00 | PS (MDO) APPROVAL Vide file ref. No. SD/PROC/2488/S.10/26
61 | M/S Bishmur Ltd. | 2011-12-29 | Supply of Students Beds, Mattresses and Pillows at Federal Training Centre, Kaduna | ₦1,436,989.70 | PS (MDO) APPROVAL Vide file ref. No. SD/PROC/2488/S.8/24
62 | M/S Maral Nig. Ltd. | 2011-12-29 | Supply of Computers for Federal Training Centre, Kaduna | ₦2,575,566.00 | PS (MDO) APPROVAL Vide file ref. No. SD/PROC/2488/S.7/16
63 | M/S Jonad Enterprises | 2011-12-29 | Supply of 30 Nos. of Sleeping Kits at the Federal Training Centre, Lagos | ₦2,700,708.00 | PS (MDO) APPROVAL Vide file ref. No. SD/PROC/2488/S.4/25
64 | M/S Adatech Integrated Services Ltd. | 2011-12-29 | Supply of Learning Materials Federal Training Centre, Lagos | ₦4,998,015.00 | PS (MDO) APPROVAL Vide file ref. No. SD/PROC/2488/S.3/19
65 | M/S Danak Transglobal Ventures Ltd. | 2011-12-29 | Rehabilitation of Perimeter Fence at Federal Training Centre, Enugu | ₦3,618,948.70 | PS (MDO) APPROVAL Vide file ref. No. SD/PROC/2488/S.16/18
66 | M/S Machiom Ventures | 2011-12-29 | Clearing of the Permanent site of Federal Training Centre, Calabar | ₦5,066,544.80 | PS (MDO) APPROVAL Vide file ref. No. SD/PROC/2488/S.21/17
67 | M/S Toyin Investment Nig. Ltd | 2011-12-29 | Connection of Permanent Site Federal Training Centre, Calabar to the National Grid | ₦5,428,423.00 | PS (MDO) APPROVAL Vide file ref. No. SD/PROC/2488/S.7/16
68 | M/S Bawgh International Ltd | 2011-12-29 | Procurement of 12 Nos. Del Computers for Federal Training Centre, Enugu | ₦2,171,369.50 | PS (MDO) APPROVAL Vide file ref. No. SD/PROC/2488/S.14/18
69 | M/S Hometech Consortium Ltd | 2011-12-29 | Sinking/reticulation of borehole at Federal Training Centre, Ilorin | ₦9,796,000.00 | PS (MDO) APPROVAL Vide file ref. No. SD/PROC/2488/S.11/30
70 | M/S jamec West Africa Ltd | 2011-12-29 | Connection/Reticulation of Water Supply at Federal Training Centre Maiduguri | ₦3,143,624.00 | PS (MDO) APPROVAL Vide file ref. No. SD/PROC/2488/S.22/19
71 | M/S HomeTech Constructium Ltd | 2011-12-29 | Contract for the Clearing of the Permanent Site, Federal Training Centre Ilorin | ₦9,995,650.00 | PS (MDO) APPROVAL Vide file ref. No. SD/PROC/2488/S.13/23
72 | M/S Lume Resource | 2011-12-29 | Fumigation of Federal Training Centre Enugu | ₦3,679,249,70 | PS (MDO) APPROVAL Vide file ref. No. SD/PROC/2488/S.15/17
73 | M/S Fransprisco Impex Nigeria Ltd. | 2011-06-30 | Supply of Library Materials | ₦1,500,000.00 | PS APPROVAL Vide file ref. No. HCSF/PRS/LIB/286/I/76
74 | M/S Micro Alliance | 2011-06-30 | Installation of Back-Up Server for E-Learning in OHCSF | ₦1,695,500.00 | PS APPROVAL Vide file ref. No. HCSF/904/T
75 | M/S Christec Computers Ltd. | 2011-10-04 | Supply and Installation of Computer System | ₦3,744,090.00 | PS (CSO) APPROVAL Vide file ref. No. HCSF/PRS/ICT/56/II/19
|  |  | Grand total | ₦1,951,952,596.21
OFFICE OF THE HEAD OF THE CIVIL SERVICE OF THE FEDERATION
2011 PROCUREMENT RECORDS – RECURRENT
S/N | NAME OF CONTRACTOR | DATE OF AWARD | NATURE OF CONTRACT | VALUE OF CONTRACT | RECORD OF PROCUREMENT PROCEEDINGS
₦
1 | M/S Phonotherm Nig. Ltd. | 2011-06-23 | Additional repair works at the Lagos Liaison office of the Head of the Head of the Civil Service of the Federation | 9953422.5 | PS APPROVAL vide file Ref. No. HCSF/LLO/3049/S.I
2 | M/S Al-Jawal Global Resources Ltd. | 2011-07-27 | Supply of Stationery items | 2227875 | PS APPROVAL vide file Ref. No. HCSF/CSO/HRM/PROC.1123/S.04/I/14
3 | M/S Mac-Tuma Options Ltd. | 2011-07-27 | Supply of Fire proof cabinet | 4875000 | PS APPROVAL vide file Ref. No. HCSF/CSO/HRM/PROC.1123/S.07
4 | M/S Kumasi & Eke Multi Services Ltd | 2011-07-27 | Supply of Stationery Items | 1206400 | PS APPROVAL vide file Ref. No. HCSF/CSO/HRM/PROC.1123/S.14/I/12
5 | M/S Felypo Concepts Ltd. | 2011-07-28 | Supply of Fire proof cabinet | 4875000 | PS APPROVAL vide file Ref. No. HCSF/CSO/HRM/PROC.1123/S.01
6 | M/S Absek Investments Nigeria Ltd | 2011-07-28 | Supply of stationery Items | 1200563 | PS APPROVAL vide file Ref. No. HCSF/CSO/HRM/PROC.1123/S.11
7 | M/S Larry Press Ltd | 2011-08-03 | Printing of Pre-retirement training modules customized jotters and certificates | 9590000 | PS APPROVAL vide file Ref. No. BPSR/ADM.88/III
8 | M/S Five Fingers Global Resources Ltd | 2011-08-03 | Supply of Stationery Items | 4680000 | PS APPROVAL vide file Ref. No. HCSF/CSO/HRM/PROC.1123/S.09/I/14
9 | M/S Magar Conceptual & Allied Serv. Ltd. | 2011-08-03 | Supply of Stationery Items | 4500000 | PS APPROVAL vide file Ref. No. HCSF/CSO/HRM/PROC.1123/S.08
10 | M/S Oraci Nigeria Ltd. | 2011-08-03 | Supply of Stationery Items | 1287000 | PS APPROVAL vide file Ref. No. HCSF/CSO/HRM/PROC.1123/S.15
11 | M/S Fac Intergrated Service Ltd | 2011-08-03 | Supply of Stationery Items | 3,120,000,00 | PS APPROVAL vide file Ref. No. HCSF/CSO/HRM/PROC.1123/S.06
12 | M/S Bendora Investment Ltd | 2011-08-03 | Supply of Stationery Items | 3,120,000,00 | PS APPROVAL vide file Ref. No. HCSF/CSO/HRM/PROC.1123/S.02
13 | M/S Five Fingers Global Resource Ltd | 2011-08-03 | Supply of Stationery Items | 3,001,050,00 | PS APPROVAL vide file Ref. No. HCSF/CSO/HRM/PROC.1123/S.13
14 | M/S Bisconmak &Sons Ltd | 2011-08-03 | Supply of Photocopier | 1,291,170,00 | PS APPROVAL vide file Ref. No. HCSF/CSO/HRM/PROC.1123/S.12
15 | M/S Samons Continental Co. Nig. Ltd | 2011-08-19 | Supply of Stationery Items | 4,992,840,00 | PS APPROVAL vide file Ref. No. HCSF/CSO/HRM/PROC.1123/S.10
16 | M/S Ani-Cee Global Concept Ltd | 2011-08-19 | Supply of Stationery Items | 4,096,950,00 | PS APPROVAL vide file Ref. No. M3017/S.211/I/28
17 | M/S B&S Nig. Enterprises | 2011-08-19 | Renovation of Office and | 2847745.5 | PS APPROVAL vide file Ref. No. HCSF/SW/HM/H021/S.234/256
Purchase of Chair
18 | M/S Ibmar Enterprises | 2011-08-19 | Supply of Air Conditioner and Refrigerator Spare Part | 1514415 | PS APPROVAL vide file Ref. No. HCSF/SW/024/II/298
19 | M/S Oludat Nig Company Ltd | 2011-08-19 | Renovation of Conference Hall | 6376000 | PS APPROVAL vide file Ref. No. PS/HOS/MA&M/05/11
20 | M/S Dippy Dunny Ventures | 2011-08-19 | Supply of Panasonic Air Conditioner | 3735375 | PS APPROVAL vide file Ref. No. HCSF/PRS/310/I/65
21 | M/S Ani-Cee Global Concept Limited | 2011-08-19 | Supply of Office Material | 2902284 | PS APPROVAL vide file Ref. No. BPSR/ADM/INVT/MGT/173/II/15
22 | M/S Samons Continental Co.Nig Ltd | 2011-08-19 | Supply of Stationery Items | 4992840 | PS APPROVAL vide file Ref. No. HCSF/SW/HM/HO/Vol. III/10
23 | M/S Blessed Uche Collins Int Com.Ltd | 2011-08-10 | Supply of Computer Material | 1158000 | PS APPROVAL vide file Ref. No. BPSR/CS/36/I/13
24 | M/S Ani-Cee Concept Ltd | 2011-08-10 | Supply of Office Materials | 1264000 | PS APPROVAL vide file Ref. No. BPSR/PRS/258/20
25 | M/S Global Royal Int. Concept Ltd | 2011-08-10 | Supply of Office Requirements | 725000 | PS APPROVAL vide file Ref. No. BPSR/GIR/2/9
26 | M/S Makera Int. Resources Nig Ltd | 2011-08-10 | Supply of Office Equipment | 1456000 | PS APPROVAL vide file Ref. No. HCSF/PS/CSO/264/I
27 | M/S E&E Nestor Project Service Ltd | 2011-08-11 | Furnishing of Guest Rooms | 3000000 | PS (CSO) APPROVAL vide file Ref. No. HCSF/SW/SS/310/S.4/T1
28 | M/S Enda Tosh Venture Ent. | 2011-08-11 | Supply of Stationery items | 3662230 | PS (CSO) APPROVAL vide file Ref. No. HCSF/PROC/ST.608/I
29 | M/S Dippy Dunny Ventures | 2011-08-11 | Supply of Stationery items | 3968215 | PS (CSO) APPROVAL vide file Ref. No. HCSF/PROC/ST/117/T/37
30 | M/S Lekan Sofola & Conpany | 2011-08-11 | Supply of Store Consumables | 3018250 | PS (CSO) APPROVAL vide file Ref. No. M3017/S.045/I/
31 | M/S Solid Link Technologies Limited | 2011-08-11 | Supply of Stationery items | 3000800 | PS (CSO) APPROVAL vide file Ref. No. HCSF/PROC/ST/.24/I
32 | M/S Venture De Zodac Limited | 2011-08-11 | Supply of Stationery items | 3344000 | PS (CSO) APPROVAL vide file Ref. No. HCSF/SM/HM/HO/Vol.IV/8
33 | M/S Chikzon Nig Enterprise | 2011-08-11 | Supply of Stationery Material | 4196400 | PS (CSO) APPROVAL vide file Ref. No. HCSF/CSO/PROC/ST.102/I/35
34 | M/S Lekan Sofola&Company | 2011-08-22 | Supply of Plumbing Materials | 1751295 | PS (CSO) APPROVAL vide file Ref. No. HCSF/CSO/SWD/MTCE/25
35 | M/S Kachi Concepts | 2011-08-22 | Printing of Newspaper | 498750 | PS (CSO) APPROVAL vide file Ref. No. BPSR/CS/33/I/T
36 | M/S Anchor Daraware Solution | 2011-08-22 | Printing of Newspaper | 4100000 | PS (CSO) APPROVAL vide file Ref. No. HCSF/CSO/PD/451
37 | M/S Anchor Daraware Solution | 2011-08-22 | Reconfiguration and Reactivation of Intranet system | 4100000 | PS (CSO) APPROVAL vide file Ref. No. HCSF/CSO/PD/451
38 | M/S Anchor Dataware Solution | 2011-08-29 | Installation of interactive web portal and content system | 3930000 | PS APPROVAL vide file Ref. No. HCSF/CSO/PD/451
39 | M/S Ibmar Enterprise | 2011-08-29 | Supply of Door Locks | 967000 | PS APPROVAL vide file Ref. No. HCSF/SW/HM/HO21/S.234/256/51
40 | M/S Xavier Communications Ltd | 2011-10-12 | Publication of Selected Speeches | 4980000 | PS APPROVAL vide file Ref. No. BPSR/CS/59/I
41 | M/S Xavier Communications | 2011-10-14 | Production of Reform literature and generic guidelines | 4920000 | PS APPROVAL vide file Ref. No. BPSR/CS/16/I/147
42 | M/S Randberg Visage | 2011-10-14 | Training of Resident Information Officers | 4980000 | PS APPROVAL vide file Ref. No. BPSR/CS/29/II
43 | M/S Hawab Printer Ltd | 2011-10-18 | Printing of Ethics and Values document for the Federal Civil Service | 2500000 | PS APPROVAL vide file Ref. No. HCSF/061/S.1/II/Vol. II
44 | M/S Lekan Sofola&Company | 2011-10-26 | Renovation of ICT office | 807200 | PS APPROVAL vide file Ref. No. HCSF/PRS/ICTD/66/I/13
45 | M/S Chikzon Nigeria Enterprise | 2011-10-27 | Procurement of Computer Consumables | 4437500 | PS APPROVAL vide file Ref. No. OHCSF/CSO/PRO/10/II/18
46 | M/S Al-Nald Limited | 2011-11-02 | Supply of Office Equipment | 2740000 | PS APPROVAL vide file Ref. No. HCSF/CSO/HRM/PROC./II/68
47 | M/S Barbar Tee Industrial Interbiz | 2011-11-02 | Binding of backlogs of Newspaper & Gazettes | 848000 | PS APPROVAL vide file Ref. No. HCSF/PRS/LIB/413/54
48 | M/S Mikalu Abdullahi Arts Work & Printing | 2011-11-03 | Printing and Writing certificate | 1990000 | PS APPROVAL vide file Ref. No. SD.2106/26
49 | M/S Rubby(Nigeria)Ltd | 2011-11-16 | Procurement of industrial stabilizer | 2466328 | PS APPROVAL vide file Ref. No. HCSF/SW/HM/472/224
50 | M/S Grafpriscy Global Investment Nig Ltd | 2011-11-17 | Supply of Library books | 2365340 | PS APPROVAL vide file Ref. No. HCSF/PRS/LIB/418/I/69
51 | M/S Blue Camel Limited | 2011-11-21 | Supply and Installation of Solar Hybrid System | 4970700 | PS APPROVAL vide file Ref. No. HCSF/PRS/ICT/Proc./56/S.15/25
52 | M/S Pawa Safety Service Ltd | 2011-11-21 | Reactivation, Supply and Installation | 3538000 | PS APPROVAL vide file Ref. No. HCSF/SW/SS/992/123
53 | M/S Hussisyak Nig Ltd | 2011-11-21 | Supply of Office Furniture /Equipment | 1924500 | PS APPROVAL vide file Ref. No. HCSF/PS/ERO/245
54 | M/S Sebas Nig Ltd | 2011-11-22 | Supply of Office Furniture/Equipment | 1861000 | PS APPROVAL vide file Ref. No. HCSF/PS/ERO/245
55 | M/S Aflon Ltd. | 2011-11-23 | Training of Advance web content management in Minna | 869000 | PS APPROVAL vide file Ref. No. HCSF/PRS/ICT/PROC/56/S/03
56 | M/S Cyrux Global Ltd | 2011-12-09 | One (1) year subscription for global electronic database in Office of the Head of the Civil Service of the Federation | 4200000 | PS APPROVAL vide file Ref. No. HCSF/PRS/LIB/409/I/32
57 | M/S Dippy Dunny Ventures | 2011-12-09 | Supply of Office Equipment | 2431000 | PS APPROVAL vide file Ref. No. HCSF/MDO/MP/PROC/S.1093/S.I/26
58 | M/S Days Associate Service | 2011-12-12 | Supply of Diesel | 5717250 | PS APPROVAL vide file Ref. No. HCSF/SW/HM/HO/21/S.234/13/Vol. II/252
59 | M/S Compass Computers & Cyber Café | 2011-12-12 | Design and Development of Database Software | 3583060 | PS APPROVAL vide file Ref. No. HCSF/MDO/MP/PROC./S.1093/S.IV/26
60 | M/S Mamtach & ICT Consultancy Services Ltd. | 2011-12-12 | Supply of Computer Equipment | 3583060 | PS APPROVAL vide file Ref. No. HCSF/MDO/MP/PROC/S.1093/S. III/20
61 | M/S Briggy Resources Ltd. | 2011-12-12 | Supply of Office Requirement | 3153150 | PS APPROVAL vide file Ref. No. HCSF/MDO/MP/PROC/S.1093/S.II/26
62 | M/S Rocamil Nig. Ltd. | 2011-12-12 | Supply of Binding Machine | 4845300 | PS APPROVAL vide file Ref. No. HCSF/PRS/ICT/Vol. I/27
63 | M/S Rubby (Nigeria) Ltd | 2011-12-21 | Supply and Installation of Industrial Stabilizer | 3150000 | PS APPROVAL vide file Ref. No. HCSF/SW/HM/472/224
64 | M/S Rash Ideal Kreations | 2011-12-22 | Printing and Supply of Office Stationeries | 1550000 | PS APPROVAL vide file Ref. No. HSCF/161/T/9
65 | M/S Jambey Concepts | 2011-12-27 | Repair of Photocopier Machines | 330100 | PS APPROVAL vide file Ref. No. HCSF/PSO/SW/ADV/001/I
66 | M/S Onye-eteremmanu Inv. Nig. Ltd. | 2011-12-27 | Supply of Stationery Items | 790000 | PS APPROVAL vide file Ref. No. HCSF/HRM/ST/003/TF/I
67 | M/S Ondo-River-Side Investment’s Ltd. | 2011-12-27 | Supply of Stationery Items | 1296300 | PS APPROVAL vide file Ref. No. HCSF/PS/CSO/271/II/52
68 | M/S Lekan Sofola & Company | 2011-12-27 | Supply of Stationery Items | 1950000 | PS APPROVAL vide file Ref. No. HCSF/CSO/PRO/10/II/33
69 | M/S Chikzon Nigeria Enterprises | 2011-12-27 | Supply of Gestetner Toners | 1927250 | PS APPROVAL vide file Ref. No. HCSF/CSO/Proc./3017/I/27
70 | M/S Ab-Lab investment Nig. Ltd. | 2011-12-27 | Supply of Photocopiers and Office Equipments | 2395750 | PS APPROVAL vide file Ref. No. HCSF/PD/GLA/A/IV/I/11
71 | M/S Viceprom Investment Nig. Ltd. | 2011-12-27 | Printing of Letter Head on Conqueror Paper | 1000000 | PS APPROVAL vide file Ref. No. HCSF/CSO/PD/VIII/I
72 | M/S B & S Nigeria Enterprises | 2011-12-27 | Supply of Stationery and Hardcover notes | 2000000 | PS APPROVAL vide file Ref. No. HCSF/CSO/PD/VII/10
73 | M/S God’s Agenda Concepts Global Ltd | 2011-12-27 | Supply of Computer Tables and Stationery Items | 4030000 | PS APPROVAL vide file Ref. No. HCSF/SW/GLA/B/PRO/274
74 | M/S Cylmax Global Link Ltd | 2011-12-28 | Supply of Printing inkjets | 3170000 | PS APPROVAL vide file Ref. No. HCSF/CSO/PD/VI/I
75 | M/S Prince Mega Logistics Partners Ltd | 2011-12-28 | Supply of Stationery Items | 2000000 | PS APPROVAL vide file Ref. No. HCSF/PD/GLA/A/VI/I/II
76 | M/S Nonny-Gold Services Ltd | 2011-12-28 | Supply of Stationery Items | 2812050 | PS APPROVAL vide file Ref. No. HCSF/PD/GLA/III
77 | M/S Zimra Environment & Engr. Co. Ltd. | 2011-12-28 | Supply of Computers and Accessories | 4792200 | PS APPROVAL vide file Ref. No. HCSF/SW/GLA/B/PRO/274
78 | M/S Chikzon Nigeria Enterprises | 2011-12-28 | Supply of Office Furniture for the Federal Civil Service Club, Mabushi | 1149750 | PS APPROVAL vide file Ref. No. HCSF/SW/SS/Proc./310/S.3/T²/S.11/10
79 | M/S Dippy Dunny Ventures | 2011-12-28 | Supply of Office Equipment for the Federal Civil Service Club, Mabushi | 4755450 | PS APPROVAL vide file Ref. No. HCSF/SW/SS/Proc./310/S.IV
80 | M/S Chakamai Ventures & Properties Ltd | 2011-12-28 | Supply of Office Furniture for the Mini Hall Federal Civil Service Club, Mabushi | 4788000 | PS APPROVAL vide file Ref. No. HCSF/SW/SS/Proc./310/S.3/T²/S.III/10
81 | M/S Tuyit Nigeria Ltd. | 2011-12-28 | Supply of Stationery Items | 4800000 | PS APPROVAL vide file Ref. No. HCSF/PD/GLA/A/VI/I/9
82 | M/S Olard Business Ltd. | 2011-12-29 | Supply of Office Furniture for the Main Bar, Federal Civil Service Club, Mabushi | 4961250 | PS APPROVAL vide file Ref. No. HCSF/SW/SS/Proc./310/S.I
83 | M/S Ani-Cee Global Concept Ltd. | 2011-12-29 | Supply of HP desktop Computer | 4995000 | PS APPROVAL vide file Ref. No. HCSF/SD/PROC./2488/S.2/I
84 | M/S Chikzon Nigeria Enterprises | 2011-09-26 | Supply of Stationery Items | 4939600 | PS APPROVAL Vide file ref. No. BPSR/PROC.101/S.I/7
85 | M/S Xavier Comm. Ltd. | 2011-10-14 | Production of Reform Literature, organizational & strategic corruption control guideline | 4950000 | PS APPROVAL Vide file ref. No. BPSR/CS/25/I/85
86 | M/S SYL Technics Ent. Nig. | 2011-06-07 | Supply and Installation of Close Circuit Television | 1231250 | PS (CMO) Approval vide file ref. No. CMO/PS/050/Vol.1/99
87 | M/S Five Finger Global Resources Ltd. | 2011-09-15 | Supply of Office Equipment | 4586740 | PS APPROVAL Vide file ref. No. BPSR/ADM./176/11/12
88 | M/S Dobas Nigeria Ltd. | 2011-09-30 | Production and Documentation of Federal Government Service Reforms | 4935000 | PS APPROVAL Vide file ref. No. BPSR/CS/04/11/T/127
89 | M/S Ani-Cee Global Concept Ltd | 2011-08-23 | Supply of Office Equipment | 4568740 | PS APPROVAL Vide file ref. No. BPSR/ADM/176/II
|  |  | Grand Total | 278137265.5
1951952596.21
2230089861.71

## National Youth Ser.
(A) | CAPITAL ROJECTS
PROCUREMENT RECORDS
PROCURING ENTITY (MDS): |  | NATIONAL YOUTH SERVICE CORPS
MINISTRY: |  | FEDERAL MINISTRY OF YOUTH DEVELOPMENT
FINANCIAL YEAR: |  | 2011
|  | BASIC DATA |  |  |  | CONTRACT AWARD | [5 empty] | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | ADVERTISEMENT DATE AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | CONTRACTOR | DATE OF CONTRACT AWARD | DATE OF CONTRACT COMMEN-CEMENT | CONTRACT PERIOD | CONTRACT VANUE | BUDGETARY PROVISION | AMOUNT PAID AS AT FEB 2012 | EXPECTED COMPLE-TION DATE | % COMPLETION AS AT | REMARKS
[10 empty] | N | N |  |  | 2012-02-01
1 | 1000KVA Power Generating Set | Federal Tenders Journal, National Daily and Compass Newspapers of February 7, 2011 | 250000000 | By bidding | Aug 9, 2011 | Basmol Ventures Limited | Aug 22, 2011 | Aug 22, 2011 | 4 weeks | 47020000 | 47027295 | 47020000 | Sept 19, 2011 | 100% | Com-pleted
2 | Toyota Hilux Vans | Federal Tenders Journal, National Daily and Compass Newspapers of February 7, 2011 | 250000000 | By bidding | Aug 9, 2011 | Enternity Int’l Ltd | Aug 22, 2011 | Aug 22, 2011 | 4 weeks | 25765000 | 25795435 | 25765000 | Sept 19, 2011 | 100% | Com-pleted
& Mai-Rem
Ventures Limited
3 | Water Tanker | Federal Tenders Journal, National Daily and Compass Newspapers of February 7, 2011 | 250000000 | By bidding | Aug 9, 2011 | Sitamek Ventures Limited | Aug 22, 2011 | Aug 22, 2011 | 4 weeks | 18200000 | 18225459 | 18200000 | Sept 19, 2011 | 100% | Com-pleted
4 | Tents/ | Federal Tenders Journal, National Daily and Compass Newspapers of February 7, 2011 | 250000000 | By bidding | Aug 9, 2011 | Duchan Contractors Limited | Aug 22, 2011 | Aug 22, 2011 | 4 weeks | 25060000 | 25116585 | 25060000 | Sept 19, 2011 | 100% | Com-pleted
Marquees 1,300 sitting capacity
(B) | RECURRENT
PROCUREMENT RECORDS
PROCURING ENTITY (MDS): |  | NATIONAL YOUTH SERVICE CORPS
MINISTRY: |  | FEDERAL MINISTRY OF YOUTH DEVELOPMENT
FINANCIAL YEAR: |  | 2011
|  | BASIC DATA |  |  |  | CONTRACT AWARD | [5 empty] | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | ADVERTISEMENT DATE AND MEDIA | APPROVAL THRESHOLD | PROCURE-MENT METHOD | BID OPENING DATE | CON-TRACTOR | DATE OF CONTRACT AWARD | DATE OF CONTRACT COMMEN-CEMENT | CONTRACT PERIOD | CONTRACT VANUE | BUDGETARY PROVISION | AMOUNT PAID AS AT FEB 2012 | EXPECTED COMPLE-TION DATE | % COMPLE-TION AS AT | REMARKS
[10 empty] | N | N |  |  | 2012-02-01
1 | 2011 Batch A Kit Items | Federal Tenders Journal, National Daily and the Nigerian Compass of November 15, 2010 | 50000000 | By bidding | Dec 14, 2010 | See the attached | Dec 23, 2010 | Dec 23, 2010 | 8 weeks | 946620000 | 2214450000 | 946620000 | Feb 17, 2011 | 100% | Com-pleted
2 | 2011 | Federal Tenders Journal, National Daily and the Nigerian Compass of May 16, 2011 | 50000000 | By bidding | June 10, 2011 | See the attached | June 21, 2011 | June 21, 2011 | 4 weeks | 946620000 | From No. 1 above | 934377000 | July 19, 2011 | 98.71% | Com-pleted
Batch B Kit Items
|  |  | 2011 BATCH A KIT ITEMS | [6 empty] | 2011 BATCH B KIT ITEMS
|  |  | NATIONAL YOUTH SERVICE CORPS (NYSC) | [6 empty] | NATIONAL YOUTH SERVICE CORPS (NYSC)
| S/N | PROJECT DESCRIPTION | DATE OF AWARD | NAME OF CONTRACTOR | PROJECT COST | REMARKS |  | S/N | PROJECT DESCRIPTION | DATE OF AWARD | NAME OF CONTRACTOR | PROJECT COST | REMARKS
| 1 | Corps Members’ Kit Items | December 23, 2010 | Ugo Garments Industry Limited | N25,010,500.00 | Completed |  | 1 | Corps Members’ Kit Items | June 21, 2011 | Osita Merchantile Works Limited | N25,010,500.00 | Completed
| 2 | Corps Members’ Kit Items | December 23, 2010 | J.O. Ebuoma & Sons Limited | N25,005,600.00 | Completed |  | 2 | Corps Members’ Kit Items | June 21, 2011 | J.O. Ebuoma & Sons Limited | N25,005,600.00 | Completed
| 3 | Corps Members’ Kit Items | December 23, 2010 | S-Turke International Limited | N25,004,880.00 | Completed |  | 3 | Corps Members’ Kit Items | June 21, 2011 | S-Turke International Limited | N25,004,880.00 | Completed
| 4 | Corps Members’ Kit Items | December 23, 2010 | Osita Merchantile Works Limited | N25,001,760.00 | Completed |  | 4 | Corps Members’ Kit Items | June 21, 2011 | Ugo Garments Industry Limited | N25,001,760.00 | Completed
| 5 | Corps Members’ Kit Items | December 23, 2010 | Lowell Industries Nigeria Limited | N24,101,900.00 | Completed |  | 5 | Corps Members’ Kit Items | June 21, 2011 | Lowell Industries Nigeria Limited | N24,099,500.00 | Completed
| 6 | Corps Members’ Kit Items | December 23, 2010 | Ya-Sad Enterprises Limited | N25,089,000.00 | Completed |  | 6 | Corps Members’ Kit Items | June 21, 2011 | Ya-Sad Enterprises Limited | N25,089,000.00 | Completed
| 7 | Corps Members’ Kit Items | December 23, 2010 | Bashmol Ventures Limited | N25,116,200.00 | Completed |  | 7 | Corps Members’ Kit Items | June 21, 2011 | Bashmol Ventures Limited | N25,116,200.00 | Completed
| 8 | Corps Members’ Kit Items | December 23, 2010 | Enternity International Limited | N25,185,000.00 | Completed |  | 8 | Corps Members’ Kit Items | June 21, 2011 | Enternity International Limited | N25,185,000.00 | Completed
| 9 | Corps Members’ Kit Items | December 23, 2010 | Gamji Nigeria Company Limited | N24,019,000.00 | Completed |  | 9 | Corps Members’ Kit Items | June 21, 2011 | Gamji Nigeria Company Limited | N23,094,000.00 | Completed
| 10 | Corps Members’ Kit Items | December 23, 2010 | Sul-Rak & A Nigeria Limited | N10,002,900.00 | Completed |  | 10 | Corps Members’ Kit Items | June 21, 2011 | Sul-Rak & A Nigeria Limited | N11,791,900.00 | Completed
| 11 | Corps Members’ Kit Items | December 23, 2010 | SS Hunny Ventures Limited | N16,037,400.00 | Completed |  | 11 | Corps Members’ Kit Items | June 21, 2011 | SS Hunny Ventures Limited | N16,037,400.00 | Completed
| 12 | Corps Members’ Kit Items | December 23, 2010 | Venco Mac V-Tex Nigeria Limited | N12,002,200.00 | Completed |  | 12 | Corps Members’ Kit Items | June 21, 2011 | Venco Mac V-Tex Nigeria Ltd | N14,372,000.00 | Completed
| 13 | Corps Members’ Kit Items | December 23, 2010 | Shockle Gold Nigeria Limited | N17,159,550.00 | Completed |  | 13 | Corps Members’ Kit Items | June 21, 2011 | Shockle Gold Nigeria Limited | N14,270,500.00 | Completed
| 14 | Corps Members’ Kit Items | December 23, 2010 | Loko Resources Limited | N25,031,000.00 | Completed |  | 14 | Corps Members’ Kit Items | June 21, 2011 | Loko Resources Limited | N25,064,500.00 | Completed
| 15 | Corps Members’ Kit Items | December 23, 2010 | Joyana Suites Limited | N25,008,900.00 | Completed |  | 15 | Corps Members’ Kit Items | June 21, 2011 | Joyana Suites Limited | N25,322,900.00 | Completed
| 16 | Corps Members’ Kit Items | December 23, 2010 | Alab Nigeria Limited | N16,062,900.00 | Completed |  | 16 | Corps Members’ Kit Items | June 21, 2011 | Alab Nigeria Limited | N22,931,500.00 | Completed
| 17 | Corps Members’ Kit Items | December 23, 2010 | Sad-Qaf Enterprises Limited | N18,226,000.00 | Completed |  | 17 | Corps Members’ Kit Items | June 21, 2011 | Sad-Qaf Enterprises Limited | N18,226,000.00 | Completed
| 18 | Corps Members’ Kit Items | December 23, 2010 | Sailthru Nigeria Limited | N8,305,000.00 | Completed |  | 18 | Corps Members’ Kit Items | June 21, 2011 | Cosguide Shelter Limited | N14,581,000.00 | Completed
| 19 | Corps Members’ Kit Items | December 23, 2010 | C-Bus Gold Limited | N14,306,040.00 | Completed |  | 19 | Corps Members’ Kit Items | June 21, 2011 | C-Bus Gold Limited | N16,095,040.00 | Completed
| 20 | Corps Members’ Kit Items | December 23, 2010 | Sitamek Venturs Limited | N24,175,200.00 | Completed |  | 20 | Corps Members’ Kit Items | June 21, 2011 | Sitamek Ventures Limited | N14,147,000.00 | Completed
| 21 | Corps Members’ Kit Items | December 23, 2010 | Enny Ventures | N17,009,290.00 | Completed |  | 21 | Corps Members’ Kit Items | June 21, 2011 | Setcon Limited | N15,267,500.00 | Completed
| 22 | Corps Members’ Kit Items | December 23, 2010 | Pireen Nigeria Limited | N13,138,500.00 | Completed |  | 22 | Corps Members’ Kit Items | June 21, 2011 | Pireen Nigeria Limited | N13,138,500.00 | Completed
| 23 | Corps Members’ Kit Items | December 23, 2010 | Rosies Textile Mills Limited | N10,184,000.00 | Completed |  | 23 | Corps Members’ Kit Items | June 21, 2011 | Mustamin Nigeria Limited | N5,067,000.00 | Completed
| 24 | Corps Members’ Kit Items | December 23, 2010 | FUT Concept Manuf Nigeria Lt | N12,243,000.00 | Completed |  | 24 | Corps Members’ Kit Items | June 21, 2011 | FUT Concept Manuf Nig Limited | N12,243,000.00 | Not done
| 25 | Corps Members’ Kit Items | December 23, 2010 | First El-Shabab Nigeria Limited | N12,001,860.00 | Completed |  | 25 | Corps Members’ Kit Items | June 21, 2011 | First El-Shabab Nigeria Limited | N15,275,000.00 | Completed
| 26 | Corps Members’ Kit Items | December 23, 2010 | NYSC Garment Factory, Mgbakwu | N7,868,000.00 | Completed |  | 26 | Corps Members’ Kit Items | June 21, 2011 | NYSC Garment Factory, Mgbakwu | N7,868,000.00 | Completed
| 27 | Corps Members’ Kit Items | December 23, 2010 | NYSC Garment Factory, Minna | N7,883,475.00 | Completed |  | 27 | Corps Members’ Kit Items | June 21, 2011 | NYSC Garment Factory, Minna | N7,883,475.00 | Completed
| 28 | Corps Members’ Kit Items | December 23, 2010 | Mail-Rem Ventures Limited | N18,430,750.00 | Completed |  | 28 | Corps Members’ Kit Items | June 21, 2011 | Mail-Rem Ventures Limited | N18,056,750.00 | Completed
| 29 | Corps Members’ Kit Items | December 23, 2010 | Ya-Sin Enterprises Limited | N15,009,300.00 | Completed |  | 29 | Corps Members’ Kit Items | June 21, 2011 | Ya-Sin Enterprises Limited | N15,009,300.00 | Completed
| 30 | Corps Members’ Kit Items | December 23, 2010 | Indometreel Nigeria Limited | N4,200,000.00 | Completed |  | 30 | Corps Members’ Kit Items | June 21, 2011 | Cite & Cite Limited | N17,495,740.00 | Completed
| 31 | Corps Members’ Kit Items | December 23, 2010 | Alsus Ventures | N12,187,540.00 | Completed |  | 31 | Corps Members’ Kit Items | June 21, 2011 | Alsus Ventures | N12,187,540.00 | Completed
| 32 | Corps Members’ Kit Items | December 23, 2010 | Yusjafa Enterprises Company | N12,406,600.00 | Completed |  | 32 | Corps Members’ Kit Items | June 21, 2011 | Yusjafa Enterprises Company | N13,086,000.00 | Completed
| 33 | Corps Members’ Kit Items | December 23, 2010 | Ajike Awoniyi Company Limited | N23,002,620.00 | Completed |  | S/N | PROJECT DESCRIPTION | DATE OF AWARD | NAME OF CONTRACTOR | PROJECT COST | REMARKS
| S/N | PROJECT DESCRIPTION | DATE OF AWARD | NAME OF CONTRACTOR | PROJECT COST | REMARKS |  | 33 | Corps Members’ Kit Items | June 21, 2011 | Ajike Awoniyi Company Limited | N20,161,800.00 | Completed
| 34 | Corps Members’ Kit Items | December 23, 2010 | Presidium Resources Nigeria Lt | N10,001,270.00 | Completed |  | 34 | Corps Members’ Kit Items | June 21, 2011 | Hercnian Integrated Services Limited | N12,571,270.00 | Completed
| 35 | Corps Members’ Kit Items | December 23, 2010 | Satco Nigeria Limited | N14,038,000.00 | Completed |  | 35 | Corps Members’ Kit Items | June 21, 2011 | Satco Nigeria Limited | N14,038,000.00 | Completed
| 36 | Corps Members’ Kit Items | December 23, 2010 | Glec Ventures Limited | N17,129,600.00 | Completed |  | 36 | Corps Members’ Kit Items | June 21, 2011 | Glec Ventures Limited | N17,129,600.00 | Completed
| 37 | Corps Members’ Kit Items | December 23, 2010 | B & E Enterprise Nigeria Limited | N4,026,000.00 | Completed |  | 37 | Corps Members’ Kit Items | June 21, 2011 | Dandiamond Nigeria Limited | N14,004,500.00 | Completed
| 38 | Corps Members’ Kit Items | December 23, 2010 | Mcdonald Jones Ent Nigeria Limited | N11,275,000.00 | Completed |  | 38 | Corps Members’ Kit Items | June 21, 2011 | Macdonald Jones Ent Nigeria Limited | N10,467,000.00 | Completed
| 39 | Corps Members’ Kit Items | December 23, 2010 | Moterfs Nigeria Limited | N13,100,000.00 | Completed |  | 39 | Corps Members’ Kit Items | June 21, 2011 | Moterfs Nigeria Limited | N13,100,000.00 | Completed
| 40 | Corps Members’ Kit Items | December 23, 2010 | Betty Pride Limited | N13,101,000.00 | Completed |  | 40 | Corps Members’ Kit Items | June 21, 2011 | Betty Pride Limited | N13,101,000.00 | Completed
| 41 | Corps Members’ Kit Items | December 23, 2010 | Shyjell Resources Limited | N14,004,500.00 | Completed |  | 41 | Corps Members’ Kit Items | June 21, 2011 | Shyjell Resources Limited | N14,004,500.00 | Completed
| 42 | Corps Members’ Kit Items | December 23, 2010 | Safari Textiles Limited | N13,008,250.00 | Completed |  | 42 | Corps Members’ Kit Items | June 21, 2011 | Safari Textiles Limited | N14,056,500.00 | Completed
| 43 | Corps Members’ Kit Items | December 23, 2010 | Rolan Concepts Limited | N16,022,000.00 | Completed |  | 43 | Corps Members’ Kit Items | June 21, 2011 | Rolan Concepts Limited | N22,565,800.00 | Completed
| 44 | Corps Members’ Kit Items | December 23, 2010 | Mark-Toyson Nigeria Limited | N10,152,200.00 | Completed |  | 44 | Corps Members’ Kit Items | June 21, 2011 | Mark-Toyson Nigeria Limited | N10,152,200.00 | Completed
| 45 | Corps Members’ Kit Items | December 23, 2010 | Bojih System Services | N18,105,100.00 | Completed |  | 45 | Corps Members’ Kit Items | June 21, 2011 | Bojih System Services | N17,089,500.00 | Completed
| 46 | Corps Members’ Kit Items | December 23, 2010 | GODM Shoe Industry Nig Ltd | N16,122,800.00 | Completed |  | 46 | Corps Members’ Kit Items | June 21, 2011 | Godm Shoe Industry Nig Limited | N15,057,400.00 | Completed
| 47 | Corps Members’ Kit Items | December 23, 2010 | Rodonvic Concepts Limited | N15,004,760.00 | Completed |  | 47 | Corps Members’ Kit Items | June 21, 2011 | Rodonvic Concepts Limited | N15,004,760.00 | Completed
| 48 | Corps Members’ Kit Items | December 23, 2010 | Prince Of Prints Limited | N15,299,680.00 | Completed |  | 48 | Corps Members’ Kit Items | June 21, 2011 | Prince of Prints Limited | N14,620,000.00 | Completed
| 49 | Corps Members’ Kit Items | December 23, 2010 | Fat-Dee Enterprises Limited | N23,026,560.00 | Completed |  | 49 | Corps Members’ Kit Items | June 21, 2011 | Fat-Dee Enterprises Limited | N14,100,000.00 | Completed
| 50 | Corps Members’ Kit Items | December 23, 2010 | CEE Industries Limited | N10,152,200.00 | Completed |  | 50 | Corps Members’ Kit Items | June 21, 2011 | CEE Industries Limited | N10,152,200.00 | Completed
| 51 | Corps Members’ Kit Items | December 23, 2010 | Goldman International Limited | N25,060,820.00 | Completed |  | 51 | Corps Members’ Kit Items | June 21, 2011 | Lab-Shir Ventures | N13,304,000.00 | Completed
| 52 | Corps Members’ Kit Items | December 23, 2010 | Solbec Limited | N25,039,700.00 | Completed |  | 52 | Corps Members’ Kit Items | June 21, 2011 | Biyaya Nigeria Limited | N14,157,000.00 | Completed
| 53 | Corps Members’ Kit Items | December 23, 2010 | Fez-Mega Industry Limited | N13,114,260.00 | Completed |  | 53 | Corps Members’ Kit Items | June 21, 2011 | Fez-Mega Industry Limited | N10,156,000.00 | Completed
| 54 | Corps Members’ Kit Items | December 23, 2010 | CaxtonJoe Nigeria Limited | N22,749,400.00 | Completed |  | 54 | Corps Members’ Kit Items | June 21, 2011 | Caxtonjoe Nigeria Limited | N23,168,900.00 | Completed
| 55 | Corps Members’ Kit Items | December 23, 2010 | Mithras Services Limited | N10,165,000.00 | Completed |  | 55 | Corps Members’ Kit Items | June 21, 2011 | Mithras Services Limited | N10,165,000.00 | Completed
| 56 | Corps Members’ Kit Items | December 23, 2010 | Krisco Investments Limited | N10,231,840.00 | Completed |  | 56 | Corps Members’ Kit Items | June 21, 2011 | Duchan Contractors Limited | N12,127,000.00 | Completed
| 57 | Corps Members’ Kit Items | December 23, 2010 | Ekadmas Nigeria Limited | N11,311,400.00 | Completed |  | 57 | Corps Members’ Kit Items | June 21, 2011 | Ekadmas Nigeria Limited | N12,023,800.00 | Completed
| 58 | Corps Members’ Kit Items | December 23, 2010 | Westrock Limited | N11,464,420.00 | Completed |  | 58 | Corps Members’ Kit Items | June 21, 2011 | Westrock Limited | N11,103,390.00 | Completed
| 59 | Corps Members’ Kit Items | December 23, 2010 | Danoks Nigeria Limited | N8,589,375.00 | Completed |  | 59 | Corps Members’ Kit Items | June 21, 2011 | Wood Green Nigeria Limited | N11,041,895.00 | Completed
|  | Total | 946620000 | [5 empty] | Total | N934,377,000.00
934377000
1880997000

## CFIPB 2011 P. R
CIVIL DEFENCE, FIRE, IMMIGRATION AND PRISONS SERVICES BOARD
PROCUREMENT RECORD FOR 2011 FINANCIAL YEAR
S/NO | CONTRACTOR | NATURE OF CONTRACT | AMOUNT | DATE OF AWARD
1 | Messrs Mandate Publication | Production of manuscripts on Guidelines for Appointment, Promotion and Discipline, Condition and Schemes of Service for the Four Paramilitary Services | 2442000 | 12th May, 2011
2 | Messrs Kasisa Nigeria Enterprises | Project Design of Biometric Database Capturing | 1235000 | 12th May, 2011
3 | Messrs Remi-Chris Computers Ltd. | Supply and Installation of 3 units of Hp Database Server, 20 units of Computer Sets with UPS, 5 units of Hp LaserJet 2055 Printer and 1 unit of Fargo/Evolis Identity Card Printer into CDIPB office, Abuja. | 7256750 | 27th June, 2011
4 | Messrs Frank Boye Nigeria Ltd. | Supply and Installation of 3 Units of 1.5KVA UPS and 1 Unit of 5 KVA Inverter/Batteries into CDIPB office, Abuja. | 1932500 | 1st Sept., 2011
5 | Messrs Dare & K Strongs Ltd. | Manpower Development on Computer Appreciation, Internet Training and Database Friendliness for Twenty-Five (25) CDIPB Staff. | 2959460 | 1st Sept., 2011
6 | Messrs Wealth Management Consultancy Ltd. | Supply and Installation of Internet Dish and Computer Networking into 50 Rooms of CDIPB Office Complex Area 1 Garki, Abuja. | 8456000 | 10th Nov., 2011
24281710

## NCA&C
PROCUREMENT RECORDS
PROCURING ENTITY (MDA): |  | NATIONAL COUNCIL FOR ARTS AND CULTURE
MINISTRY: |  | FEDERAL MINISTRY OF TOURISM, CULTURE AND NATIONAL ORIENTATION
FINANCIAL YEAR: |  | 2011
|  | BASIC DATE |  |  |  | CONTRACT AWARD | [5 empty] | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | ADVERTISEMENT DATE AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | CONTRACTOR | DATE OF CONTRACT AWARD | DATE OF CONTRACT COMMENCEMENT | CONTRACT PERIOD | CONTRACT VALUE (N) | BUDGETARY PROVISION (N) 2011 | AMOUNT PAID AS AT JANUARY - DECEMBER 2011 | EXPECTED COMPLETION DATE | % OF COMPLETION AS AT MARCH 2012 | REMARKS
1 | National Research Centre on Textile Traditions at Osogbo, Osun State (construction) | 3rd May 2010 / Federal Tender Journal, This Day and Daily Trust | 5million and above but less than 250million | NCB | 8th July, 2010 | Grillex Construction Co. Limited | 16th August, 2010 | August, 2009 | 2011 | 120 | 3M | 12384883.5 | December, 2015 | 54% | As an on-going project the total amount paid as at December 2011 include payment made in March, 2011 as part of the provision of 2010 budget financial year.
2 | National Research Centre on Boat Regatta in Uyo, Akwa Ibom State (construction) | 3rd May 2010 / Federal Tender Journal, This Day and Daily Trust | 5million and above but less than 250million | NCB | 8th July, 2010 | El-Gina Standard Company Limited | 16th August, 2010 | August, 2009 | 2011 | 180 | 10M | 7291898.01 | December, 2015 | 6.4%
3 | Development of Craft Centres (Construction)
a | Awka | 3rd May 2010 / Federal Tender Journal, This Day and Daily Trust | 5million and above but less than 250million | NCB | 8th July, 2010 | New Samekon Limited | 16th August, 2010 | August, 2009 | 2011 | 100 | 7.5M | 5000000 | December, 2015 | 19%
b | Ikare | 4th May 2010 / Federal Tender Journal, This Day and Daily Trust | 5million and above but less than 250million | NCB | 8th July, 2010 | Ayubkan Venture Nig. Ltd | 16th August, 2010 | August, 2010 | 2011 | 110 | 7.5M | 1000000 | December, 2016 | 24%
c | Kano | 3rd May 2010 / Federal Tender Journal, This Day and Daily Trust | 5million and above but less than 250million | NCB | 8th July, 2010 | Lakeview Investment Limited | 16th August, 2010 | August, 2009 | 2011 | 120 | 7.5M | 1500000 | December, 2015 | 32%
d | Sokoto | 3rd May 2010 / Federal Tender Journal, This Day and Daily Trust | 5million and above but less than 250million | NCB | 8th July, 2010 | Minderu Global Resources Limited | 16th August, 2010 | August, 2010 | 2011 | 120 | 7.5M | 12145548.41 | December, 2015 | 15% | As an on-going project the total amount paid as at December 2011 include payment made in March, 2011 as part of the provision of 2010 budget financial year.
4 | Establishment of Cultural Village in Gwagwalada FCT, Abuja | 11th August, 2008 Federal Tender Journal, This Day and Daily Trust | 5million and above but less than 250million | NCB | 27th August, 2008 | Dodo Project Consultant Limited | 28th October, 2008 | October, 2008 | 2011 | 250 | 25M | NIL | December, 2015 | 27%
5 | Maintenance/Improvement of National Research Centre on Durbar Traditions in Kaduna, Kaduna State | 3rd May 2010 / Federal Tender Journal, This Day and Daily Trust | 5million and above but less than 250million | NCB | 8th July, 2010 | Siri Peak Link Nigeria Limited | 16th August, 2010 | August, 2010 | 2011 | 150 | 15M | 18274893.21 | December, 2015 | 33% | As an on-going project the total amount paid as at December 2011 include payment made in March, 2011 as part of the provision of 2010 budget financial year.
6 | Maintenance/Improvement of National Research Centre on Masquerade Traditions in Enugu, Enugu State | 3rd May 2010 / Federal Tender Journal, This Day and Daily Trust | 5million and above but less than 250million | NCB | 8th July, 2010 | Obesa Nigeria Limited | 16th August, 2010 | August, 2010 | 2011 | 150 | 10M | 5613433.39 | December, 2015 | 7% | As an on-going project the total amount paid as at December 2011 include payment made in March, 2011 as part of the provision of 2010 budget financial year.
7 | Maintenance/Improvement of National Herbal Garden of Indigenous Plant Species in Getso, Kano State | 3rd May 2010 / Federal Tender Journal, This Day and Daily Trust | 5million and above but less than 250million | NCB | 8th July, 2010 | OAPJ Investment Company Nigeria Limited | 16th August, 2010 | August, 2009 | 2011 | 120 | 5M | 3964650 | December, 2015 | 23%
8 | Maintenance/Improvement of Lagos Crafts Centre | 3rd May 2010 / Federal Tender Journal, This Day and Daily Trust | 5million and above but less than 250million | NCB | 8th July, 2010 | Sand and So Nigeria Limited | 16th August, 2010 | August, 2009 | 2011 | 120 | 10M | 11440529.5 | December, 2015 | 24% | As an on-going project the total amount paid as at December 2011 include payment made in March, 2011 as part of the provision of 2010 budget financial year.
9a | Development of National Herbal Garden of Indigenous Plant Species Project in Garbabi, Taraba State | 3rd May 2010 / Federal Tender Journal, This Day and Daily Trust | 5million and above but less than 250million | NCB | 8th July, 2010 | Legacy Shambe Nigeria Limited | 16th August, 2010 | October, 2008 | 2011 | 250 | 15M | 8126501.39 | December, 2015 | 19%
b | Development of National Herbal Garden of Indigenous Plant Species Project in Orji River, Enugu State | 5th July, 2010 Federal Tender Journal, This Day and Daily Trust | 5million and above but less than 250million | NCB | 24th November, 2010 | Conix International Nigeria Limited | 23rd December, 2010 | January, 2011 | 2011 | 100 | 15M | NIL | December, 2015 | 3%
10 | Purchase of Office Furniture and Equipment | 17th October - 31st October 2011. Council's Notice Board | 2.50million and above but less than 50million | NCB | 21st November, 2011 | Evergreen Interior Home Limited | 16th February, 2012 | 2008 | 2011 | 150 | 5M | 6th March, 2012 4,916,000.00 | December, 2015 | 56%
2040

## FED Civl S.C
PROCUREMENT RECORDS
FEDERAL CIVIL SERVICE COMMISSION
MINISTRY
|  | FINANCIAL YEAR: |  | 2011
| BASIC DATA |  |  |  |  | CONTRACT AWARD | [5 empty] | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | ADVERTISEMENT DATE AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | CONTRACTORS | DATE OF CONTRACT AWARD | DATE OF CONTRACT COMMENCEMENT | CONTRACT PERIOD | CONTRACT VALUE(N) | BUDGETARY PROVISION(N) | AMOUNT PAID AS AT | EXPECTED COMPLETION DATE | % COMPLETION AS AT | REMARKS
1 | Renovation of 32 No Offices | Punch, Daily Trust & Federal Tenders Journal/8/9/11 | MTB | NCB | 2011-10-25 | M/S Debently Ltd | 2011-11-25 | 2011-11-25 | 6 weeks | 43000000.2 |  |  | 2012-01-07 | 90% as at 29/2/2012
2 | Renovation of 45 Nos Toilet | Punch, Daily Trust & Federal Tenders Journal/8/9/11 | MTB | NCB | 2011-10-25 | M/S Debently Ltd | 2011-11-25 | 2011-11-25 | 6 weeks | 36450050 |  |  | 2012-01-07 | 90% as at 29/2/2012
3 | Furnishing of AAPSCOMS Conference Centre (Ground Floor) | Punch, Daily Trust & Federal Tenders Journal/8/9/11 | MTB | NCB | 2011-10-25 | M/S Woods and Frames Ltd. Ltd | 2011-11-25 | 2011-11-25 | 4 weeks | 26953500 |  |  | 2011-12-24 | 90% as at 29/2/2012
4 | Supply and Instalation of Beryer Dynamic MCS-D200 Revolution Conference System | Punch, Daily Trust & Federal Tenders Journal/8/9/11 | MTB | NCB | 2011-10-25 | M/S ACTI-Tech.Ltd | 2011-11-25 | 2011-11-25 | 6 weeks | 45,006.467.56 |  |  | 2012-01-07 | 100% as at 29/2/2012
5 | Furnishing of AAPSCOMS building (First Floor) | Punch, Daily Trust & Federal Tenders Journal/8/9/11 | MTB | NCB | 2011-10-25 | M/S Interior Woodworks Ltd | 2011-11-25 | 2011-11-25 | 4 weeks | 21715023.75 |  |  | 2011-12-24 | 70% as at 29/2/2012
6 | Instalation of ICT Facilities Including On-Line Application Submission and Procesing System | Punch, Daily Trust & Federal Tenders Journal/8/9/11 | MTB | NCB | 2011-10-25 | M/S Dragnet Consortium Ltd | 2011-11-25 | 2011-11-25 | 6 weeks | 85695000 |  |  | 2012-01-07 | 90% as at 29/2/2012
7 | Upscalling the Archiving and File Tracking Management System | Punch, Daily Trust & Federal Tenders Journal/8/9/11 | MTB | NCB | 2011-10-25 | M/S Soft Alliance Ltd | 2011-11-25 | 2011-11-25 | 6 weeks | 25000000 |  |  | 2012-01-07 | 0% as at 29/2/2012 | Contractor refused to collect letter of award
8 | Furnishing of 2 Nos Conference Room | Punch, Daily Trust & Federal Tenders Journal/8/9/11 | MTB | NCB | 2011-10-25 | M/S Katsina Enterprises Ltd | 2011-11-25 | 2011-11-25 | 4 weeks | 19955014 |  |  | 2011-12-24 | 90% as at 29/2/2012
9 | Supply of Office Furniture | Punch, Daily Trust & Federal Tenders Journal/8/9/11 | MTB | NCB | 2011-10-25 | M/S Katsina Enterprises Ltd | 2011-11-25 | 2011-11-25 | 4 weeks | 17229324 |  |  | 2011-12-24 | 90% as at 29/2/2012
10 | Appointment as Consultant on Automation of Workflow Operations and Electronic Management of Documents | Notice Board | MTB | NCB |  | M/S Remi-Chris Computers Ltd | 2011-12-22 | 2011-12-22 |  | 27500000
11 | Renewal appointment as Project Consultant on ICT Paokaging and Supervision |  | MTB | NCB |  | M/S Aflon Ltd | 2011-12-22 | 2011-12-22 |  | 14017500
317515411.95

## UDUTH
USMANU DANFODIYO UNIVERSITY TEACHING HOSPITAL, SOKOTO
PROCUREMENT RECORDS
PROCUREMENT ENTITY (MDA): USMANU DANFODIYO UNIVERSITY TEACHING HOSPITAL, SOKOTO
MINISTRY: FEDERAL MINISTRY OF HEALTH
FINANCIAL YEAR: 2011
|  | BASIC DATA |  |  |  |  | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | ADVERTISEMENT DATE AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | CONTRACTOR | DATE OF CONTRACT AWARD | DATE OF CONTRACT COMMENCEMENT | CONTRACT PERIOD | CONTRACT VALUE (N) | BUDGETARY PROVISION | AMOUNT PAID AS AT 31/12/2011 | EXPECTED COMPLETION DATE | % OF COMPLETION AS AT 31/12/2011 | REMARKS
1 | Structural Underpining of Administrative Block | May & June, 2010 (Journal & Thisday Newspapers) | 250000000 | NCB | July, 2010 | Nasseemen Invets. Ltd., 07080072008 | June, 2010 | July, 2010 | 2010-2012 | 44905820 | 15549348 | 39422667.73 | 2012 | 87.8%
2 | Rehabilitation of Medical Gas Piping | Not-Awarded | 250000000 | Not-Awarded | Not-Awarded | Not-Awarded | Not-Awarded | Not-Awarded | Not-Awarded |  | Not-Awarded | Not-Awarded | Not-Awarded | Not-Awarded
3 | Furnishing of Donated Medical Library | May & June, 2010 (Journal, Dailytrust & Thisday Newspapers) | 50000000 | NCB | July, 2010 | Realone Multiconcepts Ltd., 07080072008 | Apr., 2010 | May, 2010 | 2010-2014 | 35920749 | 2105922 | 10308782.63 | 2013 | 30.4%
4 | Completion of Construction & Furnishing of 30-Bedded Amenity Ward | May & June, 2010 (Journal, Dailytrust & Thisday Newspapers) | 250000000 | NCB | July, 2010 | Yayaya Buhari & Sons Ltd. Te.: 08035754913 | May, 2010 | June, 2010 | 2010-2014 | 85531948 | 56687522 | 83337074.27 | 2013 | 100%
5 | Completion of Construction of Ward & Corridors @ Argungu Rural Health Facility | April & May 2007 (Journal & Thisday Newspaper) | 250000000 | NCB | June, 2007 | Shamnax Multiservices Nig. Ltd. Tel.: 08035042204 | July, 2007 | Aug., 2007 | 2007-2012 | 91748365 | 35628304 | 75872982.59 | 2012 | 82.7%
6 | Rehabilitation of Hospital Road Network | Oct., & Nov., 2011 (Journal, Dailytrust & Thisday Newspapers) | 250000000 | NCB | December, 2011 | Amadzone Links Concept Ltd. Tel.: 08094724045 | Oct., 2011 | Nov., 2011 | 2011-2013 | 66656700 | 20078857 | 20078957 | 2013 | 30.12%
7 | Construction of Brachytheraphy Block | Oct., & Nov., 2011 (Journal & Thisday Newspaper) | 250000000 | NCB | December, 2011 | Coinage Multilinks Ltd. Tel. 08033579381 | Oct., 2011 | Nov., 2011 | 2011-2013 | 65998661.16 | 40628304 | 18357617.56 | 2014 | 27.8%
8 | Construction of 1-Storey Block of 6-Stores, Offices & Conveniences | Oct., & Nov., 2011 (Journal, Dailytrust & Thisday Newspapers) | 250000000 | NCB | December, 2011 | Sisoco Civil Engineering Ltd. Tel. 08035754913 | Oct., 2011 | Nov., 2011 | 2011-2012 | 80660451.16 | 56157913 | 15319725.42 | 2012 | 19%
9 | Construction of Perimeter Wall @ Argungu Rural Health Facility | Not-Awarded | 250000000 | Not-Awarded | Not-Awarded | Not-Awarded | Not-Awarded | Not-Awarded | Not-Awarded |  | Not-Awarded | Not-Awarded | Not-Awarded | Not-Awarded
10 | Rehabilitation of Physiotherapy Department | Oct., & Nov., 2011 (Journal, Dailytrust & Thisday Newspapers) | 250000000 | NCB | December, 2011 | Yahaya Buhari & Sons Ltd. Tel: 08035754913 | Oct., 2011 | Nov., 2011 | 2011 | 12213222 | 12635530 | 12030023.67 | 2011 | 100%
11 | Purchase of 1No. (each) 100KVA (Sound Proof) Perkins Gen. Set & 200KVA Stepdown Transformer | June & July, 2011 (Journal, Dailytrust & Thisday Newspapers) | 50000000 | NCB | July, 2011 | M/s Mkparu & Sons Ltd. Tel.: 08035047239 | May, 2011 | June, 2011 | 2011-2012 | 20143523 | 10143523 | 10132500 | 2012 | 50.3%
503779439.32

## NPS
NIGERIAN PRISONS SERVICE
2010 LIST OF CAPITAL PROJECTS PAID IN 2011
DIRECTORATE OF HEALTH AND WELFARE SERVICES
PROCUREMENT RECORDS
| PROCURING ENTITY (MDA): | NIGERIAN PRISONS SERVICE
| MINISTRY: | MINISTRY OF INTERIOR
| FINANCIAL YEAR: | YEAR 2011
S/N | CONTRACT DESCRIPTION | ADVERT DATE & MEDIA | APPROVAL | PROCUR. | BID | CONTRACTOR | DATE OF CONTRACT AWARD | DATE OF CONTRACT COMMEN- | CONTRACT | CONTRACT | BUDGETARY | AMOUNT | EXPECTED | % OF | REMARKS
|  |  | THRESHOLD | METHOD | OPENING |  |  | CEMENT | PERIOD | VALUE | PROVISION | PAID | COMPLET. | COMPLET. AS AT
[5 empty] | DATE |  |  |  |  | (N) | (N) | AS AT | DATE
1 | Construction of 10 Bed for Prison Staff Barracks Hospital at Kano Central | April, 2010 | Department | Open | May 27, 2010 | Kcinas Link Nig. Ltd. | June, 2010 | June, 2010 | 12 Months | 30052268 | 161049966 | N12m |  | 40%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
2 | Procurement of Barbing Instrument and Relevant Accessories for Prisons Inmates | April, 2010 | Department | Open | May 27, 2010 | Chuks Mekkon Nig. Ltd. | June, 2010 | June, 2010 | 12 Months | 2987615 | 20M | N2,987,615 |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
3 | Procurement/Installation of 1 No CD4 Count Machine and Training of HIV/AIDS Personnel | April, 2010 | Department | Open | May 27, 2010 | Shua & Sons Nig. Ent. | June, 2010 | June, 2010 | 12 Months | 5975645 | 20M | N5,975,645 |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
4 | Construction of One (1) No. Science Lab at Borstal Training Institute, Kaduna | April, 2010 | Department | Open | May 27, 2010 | Mashet Nig. Ent. Ltd. | June, 2010 | June, 2010 | 12 Months | 4981800 | 15861295 | 4,760,624.70K |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
5 | Construction of One (1) No. Science Lab at Borstal Training Institute, Ilorin | April, 2010 | Department | Open | May 27, 2010 | Mashet Nig. Ent. Ltd. | June, 2010 | June, 2010 | 12 Months | 4981800 | 15861295 | 2500000 |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
6 | Equipping the Two Science Labs at Ilorin and Kaduna | April, 2010 | Department | Open | May 27, 2010 | Moscosoa Nig. Ltd. | June, 2010 | June, 2010 | 12 Months | 5836977 | 15861295 | 5836977 |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
7 | Re-engineering and Re-kitting of Port Harcourt Prison Kitchen | April, 2010 | Department | Open | May 27, 2010 | Garcons Nig. Ltd. | June, 2010 | June, 2010 | 12 Months | 7980473 | 55153535 | 4000000 |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
OPERATIONS DIRECTORATE
S/N | CONTRACT DESCRIPTION | ADVERT DATE & MEDIA | APPROVAL | PROCUR. | BID | CONTRACTOR | DATE OF CONTRACT AWARD | DATE OF CONTRACT COMMEN- | CONTRACT |  | BUDGETARY | AMOUNT | EXPECTED | % OF | REMARKS
|  |  | THRESHOLD | METHOD | OPENING |  |  | CEMENT | PERIOD |  | PROVISION | PAID | COMPLET. | COMPLET. AS AT
[5 empty] | DATE | [5 empty] | (N) | AS AT | DATE
1 | Supply/Installation of CCTV & Upgrading to Night Vision IP Cameras With Motion Sensors, 1 No. HP 42U Rack, 1 No. DL380 Proliant Server (G5) All Servers are Rack Mount With Split AC 2KVA Cooling System & Furniture at Ado-Ekiti | April, 2010 | Department | Open | May 27, 2010 | Big-Hill Contract Nig. Ltd. | June, 2010 | June, 2010 | 12 Months | 6440760 | 256301736 | 6423650 |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
2 | Supply/Installation of CCTV & Upgrading to Night Vision IP Cameras With Motion Sensors, 1 No. HP 42U Rack, 1 No. DL380 Proliant Server (G5) All Servers are Rack Mount With Split AC 2KVA Cooling System & Furniture at Zuru Prison | April, 2010 | Department | Open | May 27, 2010 | Big-Hill Contract Nig. Ltd. | June, 2010 | June, 2010 | 12 Months | 6440760 | 256301736 | 6423650 |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
3 | Supply/Installation of CCTV & Upgrading to Night Vision IP Cameras With Motion Sensors, 1 No. HP 42U Rack, 1 No. DL380 Proliant Server (G5) All Servers are Rack Mount With Split AC 2KVA Cooling System & Furniture at Sapele Prison | April, 2010 | Department | Open | May 27, 2010 | Big-Hill Contract Nig. Ltd. | June, 2010 | June, 2010 | 12 Months | 6440760 | 256301736 | 6423650 |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
4 | Supply/Installation of CCTV & Upgrading to Night Vision IP Cameras With Motion Sensors, 1 No. HP 42U Rack, 1 No. DL380 Proliant Server (G5) All Servers are Rack Mount With Split AC 2KVA Cooling System & Furniture at Umuahia Prison | April, 2010 | Department | Open | May 27, 2010 | Mountain Comm. Nig. Ltd. | June, 2010 | June, 2010 | 12 Months | 6440760 | 256301736 | 6423650 |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
5 | Supply/Installation of CCTV & Upgrading to Night Vision IP Cameras With Motion Sensors, 1 No. HP 42U Rack, 1 No. DL380 Proliant Server (G5) All Servers are Rack Mount With Split AC 2KVA Cooling System & Furniture at Gumel Prison | April, 2010 | Department | Open | May 27, 2010 | Mountain Comm. Nig. Ltd. | June, 2010 | June, 2010 | 12 Months | 6440760 | 256301736 | 6423650 |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
6 | Supply/Installation of CCTV & Upgrading to Night Vision IP Cameras With Motion Sensors, 1 No. HP 42U Rack, 1 No. DL380 Proliant Server (G5) All Servers are Rack Mount With Split AC 2KVA Cooling System & Furniture at Akure Prison | April, 2010 | Department | Open | May 27, 2010 | Mountain Comm. Nig. Ltd. | June, 2010 | June, 2010 | 12 Months | 6440760 | 256301736 | 6423650 |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
7 | Supply/Installation of CCTV & Upgrading to Night Vision IP Cameras With Motion Sensors, 1 No. HP 42U Rack, 1 No. DL380 Proliant Server (G5) All Servers are Rack Mount With Split AC 2KVA Cooling System & Furniture at Nsukka Prison | April, 2010 | Department | Open | May 27, 2010 | Mountain Comm. Nig. Ltd. | June, 2010 | June, 2010 | 12 Months | 6440760 | 256301736 | 6423650 |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
8 | Supply/Installation of CCTV & Upgrading to Night Vision IP Cameras With Motion Sensors, 1 No. HP 42U Rack, 1 No. DL380 Proliant Server (G5) All Servers are Rack Mount With Split AC 2KVA Cooling System & Furniture at Jimeta Prison | April, 2010 | Department | Open | May 27, 2010 | Commutronics Nig. Ltd. | June, 2010 | June, 2010 | 12 Months | 6440760 | 256301736 | 6423650 |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
9 | Supply/Installation of CCTV & Upgrading to Night Vision IP Cameras With Motion Sensors, 1 No. HP 42U Rack, 1 No. DL380 Proliant Server (G5) All Servers are Rack Mount With Split AC 2KVA Cooling System & Furniture at Kwale Prison | April, 2010 | Department | Open | May 27, 2010 | Commutronics Nig. Ltd. | June, 2010 | June, 2010 | 12 Months | 6440760 | 256301736 | 6423650 |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
10 | Supply/Installation of CCTV & Upgrading to Night Vision IP Cameras With Motion Sensors, 1 No. HP 42U Rack, 1 No. DL380 Proliant Server (G5) All Servers are Rack Mount With Split AC 2KVA Cooling System & Furniture at Jalingo Prison | April, 2010 | Department | Open | May 27, 2010 | Commutronics Nig. Ltd. | June, 2010 | June, 2010 | 12 Months | 6440760 | 256301736 | 6423650 |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
11 | Supply/Installation of CCTV & Upgrading to Night Vision IP Cameras With Motion Sensors, 1 No. HP 42U Rack, 1 No. DL380 Proliant Server (G5) All Servers are Rack Mount With Split AC 2KVA Cooling System & Furniture at Kebbi New Prison | April, 2010 | Department | Open | May 27, 2010 | Commutronics Nig. Ltd. | June, 2010 | June, 2010 | 12 Months | 6440760 | 256301736 | 6423650 |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
12 | Supply/Installation of CCTV & Upgrading to Night Vision IP Cameras With Motion Sensors, 1 No. HP 42U Rack, 1 No. DL380 Proliant Server (G5) All Servers are Rack Mount With Split AC 2KVA Cooling System & Furniture at Ahoada Prison | April, 2010 | Department | Open | May 27, 2010 | Commutronics Nig. Ltd. | June, 2010 | June, 2010 | 12 Months | 6440760 | 256301736 | 6423650 |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
13 | Supply/Installation of CCTV & Upgrading to Night Vision IP Cameras With Motion Sensors, 1 No. HP 42U Rack, 1 No. DL380 Proliant Server (G5) All Servers are Rack Mount With Split AC 2KVA Cooling System & Furniture at Katsina Prison | April, 2010 | Department | Open | May 27, 2010 | Commutronics Nig. Ltd. | June, 2010 | June, 2010 | 12 Months | 6440760 | 256301736 | 6423650 |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
14 | Supply/Installation of Power Inverter System 25KVA With Deep Cycle 48V DC Batteries (20 Nos.) & Solar Panels 160W (15 Nos.) With Accessories at Jimeta Prison | April, 2010 | Department | Open | May 27, 2010 | NED Investment Co. Nig. Ltd. | June, 2010 | June, 2010 | 12 Months | 9469875 | 300501125 | 9469875 |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
15 | Supply/Installation of Power Inverter System 25KVA With Deep Cycle 48V DC Batteries (20 Nos.) & Solar Panels 160W (15 Nos.) With Accessories at Ogoja Prison | April, 2010 | Department | Open | May 27, 2010 | Temple Global Resources Nig. Ltd. | June, 2010 | June, 2010 | 12 Months | 9469875 | 300501125 | 9469875 |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
DIRECTORATE OF INMATES TRAINING AND PRODUCTIVITY
S/N | CONTRACT DESCRIPTION | ADVERT DATE & MEDIA | APPROVAL | PROCUR. | BID | CONTRACTOR | DATE OF CONTRACT AWARD | DATE OF CONTRACT COMMEN- | CONTRACT |  | BUDGETARY | AMOUNT | EXPECTED | % OF | REMARKS
|  |  | THRESHOLD | METHOD | OPENING |  |  | CEMENT | PERIOD |  | PROVISION | PAID | COMPLET. | COMPLET. AS AT
[5 empty] | DATE | [5 empty] | (N) | AS AT | DATE
1 | Construction of 2 Nos. (2 Units) of Bedroom Flats per Block Semi-Detached Staff Quarters at Bissalam Farm Centre | April, 2010 | Department | Open | May 27, 2010 | Nuelic Tech Ventures | June, 2010 | June, 2010 | 12 Months | 26675415 | 277498167 | N10m |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
2 | Construction of Standard Grain Store at Dukpa MFC | April, 2010 | Department | Open | May 27, 2010 | Willy Azubiks Inv. Nig. Ltd. | June, 2010 | June, 2010 | 12 Months | 7479650 | 277498167 | 3,751,005.18k |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
3 | Construction of 2 Units Cell Block, 3 Offices and Kitchen at Lamingo Agric Project | April, 2010 | Department | Open | May 27, 2010 | Spaac Invest & Construction Ltd. | June, 2010 | June, 2010 | 12 Months | 15772915 | 277498167 | 6338854.73 |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
4 | Construction of 3 Bedroom Bungalow With BQ for Farm Manager at Bissalam F.C | April, 2010 | Department | Open | May 27, 2010 | Candef Nig. Ltd. | June, 2010 | June, 2010 | 12 Months | 14282400 | 277498167 | N4m |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
5 | Construction of a Semi House Carpentry/Machines Workshop to Include 2 Nos. Toilets, Iron Stanchions, Block Work, Ghana Roofing Zinc (Khaki Colour) Ceiling, Plastering, Flooring, Electrical, Plumbing, Iron Mongering, Doors and Windows and Painting Measuring (60x25x10) at Kuje Industrioal Prison Complex | April, 2010 | Department | Open | May 27, 2010 | Emab Associates Ltd. | June, 2010 | June, 2010 | 12 Months | 10968715 | 100525000 | 7,170,797.05k |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
PROCUREMENT UNIT
S/N | CONTRACT DESCRIPTION | ADVERT DATE & MEDIA | APPROVAL | PROCUR. | BID | CONTRACTOR | DATE OF CONTRACT AWARD | DATE OF CONTRACT COMMEN- | CONTRACT |  | BUDGETARY | AMOUNT | EXPECTED | % OF | REMARKS
|  |  | THRESHOLD | METHOD | OPENING |  |  | CEMENT | PERIOD |  | PROVISION | PAID | COMPLET. | COMPLET. AS AT
[5 empty] | DATE | [5 empty] | (N) | AS AT | DATE
1 | Establishment, Renovation/Furnishing of Procurement Offices at Gombe, Jigawa, Nasarawa, Ondo, Osun, Plateau, Taraba, Yobe and Zamfara State Headquarters Offices | April, 2010 | Department | Open | May 27, 2010 | Mubarak Real Solid Ltd. | June, 2010 | June, 2010 | 12 Months | 17975000 | 101624706 | 17975000 |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
DIRECTORATE OF ADMIN
S/N | CONTRACT DESCRIPTION | ADVERT DATE & MEDIA | APPROVAL | PROCUR. | BID | CONTRACTOR | DATE OF CONTRACT AWARD | DATE OF CONTRACT COMMEN- | CONTRACT |  | BUDGETARY | AMOUNT | EXPECTED | % OF | REMARKS
|  |  | THRESHOLD | METHOD | OPENING |  |  | CEMENT | PERIOD |  | PROVISION | PAID | COMPLET. | COMPLET. AS AT
[5 empty] | DATE | [5 empty] | (N) | AS AT | DATE
1 | Re-roofing of Existing Block ‘A With Green Long Span & Partitioning, PTCK Lagos | April, 2010 | Department | Open | May 27, 2010 | Mac-Dave Business Ent. | June, 2010 | June, 2010 | 12 Months | 6743995 | 165775137 | 6549686.32 |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
DIRECTORATE OF WORKS AND LOGISTICS
S/N | CONTRACT DESCRIPTION | ADVERT DATE & MEDIA | APPROVAL | PROCUR. | BID | CONTRACTOR | DATE OF CONTRACT AWARD | DATE OF CONTRACT COMMEN- | CONTRACT |  | BUDGETARY | AMOUNT | EXPECTED | % OF | REMARKS
|  |  | THRESHOLD | METHOD | OPENING |  |  | CEMENT | PERIOD |  | PROVISION | PAID | COMPLET. | COMPLET. AS AT
[5 empty] | DATE | [5 empty] | (N) | AS AT | DATE
1 | Purchase and Installation of 8 Units of Flat Bar Light, Electronic Siren and Communication Equipment to be fixed on 8 Nos. 4x2 S.C Pick-up Van (Petrol Engine) A/C Fitted Mini Black Maria Vehicles at PHQ Abuja ‘Lot A’ | April, 2010 | Department | Open | May 27, 2010 | Peks Engineering Ltd. | June, 2010 | June, 2010 | 12 Months | 5738660 | 211320750 | 5738660 |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
2 | Purchase and Installation of 7 Units of Flat Bar Light, Electronic Siren and Communication Equipment to be fixed on 7 Nos. 4x2 S.C Pick-up Van (Petrol Engine) A/C Fitted Mini Black Maria Vehicles at PHQ Abuja ‘Lot B’ | April, 2010 | Department | Open | May 27, 2010 | Peks Engineering Ltd. | June, 2010 | June, 2010 | 12 Months | 5019235 | 211320750 | 5019235 |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
3 | Construction of Perimeter Fence (700m) at 160 Bed MSP Numan | April, 2010 | Department | Open | May 27, 2010 | Aliyu Assarakawa Nig. Ltd. | June, 2010 | June, 2010 | 12 Months | 55916548.25 | 503929250 | N40m |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
4 | Construction of 2BR Semi Detached Bungalow Block ‘A’ at Prison Academy Ijebu-Igbo | April, 2010 | Department | Open | May 27, 2010 | Welly Holdings Ltd. | June, 2010 | June, 2010 | 12 Months | 14976880 | 612059879 | 14426958 |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
5 | Construction of 2BR Semi Detached Bungalow Block ‘C’ at Prison Academy Ijebu-Igbo | April, 2010 | Department | Open | May 27, 2010 | Laifess Nig. Ltd. | June, 2010 | June, 2010 | 12 Months | 14976880 | 612059879 | 14500083 |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
6 | Construction of 2 Units 2 Bedroom Flats Block ‘E’ at 160 Bed MSP Ilorin | April, 2010 | Department | Open | May 27, 2010 | Ernies Integrated Services Ltd. | June, 2010 | June, 2010 | 12 Months | 14976880 | 612059879 | 7529185.29 |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
7 | Construction of Access Road to Staff Barracks (350m) at !60 Bed MSP Ilorin | April, 2010 | Department | Open | May 27, 2010 | Khafadez Resources Ltd. | June, 2010 | June, 2010 | 12 Months | 21103000 | 119074850 | 9773960 |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
8 | Completion of Access Road (220 x 250m) at Ado-Ekiti Prison | April, 2010 | Department | Open | May 27, 2010 | Hopewell Co. Ltd. | June, 2010 | June, 2010 | 12 Months | 47851105 | 119074850 | 18183419.9 |  | 66%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
9 | Construction of 2 Bedroom Semi Detached Bungalow Block ‘B’ at Ado-Ekiti Prison | April, 2010 | Department | Open | May 27, 2010 | Mut-Bar Cont. Int’l Ltd. | June, 2010 | June, 2010 | 12 Months | 14976880 | 119074850 | N4m |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
10 | Reconstruction of Satellite Prison Composite Block at Zing Satellite Prison | April, 2010 | Department | Open | May 27, 2010 | Brightway Tech. Nig. Ltd. | June, 2010 | June, 2010 | 12 Months | 35825000 | 1525287000 | 30226038 |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
11 | Erosion Control Drainage and Earthwork at Kirikiri Medium and Female Prison | April, 2010 | Department | Open | May 27, 2010 | Etokams Ventures Ltd. | June, 2010 | June, 2010 | 12 Months | 34964840 | 1525287000 | N8m |  | 82%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
12 | Completion of Perimeter Fence at Yola New Prison | April, 2010 | Department | Open | May 27, 2010 | Mados Nig. Ltd. | June, 2010 | June, 2010 | 12 Months | 16478110 | 1525287000 | 3,366,452.75K |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
13 | Reconstruction of Female Cell at Yola New Prison | April, 2010 | Department | Open | May 27, 2010 | Jack Ventures | June, 2010 | June, 2010 | 12 Months | 8661685 | 1525287000 | 7,759,304.39k |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
14 | Construction of Storey Cell Block (212) at Yola New Prison | April, 2010 | Department | Open | May 27, 2010 | Environment Saving Nig. Ltd. | June, 2010 | June, 2010 | 12 Months | 72196155.15 | 1525287000 | 21273707.44 |  | 54%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
15 | Expansion of Perimeter Fence at Shagamu Prison | April, 2010 | Department | Open | May 27, 2010 | Alliance Synergy Power Eng. Ltd. | June, 2010 | June, 2010 | 12 Months | 9922681.75 | 1525287000 | 4127086.35 |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
16 | Extension/Rehabilitation of Admin Block at Owo Prison | April, 2010 | Department | Open | May 27, 2010 | Haward Engineering Ltd. | June, 2010 | June, 2010 | 12 Months | 10540815.35 | 1525287000 | 9,838,544.97k |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
17 | Construction of Perimeter Fence (200m) at Burra Satellite Prison | April, 2010 | Department | Open | May 27, 2010 | Karamchi Agro Services Ltd. | June, 2010 | June, 2010 | 12 Months | 11979870.25 | 1525287000 | 11527732.12 |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
18 | Completion of Female Cell and Wall at Lapai Prison | April, 2010 | Department | Open | May 27, 2010 | Pyril Invest. Ltd. | June, 2010 | June, 2010 | 12 Months | 5957315 | 1525287000 | 5,345,101.12K |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
19 | Fortification of Perimeter Fence at Kontagora Prison | April, 2010 | Department | Open | May 27, 2010 | Hamid & Sons Nig. Ltd. | June, 2010 | June, 2010 | 12 Months | 4985110.1 | 1525287000 | 4,664,702.35k |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
20 | Construction of 3 Units Cell Block/Clinic at Ubiaja Prison | April, 2010 | Department | Open | May 27, 2010 | Wif Services Ltd. | June, 2010 | June, 2010 | 12 Months | 11180225 | 1525287000 | N10m |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
21 | Rehabilitation of ‘A’ Line at Kwale Prison | April, 2010 | Department | Open | May 27, 2010 | Wilghens Nig. Company | June, 2010 | June, 2010 | 12 Months | 5900200 | 1525287000 | 5742433.13 |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
22 | Construction of Perimeter Fence (200m) at Kamba Satellite Prison | April, 2010 | Department | Open | May 27, 2010 | G.G & MP Integ. Concept Ltd. | June, 2010 | June, 2010 | 12 Months | 11969870 | 1525287000 | N10m |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
23 | Construction of Admin Block at Kamba Satellite Prison | April, 2010 | Department | Open | May 27, 2010 | Sound Project Consult Ltd. | June, 2010 | June, 2010 | 12 Months | 6180175 | 1525287000 | 6,003,259.76k |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
24 | Completion of Abandoned 4 Unit Cell Block at Gashua Prison | April, 2010 | Department | Open | May 27, 2010 | Swift Wind Global Services Ltd. | June, 2010 | June, 2010 | 12 Months | 13002612.75 | 1525287000 | N5m |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
25 | Construction of Clinic at Tula Prison | April, 2010 | Department | Open | May 27, 2010 | Esdem Global Resources Ltd. | June, 2010 | June, 2010 | 12 Months | 7868479 | 1525287000 | N5m |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
26 | Construction of Kitchen at Tula Prison | April, 2010 | Department | Open | May 27, 2010 | Ventaja Global Services | June, 2010 | June, 2010 | 12 Months | 5258715 | 1525287000 | 4876027.51 |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
27 | Demolition/Reconstruction of Perimeter Fence (128.7m) at Tula Prison | April, 2010 | Department | Open | May 27, 2010 | A.A.I Giade & Sons Ltd. | June, 2010 | June, 2010 | 12 Months | 16287500 | 1525287000 | 15,555,089.71k |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
28 | Construction of CB 136 to Replace Mud Blocks A & B at Aba Prison | April, 2010 | Department | Open | May 27, 2010 | Mark Toyson Nig. Ltd. | June, 2010 | June, 2010 | 12 Months | 57676050 | 1525287000 | 23685000 |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
29 | Renovation of Cell Blocks A, B & C at Gusau Prison | April, 2010 | Department | Open | May 27, 2010 | Ernies Logistics Serv. Ltd. | June, 2010 | June, 2010 | 12 Months | 9252985 | 1525287000 | 3,952,855.27K |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
30 | Completion of Gatelodge and Connection of Electricity to PHCN at Kaura Namoda | April, 2010 | Department | Open | May 27, 2010 | Ade Atoyebi Nig. Ent. Ltd. | June, 2010 | June, 2010 | 12 Months | 8013115 | 1525287000 | 201,827.88k |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
31 | Construction of 4 Unit Cell Block at Idah Prison | April, 2010 | Department | Open | May 27, 2010 | Sybstec Nig. Ltd. | June, 2010 | June, 2010 | 12 Months | 17721015.95 | 1525287000 | 7000000 |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
32 | Rehabilitation of ‘J’ Block SHQ Staff Barracks, Calabar | April, 2010 | Department | Open | May 27, 2010 | De-Omi Industrial Co. Ltd. | June, 2010 | June, 2010 | 12 Months | 15998875 | 1525287000 | 8,316,503.74k |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
33 | Construction of Satellite Prison Cell Blocks/Admin With Complete Facilities at gassol | April, 2010 | Department | Open | May 27, 2010 | Etokams Ventures Ltd. | June, 2010 | June, 2010 | 12 Months | 35232001.32 | 1525287000 |  |  | 100%
|  | Fed Tender | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
34 | Rehabilitation of SHQ Office/Furnishing of CP Office at Jos | April, 2010 | Department | Open | May 27, 2010 | Etokams Ventures Ltd. | June, 2010 | June, 2010 | 12 Months | 16715112 | 1525287000 |  |  | 100%
|  | Fed Tenders | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
35 | Renovation of SHQ Office at Enugu | April, 2010 | Department | Open | May 27, 2010 | Coudek Nig. Ltd. | June, 2010 | June, 2010 | 12 Months | 15531015 | 1525287000 | N10m |  | 100%
|  | Fed Tenders | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
36 | Electrification of Noncommissioned Officers Quarters at Staff Barracks Kirikiri, Lagos | April, 2010 | Department | Open | May 27, 2010 | Defensive & Protective Concepts Ltd. | June, 2010 | June, 2010 | 12 Months | 5057800 | 1525287000 | 4,920,756.60k |  | 100%
|  | Fed Tenders | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
37 | Fencing/External Works to CP Quarters at Enugu Prison | April, 2010 | Department | Open | May 27, 2010 | Maynuel Integrated Services Ltd. | June, 2010 | June, 2010 | 12 Months | 9352365 | 1525287000 | 9,069,805.88K |  | 100%
|  | Fed Tenders | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
38 | Rehabilitation/Furnishing of ACG’s Quarters at Minna Prison | April, 2010 | Department | Open | May 27, 2010 | Ismaila Rabiu & Co. | June, 2010 | June, 2010 | 12 Months | 9825621.1 | 1525287000 | N9m |  | 100%
|  | Fed Tenders | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
39 | Fencing/Gate House to ACG’s Quarters at Minna Prison | April, 2010 | Department | Open | May 27, 2010 | Remson & Sons Ent. | June, 2010 | June, 2010 | 12 Months | 8478915 | 1525287000 | N5m |  | 100%
|  | Fed Tenders | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
40 | Completion of Abandoned 2 Bedroom Semi Detached Staff Quarters at Aguata | April, 2010 | Department | Open | May 27, 2010 | Capital Ideas Ltd. | June, 2010 | June, 2010 | 12 Months | 4995287 | 1525287000 | 4,829,581.57k |  | 100%
|  | Fed Tenders | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
41 | Completion/Conversion of Storey Building Work Admin Block to Staff Quarters (19 Nos.) to 1 BR Flats and 6 Nos. 1 Room Self Contained Apartment at Kirikiri, Lagos | April, 2010 | Department | Open | May 27, 2010 | Jadubak Nig. Ltd. | June, 2010 | June, 2010 | 12 Months | 51296765 | 1525287000 | 9500000 |  | 100%
|  | Fed Tenders | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
42 | Construction of Admin Block at Maiduguri New Prison | April, 2010 | Department | Open | May 27, 2010 | Eurofrique Supplies Ltd. | June, 2010 | June, 2010 | 12 Months | 25723405 | 299000000 | 7,972,720.64k |  | 100%
|  | Fed Tenders | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
43 | Construction of CB 212 Storey Building at Maiduguri New Prison | April, 2010 | Department | Open | May 27, 2010 | Nitag Consult Ltd. | June, 2010 | June, 2010 | 12 Months | 62,737,88,613.95 | 299000000 | N6m |  | 41%
|  | Fed Tenders | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
44 | Reconstruction of Cell Block ‘A’ at Maiduguri New Prison | April, 2010 | Department | Open | May 27, 2010 | Olabin Global System Ltd. | June, 2010 | June, 2010 | 12 Months | 11965700 | 299000000 | 7,003,758.80K |  | 74%
|  | Fed Tenders | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
45 | Construction of 4 Unit Cell Block at Maiduguri New Prison | April, 2010 | Department | Open | May 27, 2010 | Rhor An Lue | June, 2010 | June, 2010 | 12 Months | 18859745.75 | 299000000 | 3000000 |  | 100%
|  | Fed Tenders | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
46 | Construction of Standard Clinic at Female Prison Kirikiri, Lagos | April, 2010 | Department | Open | May 27, 2010 | Quotas Ventures Ltd. | June, 2010 | June, 2010 | 12 Months | 9266790 | 299000000 | N3m |  | 100%
|  | Fed Tenders | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
47 | Completion of Abandoned SHQ Office Block Dutse, Jigawa State | April, 2010 | Department | Open | May 27, 2010 | Altim Integrated Serv. Ltd. | June, 2010 | June, 2010 | 12 Months | 38201320 | 651065786 | N10m |  | 15%
|  | Fed Tenders | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
48 | Construction of Concrete Pavement With Side Drains and Culverts in and Around the Prison Yard at Yenegoa | April, 2010 | Department | Open | May 27, 2010 | Uofen Nig. Ltd. | June, 2010 | June, 2010 | 12 Months | 51571015.25 | 651065786 | N15m |  | 52%
|  | Fed Tenders | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
49 | Construction of 3 Units 2 Bedroom SHQ Staff Quarters at Enugu | April, 2010 | Department | Open | May 27, 2010 | Maynuel Integrated Serv. Ltd. | June, 2010 | June, 2010 | 12 Months | 23976895 | 651065786 | N3m |  | 39%
|  | Fed Tenders | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
50 | Fencing of SHQ Office at Dutse | April, 2010 | Department | Open | May 27, 2010 | Karamchi Agro Serv. Ltd. | June, 2010 | June, 2010 | 12 Months | 16720500.35 | 651065786 | N8m |  | 100%
|  | Fed Tenders | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
51 | Construction of Composite Farm Centre Admin/Cell Blocks at Ago-Iwoye | April, 2010 | Department | Open | May 27, 2010 | Bomad Nig. Ltd. | June, 2010 | June, 2010 | 12 Months | 37965895 | 250000000 | 20601363.77 |  | 92%
|  | Fed Tenders | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
52 | Construction of Grain Store at FC Ago-Iwoye | April, 2010 | Department | Open | May 27, 2010 | Classical Eng. Co. Ltd. | June, 2010 | June, 2010 | 12 Months | 14984395 | 250000000 | 4,737,241.70k |  | 100%
|  | Fed Tenders | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
53 | Construction of Poultry at FC Ago-Iwoye | April, 2010 | Department | Open | May 27, 2010 | Vintage Emerald Nig. Ltd. | June, 2010 | June, 2010 | 12 Months | 14984395 | 250000000 | 12326554.22 |  | 100%
|  | Fed Tenders | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
54 | Site Clearance/Preparation at Borstal Institution Ogbia | April, 2010 | Department | Open | May 27, 2010 | Agorodi Nig. Ltd. | June, 2010 | June, 2010 | 12 Months | 5478465 | 221000000 | 5330745 |  | 100%
|  | Fed Tenders | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
55 | Conversion of Bucket to Water System Toilets at Nsukka | April, 2010 | Department | Open | May 27, 2010 | Geofield Nig. Ltd. | June, 2010 | June, 2010 | 12 Months | 13348000 | 35084123 | N9m |  | 100%
|  | Fed Tenders | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
56 | Construction of 9 Nos. 2 Bedroom Bungalow at PHQ Abuja | April, 2010 | Department | Open | May 27, 2010 | Decency Associates Ltd. | June, 2010 | June, 2010 | 12 Months | 223399995.8 | 715465890 | N35m |  | 100%
|  | Fed Tenders | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
57 | Supply/Installation of 3 Nos. Station Alternating Current Voltage Stabilizer at PHQ Abuja | April, 2010 | Department | Open | May 27, 2010 | Wincotech Lifts Ltd. | June, 2010 | June, 2010 | 12 Months | 14200135.75 | 719544887 | 13845132.36 |  | 100%
|  | Fed Tenders | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
58 | Construction of 7 Nos. 3 Bedroom Detached Bungalow at PHQ Abuja | April, 2010 | Department | Open | May 27, 2010 | African Sineri Nig. Ltd. | June, 2010 | June, 2010 | 12 Months | 130359898.5 | 719544887 | N55m |  | 100%
|  | Fed Tenders | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
59 | Construction of Clinic at Bida Prison | April, 2010 | Department | Open | May 27, 2010 | Passport properties Constr. Co. Ltd. | June, 2010 | June, 2010 | 12 Months | 6486845 | 1525287000 | 6,023,657.25k |  | 100%
|  | Fed Tenders | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
60 | Construction of Borehole/Water Supply to NOQ Kirikiri (Senior) Including Generator | April, 2010 | Department | Open | May 27, 2010 | Muta Bell Nig. Ltd. | June, 2010 | June, 2010 | 12 Months | 5478465 | 142740100 | 5,311,450.47k |  | 100%
|  | Fed Tenders | Tenders | Competitive
|  | Guardian & | Board
Daily Trust
61 | Construction of Access Road/Park, Reception at Prison Village Abuja |  | Department |  |  | Eagle Construction Ltd. |  |  | 12 Months |  |  | N15m |  | 100%
Tenders
Board
62 | Complimentary Work to Prisons Headquarters Complex/Parade Ground |  | Department |  |  | Eagle Construction Ltd. |  |  | 12 Months |  |  | N5m |  | 100%
Tenders
Board
63 | Water Extension & External Electrification to CGP Resident at Prisons Village Abuja |  | Department |  |  | Eagle Construction Ltd |  |  | 12 Months |  |  | 15,210,358.80k |  | 100%
Tenders
Board
64 | Completion of Shoe Work Factory at Aba |  | Department |  |  | Nco & Co. Ltd. |  |  | 12 Months |  |  | N15m |  | 100%
Tenders
Board
64 | Supply/Installation of Omitted Shoe Making Machine at Aba |  | Department |  |  | Nco & co Ltd. |  |  | 12 Months |  |  | N3m |  | 100%
Tenders
Board
65 | Supply of 8 Nos. Toyota Camry 2.5 Litres Auto at PHQ Abuja |  | Department | Selective |  | Elizade Nig. Ltd. |  |  | 12 Months | 95820000 |  | 95820000 |  | 100%
Tenders
Board
1773998509.37

## works
PROCUREMENT RECORDS
PROCUREMENT ENTITY (MDA) |  | FEDERAL MINISTRYOF WORKS
MINISTRY: |  | FEDERAL MINISTRYOF WORKS
FINANCIAL YEAR |  | 2011 UP-TO FEBRUARY, 2012
| BASIC DATA |  |  |  |  | CONTRACT AWARD | [5 empty] | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | ADVERTISEMENT DATE AND MEDIA | APPROVING THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | CONTRACTOR | DATE OF CONTRACT AWARD | DATE OF CONTRACT COMMENCEMENT | CONTRACT PERIOD | CONTRACT VALUE (N) | BUDGETARY PROVISION (N) | AMOUNT PAID AS AT | EXPECTED COMPLETION DATE | % OF COMPLETION AS AT | REMARKS
1 | Rehabilitation Of Ijebu Igbo-Olomi (Oyo State Border) Road In Ogun State. c/No. 6113 | Daily Trust, ThisDay (June 15, 2010) | FEC | Open Competitive Bidding | 2010-10-20 | M/s A. A. Duhu& Sons Ltd | 13th Sept., 2011 | 2011-09-26 | 13 months | 1381556046.26 | 275000000 | 207233406.74 | 2012-12-25 | Just mobilised to site
2 | Rehabilitation of Ondo-Ore Road in Ondo State. C/No.6115 | Daily Trust, ThisDay (June 15, 2010) | FEC | Open Competitive Bidding | 2010-10-20 | M/s Chrisbrown International limited | 13th Sept., 2011 | 2011-09-26 | 9 months | 1799786661.75 | 375000000 | 269967999.26 | 2012-12-25 | Just mobilised to site
3 | Rehabilitation Of Odo-Oba-Takie-Gambari-Otte Oyo State B/D Along Ibadan – Oyo – Ogbomosho – Ilorin Road 45.3km (Route 20) In Oyo State. C/No. 6116 | Daily Trust, ThisDay (June 15, 2010) | FEC | Open Competitive Bidding | 2010-10-20 | M/s Coduc Nigeria Ltd | 13th Sept., 2011 | 2011-09-26 | 18 months | 2136669265.5 | 800000000 | 320500309.03 | 2012-12-25 | Just mobilised to site
4 | Reconstruction/Rehabilitation of Gbongan - Iwo – Oyo Road in Oyo State. C/No. 6102 | Daily Trust, ThisDay (June 15, 2010) | FEC | Open Competitive Bidding | 2010-10-20 | M/s Kopek Construction Ltd | 13th Sept., 2011 | 2011-09-26 | 24 Months | 6917558164 | 1175000000 | 1037633724.06 | 2012-12-25 | Just mobilised to site
5 | Rehabilitation of Spur from Onitsha – Owerri Road To Okija – Ihembosi - Afor Ukpor – Ebenator – Ezinifite In Nnewi South LGA, In Anambra State. C/No. 6112 | Daily Trust, ThisDay (June 15, 2010) | FEC | Open Competitive Bidding | 2010-10-20 | M/s Ffordiac Engineering Ltd | 13th Sept., 2011 | 2011-09-26 | 9 months | 1786546349.6 | 250000000 | 267981952.44 | 2012-12-25 | Just mobilised to site
6 | Construction of 15.00km Inter – State Road from Aiyegunle, Akoko Edo LGA in Edo State. | Daily Trust, ThisDay (June 15, 2010) | FEC | Open Competitive Bidding | 2010-10-20 | M/s Fame Highway Company Ltd | 13th Sept., 2011 | 2011-09-26 | 12 Months | 1428007350 | 787000000 (37,000,000.00 + 750,000,000.00) | 214201102.5 | 2012-12-25 | Just mobilised to site
7 | Construction of Jalingo – Kuna – Lau Road Section II in Taraba State. C/No. 6119 | Daily Trust, ThisDay (June 15, 2010) | FEC | Open Competitive Bidding | 2010-10-20 | M/s Amitech Interglobal Engineering Limited | 13th Sept., 2011 |  | 16 months | 1430875575.94 | 565605956 | 214631336.39 |  | Just mobilised to site
8 | Re-instatement of Washout and Completion of the Rehabilitation of Sokoto-Ilella Road including Repairs of Usman Danfodio University Road, Sokoto State |  | FEC | Selective |  | M/s Mothercat Lmited | 13th Sept., 2011 |  | 24 months | 2256354874.62 | 23,000,000,000 (Presidential Special Fund) | 338453231.19 |  | On-going
9 | Emergency Reinstatement of Washout/Gully Erosion at KM 127+000 (Auchi) along Okene-Benin Road, Route No. 50(A2) and KM 14+000 along Auchi-Agenebode Road, Edo State, (C/No. 6120) |  | Presidential Anticipatory Approval | Selective/Emergency |  | M/s Setraco Nig. Ltd | 19th Sept., 2011 | 2011-10-03 | 4 months | 1348283765.33 | 23,000,000,000 (Presidential Special Fund) | 715542310.7 | 2012-02-02 | On-going
10 | Emergency Reinstatement of Collapsed Section of Gombe-Potiskum Road, (KM 12) in Gombe State |  | MTB | Selective/Emergency | 2011-09-29 | M/s Triacta Nig. Ltd | 12th October, 2011 | 2011-11-29 | 6 months | 992095650 | 23,000,000,000 (Presidential Special Fund) | 148814347.5 | 2012-05-28 | On-going
11 | Augmentation of Contract No. 5862, for the Dualisation of Abuja-Abaji-Lokoja Road Section I (International Airport Link Road Junction to Sheda Village Junction) |  | FEC | OCB/Direct Procurement for Augmentation |  | M/s Dantata & Sawoe Construction Company (Nigeria) Limited | 28th September, 2011 | 2006-08-03 | 30 months | 17439150440.95 | 1875000000 | 7835067080.1 | 2011-02-02 | 56.61% | Augmentation of N17,439,150,440.95 from N11,227,571,390.41 to revised contract sum of N28,666,721,831.64
12 | Augmentation of Contract No. 5863, for the Dualisation of Abuja-Abaji-Lokoja Road Section II (Sheda VII Junction to Abaji) |  | FEC | OCB/Direct Procurement for Augmentation |  | M/s Reynolds Construction Company Ltd | 28th September, 2011 | 3/8/2006% | 30 months | 21609289700.89 | 2250000000 | 6697081797.59 | 2011-02-02 | 60.74% | Augmentation of N21,609,289,700.89 from N9,627,615,469.94 to revised contract sum of N31,236,905,170.83
13 | Award of Contract for the Construction of Oju/Loko-Oweto Bridge over River Benue to link Loko (Nasarawa State) and Oweto (Benue State) along Traffic Route F.238, (C/No.6108) |  | FEC | Selective Tendering | 2010-09-22 | M/s Reynolds Construction Company Ltd | 19th October, 2011 | 2011-11-30 | 48 months | 36118910405.94 | 2300000000 | 5417836560.89 | 2015-11-29 | Just mobilised to site
14 | Emergency Reinstatement of Collapsed Section of Wukari Mutum Biyu Road, Route No. 90, Taraba State |  | MTB | Selective/Emergency |  | Triacta Nig. Ltd | 25th Novemebr, 2011 | 2011-12-23 | 6 months | 994581787.5 | 2300000000 | 149187268.13 | 2012-06-22 | Just mobilised to site
15 | Reinstatement of Washouts at Km6+750 on the Onitsha Bound Carriageway and two (2Nos) others on the Enugu Bound Carriageway (Km 30+400 and Km35+325-RHS) along Onitsha-Enugu Dual Carriageway in Anambra and Enugu States as additional works to the subsisting contract for the Rehabilitation of Enugu Bound Carriageway of the Onitsha-Enugu Dual Carriageway (Section 1) in Anambra State |  | MTB | Direct Procurement BPP's No Objection |  | Messrs CCC Nigeria Limited | 25th Novemebr, 2011 |  | 4 months | 836596765.81 | 2300000000 | 125489514.87 |  | 25.82% | On-going
16 | Award of Contract No. 6125, for the Repairs of 3rd Mainland Bridge, Phase II Additional Works involving the repairs of 8Nos Expansion Joints, to eliminate noticed super-structure sources of stresses on the already compromised foundation structure of the Bridge in Lagos |  | FEC | Direct Procurement BPP's No Objection |  | Messrs Borini Prono construction Company Limited | 23rd November, 2011 |  | 9 months | 1055477608.16 | 23,000,000,000 (Presidential Special Fund) | 158321641.22 |  | Just mobilised to site
17 | Augmentation of Contract No. 5884 for the Dualisation of Abuja-Abaji-Lokoja Road Section III (Abaji-Koton Karfe) |  | FEC | OCB/Direct Procurement for Augmentation |  | Messrs Bulletine Construction Company Limited | 23rd November, 2011 | 2006-10-12 | 24 Months | 16130125987.32 |  | 4643965196.96 | 2011-04-11 | 35.62% | augmentation of N16,130,125,987.32 from N9,697,207,699.20 to a fixed revised contract sum of N25,827,333,686.52
18 | Augmentation of Contract No. 5885 for the Dualisation of Abuja-Abaji-Lokoja Road Section IV (Koton Karfe to Lokoja) |  | FEC | OCB/Direct Procurement for Augmentation |  | Messrs Gitto Construzioni Generalli (Nigeria) Limited | 23rd November, 2011 | 2006-10-12 | 24 Months | 19100161499.91 |  | 5140396234.23 | 2011-10-11 | 39.92% | Augmentation of N19,100,161,499.91 from N11,987,594,536.93 to a fixed revised contract sum of N31,087,756,036.84
19 | Augmentation of Contract No. 6018 to address Gully Erosion at Chainages 9+700 and 11+400 for the Rehabilitation of 9th Mile-Enugu-Port Harcourt Dual Carriageway in Enugu/Abia States (Contract No. 6018) |  | FEC | Additional works to existing contract BPP's No Objection |  | Messrs CCC Nigeria Limited | 7th December, 2011 | 2009-05-28 | 24 months | 710135133.75 |  | 4098036514.9 | 2011-05-27 | 44.41% | Augmentation of N710,135,133.75 from N8,964,995,597.25 to N9,675,130,731.00
20 | Augmentation of Contract No. 5828 for the Rehabilitation of Obiozora-Uburu-Mpu-Ishiagu-Port Harcourt Expressway Road |  | FEC | Augmentatiion to existing contract |  | Messrs Setraco Nig. Ltd | 7th December, 2011 | 2007-05-14 | 12 months | 390269066.25 |  | 60848576734.88 | 2007-11-10 | 92.89% | Augmentation of N390,269,066.25 from N7,977,074,028.00 to N8,367,343,094.25
21 | Lot 1: Supply, installation and commissioning of Road Digital Bridge Mont Steel (BMS), (18m length x 3m width) Road Weighbridge Equipment complete with all civil and ancillary works at Isiala-Ngwa Toll Plaza along Umuahia-Aba Dual Carriageway in Abia State (Single Station) | Daily Trust, ThisDay (August 18, 2011 | MTB | Open Competitive Bidding | 2011-11-10 | Messrs Chemical and Environmental Engineering Ltd | 25th Novemebr, 2011 | 2012-01-06 | 12 weeks | 77475077.95 | 1350000000 | Nil | 2012-03-16
22 | Lot 2: Supply, installation and commissioning of Road Digital Bridge Mont Steel (BMS), (18m length x 3m width) Road Weighbridge Equipment complete with all civil and ancillary works at Onitsha Toll Plaza along Onitsha-Enugu Dual Carriageway in Anambra State (Single Section) | Daily Trust, ThisDay (August 18, 2011 | MTB | Open Competitive Bidding | 2011-11-10 | Messrs Fastrack Engineering Ltd | 25th Novemebr, 2011 | 2012-01-06 | 12 weeks | 74912506.06 | 1350000000 | Nil | 2012-03-16 | No advanced Payment Yet
23 | Lot 3: Supply, installation and commissioning of Road Digital Bridge Mont Steel (BMS), (18m length x 3m width) Road Weighbridge Equipment complete with all civil and ancillary works at Numan Toll Plaza along Numan-Biu Road in Adamawa State (Single Station) | Daily Trust, ThisDay (August 18, 2011 | MTB | Open Competitive Bidding | 2011-11-10 | Messrs Arkland Construction Ltd | 25th Novemebr, 2011 | 2012-01-06 | 12 weeks | 57537283.73 | 1350000000 | Nil | 2012-03-16 | No advanced Payment Yet
24 | Lot 4: Supply, installation and commissioning of Road Digital Bridge Mont Steel (BMS), (18m length x 3m width) Road Weighbridge Equipment complete with all civil and ancillary works at Ife Toll Plaza along Ilesha-Ibadan Dual Carriageway in Osun State (Single Station | Daily Trust, ThisDay (August 18, 2011 | MTB | Open Competitive Bidding | 2011-11-10 | Messrs Muib Management Consult Ltd | 25th Novemebr, 2011 | 2012-01-06 | 12 weeks | 45640694.97 | 1350000000 | Nil | 2012-03-16 | No advanced Payment Yet
25 | Lot 5: Supply, installation and commissioning of Road Digital Bridge Mont Steel (BMS), (18m length x 3m width) Road Weighbridge Equipment complete with all civil and ancillary works at Enugu Toll Plaza along Port Harcourt-Enugu Dual Carriageway in Enugu State (Single Station) | Daily Trust, ThisDay (August 18, 2011 | MTB | Open Competitive Bidding | 2011-11-10 | Messrs Oil Response Ltd | 25th Novemebr, 2011 | 2012-01-06 | 12 weeks | 78277500 | 1350000000 | Nil | 2012-03-16 | No advanced Payment Yet
26 | Lot 6: Supply, installation and commissioning of Road Digital Bridge Mont Steel (BMS), (18m length x 3m width) Road Weighbridge Equipment complete with all civil and ancillary works at Okene Toll Plaza along Okene-Ajaokuta Dual Carriageway in Kogi State (Single Station) | Daily Trust, ThisDay (August 18, 2011 | MTB | Open Competitive Bidding | 2011-11-10 | Messrs Uhud International Resources Ltd | 25th Novemebr, 2011 | 2012-01-06 | 10 weeks | 57591600.72 | 1350000000 | Nil | 2012-03-16 | No advanced Payment Yet
27 | Lot 7: Supply, installation and commissioning of Road Digital Bridge Mont Steel (BMS), (18m length x 3m width) Road Weighbridge Equipment complete with all civil and ancillary works at Shagamu Toll Plaza along Shagamu-Benin Dual Carriageway in Ogun State (Double Station) | Daily Trust, ThisDay (August 18, 2011 | MTB | Open Competitive Bidding | 2011-11-10 | Messrs Uniglobe Industrial Services Ltd | 25th Novemebr, 2011 | 2012-01-06 | 10 weeks | 93746734.33 | 1350000000 | Nil | 2012-03-16 | No advanced Payment Yet
28 | Lot 8: Supply, installation and commissioning of Road Digital Bridge Mont Steel (BMS), (18m length x 3m width) Road Weighbridge Equipment complete with all civil and ancillary works at Port Harcourt Toll Plaza along Port Harcourt-Aba Dual Carriageway in Rivers State (Single Station) | Daily Trust, ThisDay (August 18, 2011 | MTB | Open Competitive Bidding | 2011-11-10 | Messrs Marblehead Marine and Construction Ltd | 25th Novemebr, 2011 | 2012-01-06 | 16 weeks | 91250000 | 1350000000 | Nil | 2012-03-16 | No advanced Payment Yet
29 | Lot 9: Owode-Onirin Weighbridge along Lagos-Ikorodu Road (Existing Weighbridge Station) in Lagos State (Pavement Maintenance and Weighbridge equipment) | Daily Trust, ThisDay (August 18, 2011 | MTB | Open Competitive Bidding | 2011-11-10 | Messrs Avery Nigeria Ltd | 25th November, 2011 | 2012-01-06 | 12 weeks | 40480503 | 1350000000 | Nil | 2012-03-16 | No advanced Payment Yet
30 | Lot 10: Supply, installation and commissioning of Road Digital Bridge Mont Steel (BMS), (18m length x 3m width) Road Weighbridge Equipment complete with all civil and ancillary works at Makurdi Toll Plaza along Lafia-Makurdi Road in Benue State (Double Station) | Daily Trust, ThisDay (August 18, 2011 | MTB | Open Competitive Bidding | 2011-11-10 | Messrs Uniglobe Industrial Services Ltd | 25th November, 2011 | 2012-01-06 | 12 weeks | 93746734.33 | 1350000000 | Nil | 2012-03-16 | No advanced Payment Yet
31 | Lot 11: Supply, installation and commissioning of Road Digital Bridge Mont Steel (BMS), (18m length x 3m width) Road Weighbridge Equipment complete with all civil and ancillary works at Dankande Toll Plaza along Kano-Kaduna Dual Carriageway in Kaduna State (Double Station) | Daily Trust, ThisDay (August 18, 2011 | MTB | Open Competitive Bidding | 2011-11-10 | Messrs Panel Engineering Consulting Ltd | 25th November, 2011 | 2012-01-06 | 12 weeks | 97834290.99 | 1350000000 | Nil | 2012-03-16 | No advanced Payment Yet
32 | Lot 12: Supply, installation and commissioning of Road Digital Bridge Mont Steel (BMS), (18m length x 3m width) Road Weighbridge Equipment complete with all civil and ancillary works at Makarfi Toll Plaza along Kaduna-Kano Dual Carriageway in Kaduna State (Double Station) | Daily Trust, ThisDay (August 18, 2011 | MTB | Open Competitive Bidding | 2011-11-10 | Messrs Avoland Nigeria Ltd | 25th November, 2011 | 2012-01-06 | 9 weeks | 96526649.6 | 1350000000 | Nil | 2012-03-16 | No advanced Payment Yet
33 | Lot 13: Supply, installation and commissioning of Road Digital Bridge Mont Steel (BMS), (18m length x 3m width) Road Weighbridge Equipment complete with all civil and ancillary works at Jebba Toll Plaza along Ilorin-Mokwa Road in Niger State (Double Station) | Daily Trust, ThisDay (August 18, 2011 | MTB | Open Competitive Bidding | 2011-11-10 | Messrs Dasphino Nigeria Ltd | 25th November, 2011 | 2012-01-06 | 12 weeks | 98606592.26 | 1350000000 | Nil | 2012-03-16 | No advanced Payment Yet
34 | Lot 14: Supply, installation and commissioning of Road Digital Bridge Mont Steel (BMS), (18m length x 3m width) Road Weighbridge Equipment complete with all civil and ancillary works at Sabon Wuse Toll Plaza in Niger State (Double Station) | Daily Trust, ThisDay (August 18, 2011 | MTB | Open Competitive Bidding | 2011-11-10 | Messrs SMV Nigeria Ltd | 25th November, 2011 | 2012-01-06 | 12 weeks | 96336809.06 | 1350000000 | Nil | 2012-03-16 | No advanced Payment Yet
35 | Lot 15: Supply, installation and commissioning of Road Digital Bridge Mont Steel (BMS), (18m length x 3m width) Road Weighbridge Equipment complete with all civil and ancillary works at Dankande Toll Plaza along Kano-Kaduna Dual Carriageway in Kaduna State (Double Station) | Daily Trust, ThisDay (August 18, 2011 | MTB | Open Competitive Bidding | 2011-11-10 | Messrs Dite Limited | 25th November, 2011 | 2012-01-06 | 12 weeks | 106026296.2 | 1350000000 | Nil | 2012-03-16 | No advanced Payment Yet
36 | Lot 16: Supply, installation and commissioning of Road Digital Bridge Mont Steel (BMS), (18m length x 3m width) Road Weighbridge Equipment complete with all civil and ancillary works at Ekidalor Toll Plaza along Benin-Shagamu Dual Carriage (Double Station) | Daily Trust, ThisDay (August 18, 2011 | MTB | Open Competitive Bidding | 2011-11-10 | Messrs Avoland Nigeria Ltd | 25th November, 2011 | 2012-01-06 | 12 weeks | 96526649.6 | 1350000000 | Nil | 2012-03-16 | No advanced Payment Yet
37 | LOT 1: Installation of Streetlights on Yola-Maiduguri Road (Yola End) | ThisDay, Punch, Weekly Trust (November 5, 2011) | MTB | Open Competitive Bidding | 29//11/2011 | Messrs Okosodo Nig. Ltd | 6th December, 2011 | 2012-01-09 | 8 WEEKS | 36200000 | 1350000000 | Nil | 2012-03-05 | No advanced Payment Yet
38 | Lot: 2 Installation of Streetlights at Federal Ministry of Works, Headquarters | ThisDay, Punch, Weekly Trust (November 5, 2011) | MTB | Open Competitive Bidding | 29//11/2011 | Messrs Japovik Nig. Ltd | 6th December, 2011 | 2012-01-09 | 12 WEEKS | 39780000 | 1350000000 | Nil | 2012-04-02 | No advanced Payment Yet
39 | LOT 3: Installation of Streetlights on Abeokuta-Ibadan Road (Abeokuta End) | ThisDay, Punch, Weekly Trust (November 5, 2011) | MTB | Open Competitive Bidding | 29//11/2011 | Messrs Gearnin Ventures Ltd | 6th December, 2011 | 2012-01-09 | 12 WEEKS | 35900000 | 1350000000 | Nil | 2012-04-02 | No advanced Payment Yet
40 | LOT 4: Installation of Streetlights on Ewu-Uromi Irrua | ThisDay, Punch, Weekly Trust (November 5, 2011) | MTB | Open Competitive Bidding | 29//11/2011 | Messrs Amugate Integrated Services Ltd | 6th December, 2011 | 2012-01-09 | 8 WEEKS | 73900000 | 1350000000 | Nil | 2012-03-05 | No advanced Payment Yet
41 | LOT 5: Installation of Streetlights on Kaduna Western Bypass, Kaduna | ThisDay, Punch, Weekly Trust (November 5, 2011) | MTB | Open Competitive Bidding | 29//11/2011 | Messrs Erneco Multi-Systems Int'l Ltd | 6th December, 2011 | 2012-01-09 | 12 WEEKS | 97950000 | 1350000000 | Nil | 2012-04-02 | No advanced Payment Yet
42 | LOT 6: Installation of Streetlights on Sapele-Warri Expressway Benin Interchange, Benin | ThisDay, Punch, Weekly Trust (November 5, 2011) | MTB | Open Competitive Bidding | 29//11/2011 | Messrs Del-Max Investment Ltd | 6th December, 2011 | 2012-01-09 | 8 WEEKS | 74877200 | 1350000000 | Nil | 2012-03-05 | No advanced Payment Yet
43 | LOT 7: Installation of Streetlights along Benin-Ugboko Axis of Benin-Abraka Road, Phase II | ThisDay, Punch, Weekly Trust (November 5, 2011) | MTB | Open Competitive Bidding | 29//11/2011 | Messrs Odighi-Gbeni Nig. Ltd | 6th December, 2011 | 2012-01-09 | 10 WEEKS | 94350000 | 1350000000 | Nil | 2012-03-19 | No advanced Payment Yet
44 | LOT 8: Installation of Streetlights on Gusau-Kaura Namoda Road (Gusau End) | ThisDay, Punch, Weekly Trust (November 5, 2011) | MTB | Open Competitive Bidding | 29//11/2011 | Messrs Medina Integrated Global Ltd | 6th December, 2011 | 2012-01-09 | 12 WEEKS | 72900000 | 1350000000 | Nil | 2012-04-02 | No advanced Payment Yet
45 | LOT 9: Installation of Streetlights on Sokoto-Jega Road (Jega End) | ThisDay, Punch, Weekly Trust (November 5, 2011) | MTB | Open Competitive Bidding | 29//11/2011 | Messrs Enbridge Engineering Nig. Ltd | 6th December, 2011 | 2012-01-09 | 12 WEEKS | 74100000 | 1350000000 | Nil | 2012-04-02 | No advanced Payment Yet
46 | LOT 10: Installation of Streetlights on Agbor-Asaba Expressway (Umunede End) | ThisDay, Punch, Weekly Trust (November 5, 2011) | MTB | Open Competitive Bidding | 29//11/2011 | Messrs Tida International Ltd | 6th December, 2011 | 2012-01-09 | 8 WEEKS | 99618960 | 1350000000 | Nil | 2012-03-05 | No advanced Payment Yet
47 | LOT 11: Installation of Streetlights on Dutse-Hadeja Road (Dutse End) | ThisDay, Punch, Weekly Trust (November 5, 2011) | MTB | Open Competitive Bidding | 29//11/2011 | Messrs Systematic Engineering Ltd | 6th December, 2011 | 2012-01-09 | 8 WEEKS | 54500000 | 1350000000 | Nil | 2012-03-05 | No advanced Payment Yet
48 | LOT 12: Installation of Streetlights on Yola Jalingo Road (Jalingo End) | ThisDay, Punch, Weekly Trust (November 5, 2011) | MTB | Open Competitive Bidding | 29//11/2011 | Messrs Sahnazal Int. Nig. Ltd | 6th December, 2011 | 2012-01-09 | 12 WEEKS | 98900000 | 1350000000 | Nil | 2012-04-02 | No advanced Payment Yet
49 | LOT 13: Installation of Streetlights on Nsukka-Enugu 9th Mile NBL Breweries Road (Enugu End) | ThisDay, Punch, Weekly Trust (November 5, 2011) | MTB | Open Competitive Bidding | 29//11/2011 | Messrs sabtech Towers Nig. Ltd | 6th December, 2011 | 2012-01-09 | 12 WEEKS | 97850000 | 1350000000 | Nil | 2012-04-02 | No advanced Payment Yet
50 | LOT 14: Installation of Streetlights on Owerri –Onitsha Expressway (Owerri End) | ThisDay, Punch, Weekly Trust (November 5, 2011) | MTB | Open Competitive Bidding | 29//11/2011 | Messrs Nassalec (WA) Ltd | 6th December, 2011 | 2012-01-09 | 8 WEEKS | 117400000 | 1350000000 | Nil | 2012-03-05 | No advanced Payment Yet
51 | LOT 15: Installation of Streetlights on Makurdi-Lafia Road (Makurdi End) | ThisDay, Punch, Weekly Trust (November 5, 2011) | MTB | Open Competitive Bidding | 29//11/2011 | Messrs Datlex Nig. Ltd | 6th December, 2011 | 2012-01-09 | 12 WEEKS | 68200000 | 1350000000 | Nil | 2012-04-02 | No advanced Payment Yet
52 | LOT 16: Installation of Streetlights on Lokoja-Ayingba Road (Lokoja End) | ThisDay, Punch, Weekly Trust (November 5, 2011) | MTB | Open Competitive Bidding | 29//11/2011 | Brem Int’l Ltd | 6th December, 2011 | 2012-01-09 | 8WEEKS | 68900000 | 1350000000 | Nil | 2012-03-05 | No advanced Payment Yet
53 | LOT 17: Installation of Streetlights on Gombe Biu Road (Biu End) | ThisDay, Punch, Weekly Trust (November 5, 2011) | MTB | Open Competitive Bidding | 29//11/2011 | Messrs Maduwa Nig. Ltd | 6th December, 2011 | 2012-01-09 | 8 Weeks | 57750000 | 1350000000 | Nil | 2012-03-05 | No advanced Payment Yet
54 | LOT 18: Installation of Streetlights on Mbaise-Umuahia Road (Amuzi Oreikpa End) | ThisDay, Punch, Weekly Trust (November 5, 2011) | MTB | Open Competitive Bidding | 29//11/2011 | Messrs Multi Trust Services Ltd | 6th December, 2011 | 2012-01-09 | 8 WEEKS | 58183650 | 1350000000 | Nil | 2012-03-05 | No advanced Payment Yet
55 | LOT 19: Installation of Streetlights on Ibadan Iseyin Road (Iseyin End) | ThisDay, Punch, Weekly Trust (November 5, 2011) | MTB | Open Competitive Bidding | 29//11/2011 | Messrs Glo Dynamics Const. & Inv. Ltd | 6th December, 2011 | 2012-01-09 | 8 WEEKS | 73900000 | 1350000000 | Nil | 2012-03-05 | No advanced Payment Yet
56 | LOT 20: Installation of Streetlights on Ado-Ekiti-Iyin Road (Ado-Ekiti End) | ThisDay, Punch, Weekly Trust (November 5, 2011) | MTB | Open Competitive Bidding | 29//11/2011 | Messrs Tribego Corporate Ventures Ltd | 6th December, 2011 | 2012-01-09 | 12 WEEKS | 73330237 | 1350000000 | Nil | 2012-04-02 | No advanced Payment Yet
57 | LOT 21: Installation of Streetlights on Akure-Ondo Road (Akure End) | ThisDay, Punch, Weekly Trust (November 5, 2011) | MTB | Open Competitive Bidding | 29//11/2011 | Messrs Knights Consolidated Nig. Ltd | 6th December, 2011 | 2012-01-09 | 12 Weeks | 35885000 | 1350000000 | Nil | 2012-04-02 | No advanced Payment Yet
58 | LOT 22: Installation of Streetlights in South-South and South-East Zones | ThisDay, Punch, Weekly Trust (November 5, 2011) | MTB | Open Competitive Bidding | 29//11/2011 | Messrs Alston Nig. Ltd | 6th December, 2011 | 2012-01-09 | 12 WEEKS | 36700000 | 1350000000 | Nil | 2012-04-02 | No advanced Payment Yet
59 | LOT 23: Installation of Streetlights in North-East and North-West Zones | ThisDay, Punch, Weekly Trust (November 5, 2011) | MTB | Open Competitive Bidding | 29//11/2011 | Messrs Gild Mark Nig. Ltd | 6th December, 2011 | 2012-01-09 | 12 EEKS | 36960000 | 1350000000 | Nil | 2012-04-02 | No advanced Payment Yet
60 | LOT 24: Installation of Streetlights in South West and North Central Zones | ThisDay, Punch, Weekly Trust (November 5, 2011) | MTB | Open Competitive Bidding | 29//11/2011 | Messrs Babsol Nig. Ltd | 6th December, 2011 | 2012-01-09 | 8 WEEKS | 36930000 | 1350000000 | Nil | 2012-03-05 | No advanced Payment Yet
61 | Consultancy Engineering Supervision for the Addendum to the Rehabilitation of Asphalt Overlay of Benin-Shagamu Dual Carriageway(Benin-Ofosu Section, Lagos Bound) Edo State | ThisDay, Punch, Weekly Trust (August 22, 2011) | Hon. Minister | Open Competitive Bidding | 2011-11-10 | M/s Tog Environment & Infrastructure Ltd | 26th August, 2011 | 2011-09-27 | 17 months | 67650833.35 |  | Nil | 2013-02-27 | No advanced Payment Yet
62 | Lot 1: Rehabilitation of Ajaokuta Bridge in Kogi State. | ThisDay, Punch, Weekly Trust (August 22, 2011) | MTB | Open Competitive Bidding | 2011-11-10 | Messrs Zephyrgold International Ltd. | 6th December, 2011 | 2012-01-12 | 4 Months | 30808396.5 | Various allocations for Design & Construction Projects | Nil | 2012-04-12 | On-going
63 | Lot 2: Rehabilitation of Bridge to replace sub-standard Bridge along Ilorin-Igbeti Road, Kwara State. | ThisDay, Punch, Weekly Trust (August 22, 2011) | MTB | Open Competitive Bidding | 2011-11-10 | Messrs EttehAro& Partners | 6th December, 2011 | 2012-01-12 | 4 Months | 50299562.5 | Various allocations for Design & Construction Projects | Nil | 2012-04-12 | On-going
64 | Lot 4: Engineering Design for the construction of Nenwgwe-Oduma, Road Enugu State. | ThisDay, Punch, Weekly Trust (August 22, 2011) | MTB | Open Competitive Bidding | 2011-11-10 | Messrs Global Works Consultants | 6th December, 2011 | 2012-01-12 | 4 Months | 49750093.65 | Various allocations for Design & Construction Projects | Nil | 2012-04-12 | On-going
65 | Lot 5: Engineering Design for the Rehabilitation of Aramoko-Ijero-Iddo-Ekiti Road in Ekiti State. | ThisDay, Punch, Weekly Trust (August 22, 2011) | MTB | Open Competitive Bidding | 2011-11-10 | Messrs Newtec Dev. Co. Ltd | 6th December, 2011 | 2012-01-12 | 6 Months | 83413000 | Various allocations for Design & Construction Projects | Nil | 2012-06-12 | On-going
66 | Lot 6: Engineering Design for the Rehabilitation of Ijebu Ilesha-Ife Road in Osun State. | ThisDay, Punch, Weekly Trust (August 22, 2011) | MTB | Open Competitive Bidding | 2011-11-10 | Messrs Ephraim Ray & Partners | 6th December, 2011 | 2012-01-12 | 4 Months | 31147655.7 | Various allocations for Design & Construction Projects | Nil | 2012-04-12 | On-going
67 | Lot 7: Engineering Design for the Rehabilitation of Abeokuta-Olorunda-Imeko Road in Ogun State. | ThisDay, Punch, Weekly Trust (August 22, 2011) | MTB | Open Competitive Bidding | 2011-11-10 | Messrs Tisco& Partners | 6th December, 2011 | 2012-01-12 | 6 Months | 55159060 | Various allocations for Design & Construction Projects | Nil | 2012-06-12 | On-going
68 | Lot 8: Engineering Design of Iyamoye-Isua Road in Kogi State. | ThisDay, Punch, Weekly Trust (August 22, 2011) | MTB | Open Competitive Bidding | 2011-11-10 | Messrs Unigbe, Bankole& Partners Ltd. | 6th December, 2011 | 2012-01-12 | 4 Months | 48569031 | Various allocations for Design & Construction Projects | Nil | 2012-04-12 | On-going
69 | Lot 9: Engineering Design for the Rehabilitation/Construction of Lafia Bypass Road, Asuba-Shendam to Lafia obi Road in Nasarawa State | ThisDay, Punch, Weekly Trust (August 22, 2011) | MTB | Open Competitive Bidding | 2011-11-10 | Messrs PSE Consultants | 6th December, 2011 | 2012-01-12 | 6 Months | 82541250 | Various allocations for Design & Construction Projects | Nil | 2012-06-12 | On-going
70 | Lot 10: Engineering Design for the Rehabilitation of Asarama-Unyeada-Akardi-Ngo with Bridge in Rivers State. | ThisDay, Punch, Weekly Trust (August 22, 2011) | MTB | Open Competitive Bidding | 2011-11-10 | Messrs Agbo-Mire Engineering Consultancy | 6th December, 2011 | 2012-01-12 | 6 Months | 62207812.5 | Various allocations for Design & Construction Projects | Nil | 2012-06-12 | On-going
71 | Lot 11: Engineering Design for the Rehabilitation of Owu-Ugo-Agdonta Road in Edo State. | ThisDay, Punch, Weekly Trust (August 22, 2011) | MTB | Open Competitive Bidding | 2011-11-10 | Messrs Gayimi Ltd | 6th December, 2011 | 2012-01-12 | 6 Months | 89599950 | Various allocations for Design & Construction Projects | Nil | 2012-06-12 | On-going
72 | Lot 12: Engineering Design of Adin-Agwagune-Ikun Road with Bridge and Spur from IkunUnwanaAfikpo Road in Cross River State. | ThisDay, Punch, Weekly Trust (August 22, 2011) | MTB | Open Competitive Bidding | 2011-11-10 | Messrs Yaroson Partnership Ltd | 6th December, 2011 | 2012-01-12 | 6 Months | 92632500 | Various allocations for Design & Construction Projects | Nil | 2012-06-12 | On-going
73 | Lot 13: Engineering Design for the Rehabilitation/Construction of Abak-IkotIbitan-IkotEkara Road in Akwa Ibom State. | ThisDay, Punch, Weekly Trust (August 22, 2011) | MTB | Open Competitive Bidding | 2011-11-10 | Messrs Vibro Engineering Co. Ltd. | 6th December, 2011 | 2012-01-12 | 6 Months | 89521746.8 | Various allocations for Design & Construction Projects | Nil | 2012-06-12 | On-going
74 | Lot 14: Engineering Design for the Rehabilitation of Birnin Gwari-Dangulbi Road Niger State. | ThisDay, Punch, Weekly Trust (August 22, 2011) | MTB | Open Competitive Bidding | 2011-11-10 | Messrs Zabet Consult Ltd | 6th December, 2011 | 2012-01-12 | 6 Months | 53889000 | Various allocations for Design & Construction Projects | Nil | 2012-06-12 | On-going
75 | Lot 15: The Engineering Design for the Rehabilitation of Birnin Gwari-Funtua Road in Kaduna/Katsina State. | ThisDay, Punch, Weekly Trust (August 22, 2011) | MTB | Open Competitive Bidding | 2011-11-10 | Messrs Panel Engineering Consult Ltd. | 6th December, 2011 | 2012-01-12 | 4 Months | 34517250 | Various allocations for Design & Construction Projects | Nil | 2012-06-12 | On-going
76 | Award of Contract for the Consultancy Services for Updating the Inventory of Federal Highways Nationwide to Facilitate the provision of Road Furniture | ThisDay, Punch, Weekly Trust (August 22, 2011) | MTB | Open Competitive Bidding | 2011-11-10 | Monarchs Int. Proj. Ltd | 6th December, 2011 | 2012-01-12 | 6 WEEKS | 6454350 | 37500000 | Nil | 2012-06-12 | On-going
77 | Manual Traffic Census in South-East Zone | Notice Board (August 19, 2011) | MTB | Open Competitive Bidding | 2011-11-23 | Messrs C. Jekwu Nig. Ltd | 6th December, 2011 | 2012-01-11 | 2 WEEKS | 6193031.25 | 37500000 | Nil | 2012-01-25 | On-going
78 | Manual Traffic Census in South-South Zone | Notice Board (August 19, 2011) | MTB | Open Competitive Bidding | 2011-11-23 | Messrs Gabus Afule Eng. | 6th December, 2011 | 2012-01-11 | 2 WEEKS | 6164103.75 | 37500000 | Nil | 2012-01-25 | On-going
79 | Manual Traffic Census in South-West Zone | Notice Board (August 19, 2011) | MTB | Open Competitive Bidding | 2011-11-23 | Messrs Amotec Eng. Ventures Ltd | 6th December, 2011 | 2012-01-11 | 2 WEEKS | 6216498.75 | 37500000 | Nil | 2012-01-25 | On-going
80 | Manual Traffic Census in North-Central Zone | Notice Board (August 19, 2011) | MTB | Open Competitive Bidding | 2011-11-23 | Messrs Donville Partners Ltd | 6th December, 2011 | 2012-01-11 | 2 WEEKS | 6221538.75 | 37500000 | Nil | 2012-01-25 | On-going
81 | Manual Traffic Census in North-East Zone | Notice Board (August 19, 2011) | MTB | Open Competitive Bidding | 2011-11-23 | Messrs Washo Eng. Services Ltd | 6th December, 2011 | 2012-01-11 | 2 WEEKS | 6207206.25 | 37500000 | Nil | 2012-01-25 | On-going
82 | Manual Traffic Census in North-West Zone | Notice Board (August 19, 2011) | MTB | Open Competitive Bidding | 2011-11-23 | Messrs Shweizer Lugano Nig. Ltd | 6th December, 2011 | 2012-01-11 | 2 WEEKS | 6180903.75 | 37500000 | Nil | 2012-01-25 | On-going
83 | Consultancy Service for the Engineering Supervision of the Construction of Pedestrian Bridge at Ogbia Local Government Area of Bayelsa State | ThisDay, Punch, Weekly Trust (August 22, 2011) | MTB | Open Competitive Bidding | 2011-11-23 | Messrs Hans Nelson Nig. Ltd | 6th December, 2011 | 2012-01-11 | 6 Months | 15000000 | 75000000 | Nil | 2012-06-11 | On-going
139760257843.78

## NMTIO
NATIONAL METALLURGICAL TRAINING INSTITUTE, ONITSHA.
PROCUREMENT RECORD IN 2011.
ON-GOING PROJECT
REPORT AS AT 31ST DECEMBER 2011
PROJECT DETAILS:
Title | Construction of Auditorium
Project Type | Building Work
Location | National Metallurgical Training Institute Permanent Site at Km 6/7 Onitsha – Owerri Road, Onitsha. Anambra State.
Scope of Work | The work involves erection and completion of a 1,500 Student capacity Auditorium of combined Assembly hall, Lecture hall and Theatre in line with NBTE requirement for the production of Low and Middle technical manpower in the Iron & Steel, Oil & Gas and Allied Industries.
Procuring Entity | National Metallurgical Training Institute, Onitsha.
Name of Contractor | Jimbaz (W.A.) Limited.
Contract Sum | N278,022,365.00
Date of Award | 2007-11-26
Duration | 18 Months.
Completion Date(Initial) | 2011-12-31
Realistic Completion Date | 2012-12-31
Advance Payment made | N23,310,000.00
Advance Payment Outstanding | N9,324,000.00
Mode of supervision | Ad-Michaels &Associates
2011 Appropriation | N63,498,030.00
Amount paid in 2011 | N57,218,809
Payment from inception to Dec. 2011 | N212,671,649
Amount required to complete project | N80,399,210
Percentage Completion of Works as at December 2011 ending | 76%
Components Completed. | Sub-structure, Walls & Frames, Mechanical &Electrical piping, roof structure, window & door frames and part of rendering.
Components Outstanding. | Fixture & fittings, Mechanical & Electrical installations, doors, part of rendering, painting & decoration and external works.
VARIATION: N21,307,715.00
PROBLEMS:
(i) Inadequate budgetary provisions in 2008-2011
(ii) Non release in full of 2011 Appropriation.
SUGESTION ON WAYS TO ACCELERATE COMPLETION:
Adequate budgetary provisions to complete project.
NATIONAL METALLURGICAL TRAINING INSTITUTE, ONITSHA.
PROCUREMENT RECORD IN 2011.
REPORT AS AT 31ST DECEMBER, 2011
ON-GOING PROJECT
PROJECT DETAILS:
Title | Completion of Technical Facilities Phase 1A – Contract ‘C’
Project Type | Building / Infrastructural works.
Location | National Metallurgical Training Institute, Permanent site at Km 6/7, Onitsha – Owerri Road, Onitsha, Anambra State.
Scope of Work | The work involved construction of a practical Instruction Workshop, Two lecture halls, covered ways, Roads, Paths, Pavings, Gate and gate house and associated external works.
Procuring Entity | National Metallurgical Training Institute, Onitsha.
Name of Contractor | Brown & Brown Nigeria Limited.
Contract Sum | N107,936,749 (Revised in 2008)
Date of Award | 1992-03-11
Duration | 27 Weeks
Completion Date(Initial) | 2011-12-31
Realistic Completion Date | 2011-12-31
Advance Payment made | N4,801,752.05
Advance Payment Outstanding | Nil
Mode of supervision (in house or list of Consultants) | In-House from 2009.
2011 Appropriation | N7,501,217
Amount paid in 2011 | N.6,453,992.00
Payment from inception to date | N88,983,988.00
Amount Required to complete project | N25,660.000.00
Percentage Completion of Works as at December 2011 ending. | 82%
Components Completed. | Substructure, Structural Steel works, 95% of roofing, Road, Gate & Gate house, Fence floor and Wall finishings and part of Storm water drainage.
Components Outstanding. | Mechanical & Electrical installations, doors, fixture and fittings, Side cladding, and part of Storm Water drainage.
VARIATION: N6,707,239.00
PROBLEMS:
Project suspended in 2000 due to inadequate fund and recommenced in 2009
SUGESTION ON WAYS TO ACCELERATE COMPLETION:
Adequate budgetary provision to complete the project.
REPORT AS AT 31ST DECEMBER, 2011
NATIONAL METALLURGICAL TRAINING INSTITUTE, ONITSHA.
PROCUREMENT RECORD.
ON-GOING PROJECT.
PROJECT DETAILS:
Title | Final account on Technical Facilities Phase 1A – Contract ‘A’
Project Type | Building / Infrastructural works.
Location | National Metallurgical Training Institute Permanent Site at Km 6/7 Onitsha – Owerri Road, Onitsha, Anambra State.
Scope of Work | Construction of a practical Instruction Workshop, Two lecture halls, Lavatory block, covered ways, Site development.
Procuring Entity | National Metallurgical Training Institute, Onitsha.
Name of Contractor | FGN Okoye & sons Limited
Contract Sum | N16,485,877.46 in 1992 (Final account N90,840,030.31 in 2011)
Date of Award | 11TH March, 1992
Duration | 27 Weeks
Completion Date | 29th November, 2000
Realistic Completion Date | 31st December, 2012
Advance Payment made | N9,939,243.50
Advance Payment Outstanding | Nil
Mode of supervision (in house or list of Consultants) | Desgroup Consultants
2011 Appropriation | N31,012,230.00
Amount paid in 2011 | N15,681,396.00
Payment from inception to 2011 | N68,932,360.59
Amount Outstanding | N24,849,966.72
PROGRESS REPORT:
Percentage Completion of Works as at December 2011 ending. | 100%
Components Completed. | Complete erection
Components Outstanding. | Nil
VARIATION: N40,531,362.72
PROBLEMS:
Inadequate budgetary provision from 2000 to date to settle final account claims.
SUGESTION ON WAYS TO ACCELERATE COMPLETION:
Budgetary provision of N40,531,362.72 to roll off the project.
REPORT AS AT 31st DECEMBER, 2011.
NATIONAL METALLURGICAL TRAINING INSTITUTE, ONITSHA.
PROCUREMENT RECORD.
NEW CAPITAL PROJECT IN 2011
PROJECT DETAILS:
Title | Procurement of CNC Lathe Machine
Project Type | Training Machines/Equipment
Location | National Metallurgical Training Institute Permanent Site at Km 6/7 Onitsha – Owerri Road, Onitsha, Anambra State.
Scope of Work | Procurement of one (1) CNC Lathe Machine for Mechanical Engineering Department.
2011 Appropriation | N11,883,115.00
Procuring Entity | National Metallurgical Training Institute, Onitsha.
Procurement Method | Open competitive bidding
Date of Publication and Media | 1.Federal Tenders Journal of 19th September, 2011
2. Daily Champion of 19th September, 2011
3. Nigerian Tribune of 19th September, 2011
List of bidders and Amount | 1.Peter Tiwell Ltd. N11,760,000.00
2. Browny Gold Ltd N11,598,890.50
3. Ugolanson Nig Ltd. N10,550,000.00
4. Eurobase Consult Ltd N4,938,742.20
Contract Awardee | Browny Gold Ltd
Award Value | N11,598,890.00
Date of Award | 31st October, 2011
Duration | 5 Weeks
Realistic Completion Date | 31st March, 2012
Advance Payment | NILL
Percentage Completion of supply as at December, 2011 | 0%
REPORT AS AT 31st DECEMBER, 2011.
NATIONAL METALLURGICAL TRAINING INSTITUTE, ONITSHA.
PROCUREMENT RECORD.
NEW CAPITAL PROJECT IN 2011
PROJECT DETAILS:
Title | Procurement of Pneumatic, coiling and Electrical installation equipment.
Project Type | Training Machines and Equipment
Location | National Metallurgical Training Institute Permanent Site at Km 6/7 Onitsha – Owerri Road, Onitsha, Anambra State.
Scope of Work | Procurement of Pneumatic, coiling and Electrical installation equipment.
2011 Appropriation | N13,503,540.00
Procuring Entity | National Metallurgical Training Institute, Onitsha.
Procurement Method | Open competitive bidding
Date of Publication and Media | 1.Federal Tenders Journal of 19th September, 2011
2. Daily Champion of 19th September, 2011
3. Nigerian Tribune of 19th September, 2011
List of bidders and Amount | 1. Browny Gold Ltd N12,388.829.75
2. Ugolanson Nig Ltd. N12,620,000.00
3. Eurobase Consult Ltd N16,049,520.00
Contract Awardee | Ugolanson Nig Ltd.
Award Value | N12,620,000.00
Date of Award | 31st October, 2011
Duration | 6 Weeks
Realistic Completion Date | 31st March, 2012
Advance Payment | 0
Percentage Completion of supply as at December, 2011 | 0%

## CCB
PROCUREMENT RECORDS
PROCURING ENTITY (MDA): |  | CODE OF CONDUCT BUREAU
MINISTRY: |  | THE PRESIDENCY
FINANCIAL YEAR: |  | 2011
| BASIC DATA |  |  |  |  | CONTRACT AWARD | [5 empty] | CONTRACT IMPLEMENTATION
S/NO | CONTRACT DESCRIPTION | ADVERTISEMENT DATE AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | CONTRACTOR | DATE OF CONTRACT AWARD | DATE OF CONTRACT COMMENCEMENT | CONTRACT PERIOD | CONTRACT VALUE (N) | BUDGETARY PROVISION (N) | AMOUNT (N) PAID AS AT | EXPECTED COMPLETION DATE | % OF COMPLETION AS AT | REMARKS
1 | Renovation and furnishing of Bureau Information Systems and Assets Verification Hall | 2011-10-01 | Ministerial Tenders Board | National Competitive Building | 2011-10-21 | Vikgerald (Nig) Ltd. | 2011-10-01 | 2011-10-01 | 21 days | 7493200 | 8762343 | 7493200 | 2011-10-22 | 100%
Punch
Weekly Trust
Website
Notice Board
2 | Purchase of Licensed Operating Systems EDMS Globox | “ | “ | “ | “ | D-Tech Ltd. | “ | “ | “ | 3268755 | 10362823 | 3268755 | “ | 100%
3 | Production of Assets Declaration Packages | “ | “ | “ | “ | Kureve Int. Ltd. | “ | “ | 28 days | 18952500 | 22019204 | 18952500 | 2011-10-29 | 100%
4 | Printing of Public Enlightenment Materials | “ | “ | “ | “ | Tulip Press | “ | “ | 28 days | 7650000 | 22019204 | 7650000 | 2011-10-29 | 100%
5 | Purchase of 10 Fujitsu Scanners (f1-6140) | “ | “ | “ | “ | D-Tech Ltd. | “ | “ | “ | 6877500 | 256522992 | 6877500 | 2011-10-29 | 100%
6 | Conversion of 500,000 copies of Assets Declaration Forms from Hard Copies to soft copies | “ | “ | “ | “ | CSCS Ltd. | “ | “ | 2 Months | 33000000 | “ | 33000000 | 2011-12-01 | 100%
7 | Printing of Assets Declaration Forms | “ | “ | “ | “ | Winners Global Integrated | “ | “ | 2 Months | 83160000 | “ | 83160000 | “ | 100%
8 | Printing of Assets Verification Guidelines/Forms | “ | “ | “ | “ | Doitwell Global Resources | “ | “ | 28 days | 14200000 | “ | 14200000 | 2011-10-29 | 100%
9 | Production of other Assets Declaration Related documents | “ | “ | “ | “ | Almubet Nig. Ent. | “ | “ | 28 days | 83160000 | “ | 83160000 | “ | 100%
10 | Networking of Assets Declaration Operations in 6 Zones | “ | “ | “ | “ | Piltech Technologies | “ | “ | “ | 30006600 | “ | 30006000 | “ | 100%
11 | Supply of Assets Declaration Boxes, Containers and Power surge Protectors | “ | “ | “ | “ | First Class Computers Ltd. | “ | “ | “ | 6832000 | “ | 6832000 | “ | 100%
12 | Networking of Assets Declaration Department | “ | “ | “ | “ | Data Click Global Tech. | “ | “ | “ | 9420251 | 192662416 | 9420251 | “ | 100%
13 | Purchase of Computers Consumables Accessories and Stationeries | “ | “ | “ | “ | Murahat Int. Ltd. | “ | “ | “ | 52276000 | “ | 52276000 | “ | 100%
14 | Supply of Generators for ICT | “ | ‘ | “ | “ | Gegu Nig. Ltd. | “ | “ | “ | 15022000 | “ | 15022000 | “ | 100%
15 | Furnishing of ICT Rooms | “ | “ | “ | “ | Eugene Ugwu & Bros Ltd. | “ | “ | “ | 21238000 | “ | 21238000 | “ | 100%
16 | Supply of HP Desktop Computers & Printers to State Offices | “ | “ | “ | “ | Ugentex Nig. Ltd. | “ | “ | “ | 30100000 | “ | 30100000 | “ | 100%
17 | Supply of IPAD and Laptop Computers | “ | “ | “ | “ | Ruban Int. Concept Ltd. | “ | “ | “ | 24500000 | “ | 24500000 | “ | 1005
18 | Supply of Office Equipment | “ | “ | “ | “ | Gefsco Nig. Ltd. | “ | ‘ | “ | 29016400 | “ | 29016400 | “ | 100%
19 | Supply of Security Gadgets/Equipments | “ | “ | “ | “ | Protection Best Nig. Ltd | “ | “ | “ | 7600000 | “ | 7600000 | “ | 100%
20 | Purchase of 1 No. Fargo ID Card Machine | “ | “ | “ | “` | Gegu Nig. Ltd. | “ | “ | 2 Weeks | 540000 | 567.313 | 540000 | 2011-10-15 | 100%
21 | Computerization of Central Store | “ | “ | “ | “ | Usworth Ventures | “ | “ | 3 Weeks | 4730500 | 7500860 | 4730500 | 2011-10-22 | 100%
22 | Computerization of Registry | “ | “ | “ | “ | Access Solutions | “ | “ | 3 Weeks | 6248000 | 8582301 | 6248000 | 2011-10-22 | 100%
23 | Training of ICT Staff | “ | “ | “ | “ | Piltech Technologies | “ | “ | “ | 3245000 | 4336931 | 3245000 | “ | 100%
498536706

## TOURISM
PROCUREMENT RECORDS
PROCURING ENTITY (MDA):
MINISTRY:FEDERAL MINISTRY OF TOURISM, CULTURE & NATIONAL ORIENTATION
FINANCIAL YEAR: 2011
| BASIC DATA |  |  |  |  | CONTRACT AWARD | [5 empty] | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | ADVERTISEMENT DATE AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | CONTRACTOR | DATE OF CONTRACT AWARD | DATE OF CONTRACT COMMENCEMENT | CONTRACT PERIOD | CONTRACT VALUE (N) | BUDGETARY PROVISION (N) | AMOUNT PAID AS AT | EXPECTED COMPLETION DATE | % OF COMPLETION AS AT | REMARKS
1 | Supply of House holdItems | N/A | PPC | Shopping | N/A | Nna-Martins & Bros. | 20/6/11 | 21/6/11 | 1 wk | 291931 |  | 291931 | 28/6/11 | 100%
2 | Supply & Installation of Close Circuit TV | N/A | PPC | Shopping | N/A | Keaz Int'l Vent. | 25/8/11 | 26/8/11 | 2 wks | 807465.75 |  | 807465.75 | 2011-08-09 | 100%
3 | Supply of Office Equipt/Furniture | N/A | PPC | Shopping | N/A | Izzy Global Vent. | 18/10/11 | 19/8/11 | 2 wks | 1559600 |  | 1559600 | 2011-02-11 | 100%
4 | Refurbishment of Hon. Minister's office | N/A | MTB | NCB | N/A | Unlimited Visa | 25/10/11 | 26/10/11 | 3 wks | 25009000 |  | 25009000 | 2011-09-11 | 100%
5 | Supply of Project Vehicles | N/A | MTB | Direct Proc. | N/A | Great Source Motors | 25/10/11 | 26/10/11 | 3 wks | 57695000 |  | 57695000 | 2011-09-11 | 100%
6 | Supply of ID Card Machine/Accessories | N/A | PPC | Shopping | N/A | Gerald Nig. | 2011-10-11 | 2011-11-11 | 3 wks | 1830025 |  | 1830025 | 25/11/11 | 100%
7 | Printing of Audit Guide | N/A | PPC | Shopping | N/A | Vicjus Global Ser. Ltd. | 2011-10-11 | 2011-11-11 | 2 wks | 3180000 |  | 3180000 | 18/11/11 | 100%
8 | Printing of Abuja Carnival Prog. | N/A | PPC | Shopping | N/A | Platinum crest Ltd. | 16/11/11 | 17/11/11 | 1 wk | 2720000 |  | 2720000 | 24/11/11 | 100%
9 | Supply of Audio/Photo Production equip. | N/A | PPC | Shopping | N/A | Take note Vent. | 16/12/11 | 17/12/11 | 1wk | 2960000 |  | 2960000 | 24/12/11 | 100%
10 | Supply of Sports Equipment | N/A | PPC | NCB | N/A | Jenuj Entp. Nig. | 30/11/11 | 31/11/11 | 1 wk | 4399600 |  | 4399600 | 2011-07-12 | 100%
11 | Supply Security Equip. | N/A | PPC | NCB | N/A | Brewit Comm Ltd. | 28/12/11 | 29/12/11 | 1 wk | 4164000 |  | 4164000 | 2012-05-01 | 100%
12 | Supply of Library Books & Equipt. | N/A | PPC | NCB | N/A | Aiwanose Nig. Ltd. | 2011-12-12 | 13/12/11 | 2 wks | 4002400 |  | 4002400 | 26/12/11 | 100%
13 | Execution of Art Gallery (Bronze) | N/A | MTB | Direct Proc. | N/A | Orlif Tremo Vent. Ltd. | 2011-12-12 | 13/12/11 | 2 wks | 17650000 |  | 17650000 | 26/12/11 | 100%
14 | Execution of Art Gallery (Metal & Brass) | N/A | PPC | Direct Proc. | N/A | Art Heart Studio | 2011-12-12 | 13/12/11 | 2 wks | 2880000 |  | 2880000 | 26/12/11 | 100%
15 | Execution of Gallery Scrupture | N/A | MTB | Direct Proc. | N/A | Art Abyssinia Ltd. | 2011-12-12 | 13/12/11 | 2 wks | 15940000 |  | 15940000 | 26/12/11 | 100%
16 | Execution of Art Gallery (Painting) | N/A | MTB | Direct Proc. | N/A | Azovic Res. Ltd. | 2011-12-12 | 13/12/11 | 2 wks | 10280000 |  | 10280000 | 26/12/11 | 100%
17 | Execution of Art Gallery Wood Carving Art & Craft | N/A | PPC | Shopping | N/A | Uwa-Usen Nig. Ltd | 2011-12-12 | 13/12/11 | 2 wks | 3120000 |  | 3120000 | 26/12/11 | 100%
18 | Supply of Cultural Books Publicity & Vedio DVD Pictorial Cultural Documentation | N/A | PPC | Shopping | N/A | Salmit Nig. Ltd. | 2011-12-12 | 13/12/11 | 2 wks | 4694600 |  | 4694600 | 26/12/11 | 100%
19 | Supply of Textile | N/A | PPC | Shopping | N/A | Uwa-Usen Nig. Ltd | 2011-12-12 | 13/12/11 | 2 wks | 900000 |  | 900000 | 26/12/11 | 100%
20 | Consultancy/Equipping of e-library | N/A | PPC | Shopping | N/A | Munir Trade & Invest. | 2011-12-12 | 13/12/11 | 2 wks | 3000000 |  | 3000000000 | 26/12/11 | 100%
21 | Equipping of ICT Unit | N/A | PPC | Shopping | N/A | Blemax Res. Ltd. | 2011-12-12 | 13/12/11 | 1 wk | 3000000 |  | 3000000 | 20/12/11 | 100%
22 | Interconnectivity/Computerization of the Ministry | N/A | PPC | NCB | N/A | By- Design Nig. Ltd | 28/12/11 | 29/12/11 | 2 wks | 5000000 |  | 5000000 | 20/12/11 | 100%
23 | Installation of close circuit TV, CCTV, & Dual view high Def DSTV in HM's office | N/A | PPC | NCB | N/A | Keaz Int'l Vent. | 25/8/11 | 26/8/11 | 1 wk | 807465.75 |  | 807465.75 | 2011-02-09 | 100%
24 | Supply of Electrical/Elct Equipt. | N/A | PPC | Shopping | N/A | Tin Soro Nig. Entr. | 20/6/11 | 21/6/11 | 1 wk | 1110920 |  | 1110920 | 28/6/11 | 100%
25 | Supply of House hold Items | N/A | PPC | Shopping | N/A | Nna-Martins & Bros. | 20/6/11 | 21/6/11 | 1 wk | 291931 |  | 291931 | 28/6/11 | 100%
26 | Supply of Computer & Accessories | N/A | PPC | Shopping | N/A | Sanyod Ventures. | 20/6/11 | 21/6/11 | 1 wk | 1432817 |  | 1432817 | 28/6/11 | 100%
27 | Supply of Drugs & First aid materials | N/A | PPC | Shopping | N/A | Chumalac Pharm. Ltd. | 20/6/11 | 21/6/11 | 1 wk | 1432817 |  | 1432817 | 28/6/11 | 100%
28 | Supply of Office Equipt. | N/A | PPC | Shopping | N/A | Princeton Consultant Nig. Ltd. | 20/6/11 | 21/6/11 | 1 wk | 3102400 |  | 3102400 | 28/6/11 | 100%
29 | Supply of office Equipt. | N/A | PPC | Shopping | N/A | Bonmach Enterprises | 20/6/11 | 21/6/11 | 1 wk | 2760000 |  | 2760000 | 28/6/11 | 100%
30 | Installation of software Accounting Transactions, Recording System (ATRRS) | 9th May, 2011, Notice Board | MTB | NCB | N/A | Tech. Global Network Ltd. | 20/6/11 | 21/6/11 | 1 wk | 8131500 |  | 8131500 | 28/6/11 | 100%
31 | Supply of Computer & Computer consumables | N/A | PPC | Shopping | N/A | ND General Computers Nig. Ltd. | 20/6/11 | 21/6/11 | 1 wk | 1072815 |  | 1072815 | 28/6/11 | 100%
32 | Installation of computer software Equipment | N/A | PPC | Shopping | N/A | Tin Soro Nig. Entr. | 23/6/11 | 24/6/11 | 2 wks | 6093000 |  | 6093000 | 2011-08-07 | 100%
33 | Supply of office Equipment | N/A | PPC | Shopping | N/A | U-Val Int'l Co. Nig. Ltd. | 19/7/11 | 20/7/11 | 2 wks | 915945 |  | 915945 | 2011-03-08 | 100%
34 | Office Partitioning | N/A | PPC | Shopping | N/A | Simo Sunrise Engineering | 28/7/11 | 29/7/11 | 2 wks | 431880 |  | 431880 | 2011-12-08 | 100%
35 | Supply of furniture | N/A | PPC | Shopping | N/A | 3-nity fhaze vent. | 28/7/11 | 29/7/11 | 2 wks | 1154000 |  | 1154000 | 2011-12-08 | 100%
36 | Laptop Computers & Bag | N/A | PPC | Shopping | N/A | De-ND Generalnvest. Nig. Ltd. | 2011-08-08 | 2011-09-08 | 1 wk | 1102500 |  | 1102500 | 16/8/11 | 100%
37 | Production of Collar T-Shirt & Caps | N/A | PPC | Shopping | N/A | Shephard Associate Nig. Ltd | 15/9/11 | 16/9/11 | 1 wk | 1491000 |  | 1491000 | 23/9/11 | 100%
38 | Supply of office Equipment | N/A | PPC | Shopping | N/A | Alphyke Vent. | 31/10/11 | 2011-01-11 | 1 wk | 2580000 |  | 2580000 | 2011-08-11 | 100%
39 | Production of Trophies & Plaques | N/A | PPC | Shopping | N/A | Global Award Limited | 16/11/11 | 17/11/11 | 1 wk | 2200000 |  | 2200000 | 24/11/11 | 100%
40 | Production invitation for command performance | N/A | PPC | Shopping | N/A | Mitau Consult Ltd. | 16/11/11 | 17/11/11 | 1 wk | 1980000 |  | 1980000 | 24/11/11 | 100%
41 | Production of Branded gift material | N/A | PPC | Shopping | N/A | Waptech West African Prints Tech Ltd. | 16/11/11 | 17/11/11 | 1 wk | 1905714.28 |  | 1905714.28 | 24/11/11 | 100%
42 | Supply of Branded T-Shirt & round neck for Abuja Carnival | N/A | PPC | NCB | N/A | FPKN Communication Ltd. | 16/11/11 | 17/11/11 | 1 wk | 4279000 |  | 4279000 | 24/11/11 | 100%
43 | Supply of 20 KVA Generator at Taraba State | N/A | PPC | NCB | N/A | Eventum Nig. Ltd. | 21/11/11 | 22/11/11 | 1 wk | 5000000 |  | 5000000 | 29/11/11 | 100%
44 | Construction of Borehole/Overhead tank and sign post at Otukpo Benue State | N/A | PPC | NCB | N/A | Sedabod Resources | 21/11/11 | 22/11/11 | 2 wks | 4550000 |  | 4550000 | 2011-07-12 | 100%
45 | Equipping of Cultural Industry at Gidan Ajia Abuja | N/A | PPC | NCB | N/A | Sasiem Business Ventures | 22/11/11 | 23/11/11 | 2 wks | 4049000 |  | 4049000 | 2011-07-12 | 100%
46 | Equipping the Cultural Industry at Ibi Taraba State | N/A | PPC | Shopping | N/A | Ultrade Limited | 22/11/11 | 23/11/11 | 2 wks | 1498000 |  | 1498000 | 2011-07-12 | 100%
47 | Fencing/Gate House and Sign Post at Abeokuta cultural industry centre | N/A | PPC | NCB | N/A | Zumac C. System | 22/11/11 | 23/11/11 | 2 wks | 4100000 |  | 4100000 | 2011-07-12 | 100%
48 | Supply of Items at Auchi Cultural Centre | N/A | PPC | Shopping | N/A | Venicona Global Concept Ltd. | 22/11/11 | 23/11/11 | 2 wks | 1600000 |  | 1600000 | 2011-07-12 | 100%
49 | Supply of office Equipment | N/A | PPC | Shopping | N/A | Justin Goe Ventures | 15/12/11 | 16/11/11 | 1 wk | 3652000 |  | 3652000 | 23/12/11 | 100%
50 | Supply of office Equipment | N/A | PPC | Shopping | N/A | 3-nity fhaze vent. | 15/12/11 | 16/11/11 | 1 wk | 3699500 |  | 3699500 | 23/12/11 | 100%
51 | Supply of office Equipment | N/A | PPC | Shopping | N/A | Princeton Consultant Nig. Ltd. | 15/12/11 | 16/11/11 | 1 wk | 3102400 |  | 3102400 | 23/12/11 | 100%
52 | Supply of office Items | N/A | PPC | NCB | N/A | Ablam Nig. Entrp. | 15/12/11 | 16/11/11 | 1 wk | 4980000 |  | 4980000 | 23/12/11 | 100%
53 | Supply of office Items | N/A | PPC | NCB | N/A | G-Men Supplies & Supplies Ltd. | 15/12/11 | 16/11/11 | 1 wk | 4950000 |  | 4950000 | 23/12/11 | 100%
54 | Supply of office Equipment | N/A | PPC | NCB | N/A | Ugonnia World Wide Trans. Ltd. | 15/12/11 | 16/11/11 | 1 wk | 4951000 |  | 4951000 | 23/12/11 | 100%
55 | Supply of office Equipment | N/A | PPC | NCB | N/A | Alphyke Vent. | 15/12/11 | 16/11/11 | 1 wk | 4767000 |  | 4767000 | 23/12/11 | 100%
56 | Repair Servicing & replacement of faulty parts of Computers, photocopies, & Printers | N/A | PPC | Shopping | N/A | Anesco Electrical vent. | 15/12/11 | 16/11/11 | 1 wk | 2160000 |  | 2160000 | 23/12/11 | 100%
57 | Supply of office Equipment | N/A | PPC | Shopping | N/A | Geicom Nig. Ltd. | 15/12/11 | 16/11/11 | 1 wk | 2185000 |  | 2185000 | 23/12/11 | 100%
58 | Supply of Library Books | N/A | PPC | Shopping | N/A | Hyffah Invt Ltd. | 15/12/11 | 16/11/11 | 1 wk | 1841500 |  | 1841500 | 23/12/11 | 100%
59 | Supply of office Equipment | N/A | PPC | Shopping | N/A | Bonmach Enterprises | 15/12/11 | 16/11/11 | 1 wk | 2760000 |  | 2760000 | 23/12/11 | 100%
60 | Supply of Basic Law Practice Books | N/A | PPC | Shopping | N/A | Invest. Service Africa Ltd. | 26/12/11 | 27/12/11 | 1 wk | 2100000 |  | 2100000 | 2012-03-01 | 100%
61 | Supply of office Equipment | N/A | PPC | NCB | N/A | Princeton Consultant Nig. Ltd. | 15/12/11 | 16/12/11 | 1 wk | 3855000 |  | 3855000 | 23/12/11 | 100%
62 | Supply of office Equipment | N/A | PPC | NCB | N/A | Tonem Publicity & Publications. Ltd. | 30/12/11 | 31/12/11 | 1 wk | 4997500 |  | 4997500 | 2012-07-01 | 100%
63 | Supply of office Equipment | N/A | PPC | NCB | N/A | Ejichin Tripod Ltd. | 30/12/11 | 31/12/11 | 1 wk | 4900000 |  | 4900000 | 2012-07-01 | 100%
295057226.78

## FHA
FEDERAL HOUSING AUTHORITY
PROCUREMENT TRANSACTION RECORDS FOR PROJECTS ETC. (JANUARY-DECEMBER 2011)
S/NO | DESCRIPTION OF PROJECT PROCURED | BUDGET ALLOCATION FOR THE PROJECT | PROCUREMENT METHOD | DATE PUBLISHED & MEDIA | CONTRACT AWARDEES | DATE & TOTAL VALUE OF AWARDS/ PROCUREMENT | COMPLETION PERIOD | % OF COMPLETION | REMARKS
(A) | (B) | (C) | (D) | (E) | (F) | (G) | (H) | (J) | (K)
1 | CONSTRUCTION OF 19 NOS. 3 - BEDROOM DETACHED BUNGALOWS AT LUGBE ESTATE, ABUJA | PROCEEDS FROM SALE OF FHA HOUSES | RESTRICTED TENDERING | FHA NOTICE BOARD | 6 NUMBER AWARDEES SEE ATTACHED ANNEXURE I | 135016204.95 | 6 WEEKS | 100% | BIDDERS SELECTED FROM THE CONTRACTORS EARLIER PRE-QUALIFIED FOR LUGBE PROJECT IN 2008. NOTE THAT AWARD VALUE IN COLUMN 'G' IS THE TOTAL FOR 6 NOS. CONTRACTS AWARDED.
2 | CONSTRUCTION OF 2 NOS. 3 - BEDROOM DETACHED BUNGALOWS AT LUGBE ESTATE, ABUJA | DITTO | DIRECT LABOUR | NOT APPLICABLE | FHA DIRECT LABOUR UNIT SEE ATTACHED ANNEXURE II | 8531779.72 | 6 WEEKS | 100% | TO BE CONSTRUCTED BY PROJECTS DEPT. THROUGH DIRECT LABOUR. NOTE THAT AWARD VALUE IN COLUMN 'G' IS THE TOTAL FOR 2 NOS. UNITS.
3 | PROVISION OF EXTERNAL ELECTRIFICATION WORKS AT LUGBE ESTATE EXTENSION, ABUJA | DITTO | RESTRICTED TENDERING | FHA NOTICE BOARD | MESSRS ADMAKS NIG. LTD. SEE ATTACHED ANNEXURE III (Page 24) | 12950734.22 | 8 WEEKS | 100% | BIDDER ALREADY HANDLING SIMILAR JOB ON THE LUGBE PROJECT
4 | PROVISION OF EXTERNAL MECHANICAL WORKS AT LUGBE ESTATE EXTENSION, ABUJA | DITTO | RESTRICTED TENDERING | FHA NOTICE BOARD | MESSRS REAL JANE NIG. LTD. SEE ATTACHED ANNEXURE III (Page 24) | 11244156 | 14 WEEKS | 100% | BIDDER ALREADY HANDLING SIMILAR JOB ON THE LUGBE PROJECT
5 | CONSTRUCTION OF ROADS & DRAINS AT LUGBE ESTATE EXTENSION, ABUJA | DITTO | RESTRICTED TENDERING | FHA NOTICE BOARD | MESSRS ST. JAMES NIG. LTD. SEE ATTACHED ANNEXURE III (Page 24) | 28614967.92 | 12 WEEKS | 50% | BIDDER ALREADY HANDLING SIMILAR JOB ON THE LUGBE PROJECT
6 | PROVISION OF 11KVA LINKAGE TO 240 HOUSING UNITS AT LUGBE ESTATE EXTENSION, ABUJA | DITTO | RESTRICTED TENDERING | FHA NOTICE BOARD | MESSRS ADMAKS NIG. LTD. SEE ATTACHED ANNEXURE III (Page 26-29) | 51952657.31 | 16 WEEKS | 100% | BIDDER ALREADY HANDLING SIMILAR JOB ON THE LUGBE PROJECT
7 | RENOVATION OF 3 OLD BARRIERS AND CONSTRUCTION OF 5 NEW ONES AT GWARINPA II ESTATE, ABUJA | DITTO | RESTRICTED TENDERING | FHA NOTICE BOARD | MESSRS MOGRAPH NIGERIA LTD SEE ATTACHED ANNEXURE IV | 3592646.96 | 6 WEEKS | 100% | BIDDER ALREADY HANDLING SIMILAR JOB ON THE GWARINPA II PROJECT
8 | CONSTRUCTION OF 20 NOS. 2 - BEDROOM SEMI-DETACHED BUNGALOWS AT OSHOGBO, OSUN STATE. | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 18TH NOV,2010 | 20 NUMBER. AWARDEES SEE ATTACHED ANNEXURE VA (LOT 1) | 192800542 | 7 WEEKS | 80% | NOTE THAT THE AWARD VALUE IN COLUMN 'G' IS FOR 20NO. BLOCKS
9 | CONSTRUCTION OF 60 NOS. 3 - BEDROOM DETACHED BUNGALOWS AT OSHOGBO, OSUN STATE. | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 18TH NOV,2010 | 60 NUMBER. AWARDEES SEE ATTACHED ANNEXURE VA (LOT 2) | 365344229.4 | 6 WEEKS | 80% | NOTE THAT THE AWARD VALUE IN COLUMN 'G' IS THE TOTAL FOR 60NO. BLOCKS AWARDED
10 | CONSTRUCTION OF ROADS & DRAINS AT OSHOGBO,OSUN STATE. | PROCEEDS FROM SALE OF FHA HOUSES | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 18TH NOV,2010 | MESSRS ADEYEMI SKY NIGERIA LTD SEE ATTACHED ANNEXURE VA (LOT 3) | 158168137.05 | 24 WEEKS | 45%
11 | PROVISION OF EXTERNAL ELECTRIFICATION WORKS AT OSHOGBO, OSUN STATE | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 18TH NOV,2010 | MESSRS LAKEBATO VENTURES LTD SEE ATTACHED ANNEXURE VA (LOT 4) | 50.973,268.50 | 18 WEEKS | 90%
12 | CONSTRUCTION OF INDEPENDENT WATER SUPPLY & PROVISION OF EXTERNAL MECHANICAL WORKS AT OSHOGBO, OSUN STATE | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 18TH NOV,2010 | MESSRS LABOL INDUSTRIES LTD SEE ATTACHED ANNEXURE VA (LOT 5) | 90417246.15 | 12 WEEKS | 45%
13 | CONSTRUCTION OF 18 NOS. 2 - BEDROOM SEMI-DETACHED BUNGALOWS AT ODUKPANI, CROSS RIVER STATE. | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 18TH NOV,2010 | 18 NUMBER. AWARDEES SEE ATTACHED ANNEXURE VA (LOT 12) | 223305528.6 | 7 WEEKS | 65% | NOTE THAT THE AWARD VALUE IN COLUMN 'G' IS THE TOTAL FOR 18NO. BLOCKS AWARDED
14 | CONSTRUCTION OF 50 NOS. 3 - BEDROOM DETACHED BUNGALOWS AT ODUKPANI, CROSS RIVER STATE. | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 18TH NOV,2010 | 25 NUMBER. AWARDEES SEE ATTACHED ANNEXURE VA (LOT 13) | 383725650 | 6 WEEKS | 65% | NOTE THAT THE AWARD VALUE IN COLUMN 'G' IS THE TOTAL FOR 50NO. BLOCKS AWARDED
15 | CONSTRUCTION OF ROADS & DRAINS AT ODUKPANI,CROSS RIVER STATE. | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 18TH NOV,2010 | MESSRS DEMIKE MARTINS NIG. LTD SEE ATTACHED ANNEXURE VA (LOT 14) | 111383551.13 | 24 WEEKS | 15%
16 | PROVISION OF EXTERNAL ELECTRIFICATION WORKS AT ODUKPANI, CROSS RIVER STATE | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 18TH NOV,2010 | MESSRS 21ST CENTURY GLOBAL SERVICES LTD SEE ATTACHED ANNEXURE VA (LOT 15) | 33394989.49 | 12 WEEKS | 0%
17 | CONSTRUCTION OF INDEPENDENT WATER SUPPLY & PROVISION OF EXTERNAL MECHANICAL WORKS AT ODUKPANI, CROSS RIVER STATE | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 18TH NOV,2010 | MESSRS A.A.OPARA & SONS LTD SEE ATTACHED ANNEXURE VA (LOT 16) | 78312788.4 | 12 WEEKS | 10%
18 | REHABILITATION OF ROADS & DRAINS AT NORTH BANK ESTATE, MARKUDI, BENUE STATE | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 18TH NOV,2010 | MESSRS SECURA INV. LTD SEE ATTACHED ANNEXURE VA (LOT 17) | 197439909.71 | 24 WEEKS | 40%
19 | REHABILITATION OF 4TH AVENUE ROADS IN FESTAC TOWN, PHASE I, LAGOS STATE. | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 18TH NOV,2010 | MESSRS DANZINGER NIGERIA LTD SEE ATTACHED ANNEXURE VA (LOT 18) | 50174772.82 | 12 WEEKS | 70%
20 | REHABILITATION OF 5TH AVENUE ROADS IN IPAJA ESTATE, LAGOS STATE. | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 18TH NOV,2010 | MESSRS BAM-DARLEY NIG LTD SEE ATTACHED ANNEXURE VA (LOT 19) | 67500962.83 | 12 WEEKS | 40%
21 | CONSTRUCTION OF ROADS & DRAINS AT UPPER IRETE EXTENSION ESTATE, OWERRI, IMO STATE. | PROCEEDS FROM SALE OF FHA HOUSES | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 18TH NOV,2010 | MESSRS TADAM ENGINEERING SERVICES LTD SEE ATTACHED ANNEXURE VA (LOT 20) | 27757782.36 | 12 WEEKS | 25%
22 | LANDSCAPING OF SURROUNDS OF 3NO. BLOCKS OF FLATS AT GWARINPA II ESTATE | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 18TH NOV,2010 | MESSRS HILLYPAT NIG LTD SEE ATTACHED ANNEXURE VB (LOT 4, RE-ADVERTISED) | 20273368.5 | 12 WEEKS | 95%
23 | CONSTRUCTION OF INDEPENDENT WATER SUPPLY & PROVISION OF EXTERNAL MECHANICAL WORKS AT GONIN-GORA ESTATE, KADUNA STATE | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 18TH NOV,2010 | MESSRS MOGRAPH NIGERIA LTD SEE ATTACHED ANNEXURE VB (LOT 23, RE-ADVERTISED) | 106152796.8 | 12 WEEKS | 100%
24 | REHABILITATION OF ROADS & DRAINS ON SELECTED COMMISSIONING ROUTE IN GWARINPA II, ESTATE. ABUJA | DITTO | RESTRICTED TENDERING | FHA NOTICE BOARD | MESSRS MOGRAPH NIGERIA LTD SEE ATTACHED ANNEXURE VI | 3522523.4 | 2 WEEKS | 100% | BIDDER ALREADY HANDLING SIMILAR JOB ON THE GWARINPA PROJECT
25 | RENOVATION OF GONIN-GORA SITE/PROJECT OFFICE AT GONIN-GORA ESTATE, KADUNA STATE | DITTO | RESTRICTED TENDERING | FHA NOTICE BOARD | MESSRS 21ST CENTURY GLOBAL SERVICES LTD SEE ATTACHED ANNEXURE VII | 4999944.86 | 5 WEEKS | 100% | BIDDER ALREADY HANDLING SIMILAR JOB ON GONIN-GORA ESTATE PROJECT
26 | CLEARING, GRADING AND LEVELING OF FHA LAND AT ODUKPANI, CROSS RIVER STATE | DITTO | RESTRICTED TENDERING | FHA NOTICE BOARD | MESSRS JADCOM LTD SEE ATTACHED ANNEXURE VIII | 14246925 | 2 WEEKS | 85%
27 | PROVISION OF EXTERNAL ELECTRIFICATION WORKS FOR 3NO. BLOCK OF FLATS AT GWARINPA II, ESTATE | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 18TH NOV,2010 | MESSRS CHRISTUDY NIG. LTD SEE ATTACHED ANNEXURE VB (LOT 5, RE-ADVERTISED) | 4309882.5 | 7 WEEKS | 85%
28 | CONSTRUCTION OF 2 NOS. 2 - BEDROOM SEMI-DETACHED BUNGALOWS AT GONIN GORA ESTATE, KADUNA STATE. | DITTO | RESTRICTED TENDERING | FHA NOTICE BOARD | 2NO NUMBER. AWARDEES(M/S VISION POINT & M/S GASCO INV. CO LTD) SEE ATTACHED ANNEXURE IX | 20695876.52 | 7 WEEKS | 100% | BIDDERS SELECTED FROM THE CONTRACTORS EARLIER PRE-QUALIFIED FOR GONIN-GORA HOUSING PROJECT. NOTE THAT THE AWARD VALUE IN COLUMN 'G' IS THE TOTAL FOR 2 NOS. CONTRACTS AWARDED.
29 | CONSTRUCTION OF 9 NOS. 3- BEDROOM SEMI-DETACHED BUNGALOWS AT GONIN GORA ESTATE, KADUNA STATE. | DITTO | RESTRICTED TENDERING | FHA NOTICE BOARD | 9NO NUMBER. AWARDEES SEE ATTACHED ANNEXURE IX | 60738797.61 | 6 WEEKS | 100% | BIDDERS SELECTED FROM THE CONTRACTORS EARLIER PRE-QUALIFIED FOR GONIN-GORA HOUSING PROJECT. NOTE THAT THE AWARD VALUE IN COLUMN 'G' IS THE TOTAL FOR 9 NOS. CONTRACTS AWARDED.
30 | DEMOLITION OF ALL DEFECTIVE NHP BUILDING STRUCTURES, LEVELING & CARTING AWAY AT FHA SITE, OSHOGBO, OSUN STATE. | DITTO | RESTRICTED TENDERING | FHA NOTICE BOARD | MESSRS ADEYEMI SKY NIGERIA LTD SEE ATTACHED ANNEXURE X | 4630972.5 | 2 WEEKS | 100% | BIDDER SELECTED FROM THE EXISTING CONTRACTORS EARLIER PRE-QUALIFIED ON THE OSHOGBO PROJECT
31 | CLEARING, GRADING AND LEVELING OF FHA LAND AT OSHOGBO, OSUN STATE | DITTO | RESTRICTED TENDERING | FHA NOTICE BOARD | MESSRS ADEYEMI SKY NIGERIA LTD SEE ATTACHED ANNEXURE XI | 4851000 | 2 WEEKS | 100% | BIDDER SELECTED FROM THE EXISTING CONTRACTORS EARLIER PRE-QUALIFIED ON THE OSHOGBO PROJECT
32 | CLEARING, GRADING AND LEVELING OF FHA LAND AT YENAGOA, BAYELSA STATE | PROCEEDS FROM SALE OF FHA HOUSES | RESTRICTED TENDERING | FHA NOTICE BOARD | MESSRS KINAMICS NIG. LTD. SEE ATTACHED ANNEXURE XII | 29452500 | 2 WEEKS | 50% | BIDDER SELECTED FROM THE EXISTING CONTRACTORS EARLIER PRE-QUALIFIED ON THE BAYELSA PROJECT
33 | PROVISION OF WATER DISTRIBUTION NETWORK AT CENTRAL BUSINESS DISTRICT, GWARINPA II ESTATE,ABUJA, FCT. | DITTO | RESTRICTED TENDERING | FHA NOTICE BOARD | MESSRS REAL JANE NIG LTD. SEE ATTACHED ANNEXURE XIII | 54251851.5 | 5 WEEKS | 100% | BIDDER ALREADY HANDLING SIMILAR WORK ON THE GWARINPA II PROJECT
34 | PROVISION OF EXTERNAL ELECTRIFICATION WORKS AT CENTRAL BUSINESS DISTRICT, GWARINPA II ESTATE,ABUJA, FCT. | DITTO | RESTRICTED TENDERING | FHA NOTICE BOARD | MESSRS C.ROLLINS INVESTMENT CO. LTD. SEE ATTACHED ANNEXURE XIII | 41873835.5 | 12 WEEKS | 100% | BIDDER ALREADY HANDLING SIMILAR WORK ON THE GWARINPA II PROJECT
35 | CONSTRUCTION OF 2 NOS. 3 - BEDROOM DETACHED BUNGALOWS AT LUGBE ESTATE, ABUJA | DITTO | RESTRICTED TENDERING | FHA NOTICE BOARD | 2 NUMBER AWARDEES SEE ATTACHED ANNEXURE XIV | 14212232.1 | 6 WEEKS | 100% | BIDDERS SELECTED FROM THE CONTRACTORS EARLIER PRE-QUALIFIED FOR LUGBE PROJECT IN 2008. NOTE THAT AWARD VALUE IN COLUMN 'G' IS THE TOTAL FOR 2 NOS. CONTRACTS AWARDED.
36 | CONSTRUCTION OF 4 NOS. 3 - BEDROOM DETACHED BUNGALOWS AT LUGBE ESTATE, ABUJA | DITTO | RESTRICTED TENDERING | FHA NOTICE BOARD | 4 NUMBER AWARDEES SEE ATTACHED ANNEXURE XIV | 32578693.4 | 6 WEEKS | 100% | BIDDERS SELECTED FROM THE CONTRACTORS EARLIER PRE-QUALIFIED FOR LUGBE PROJECT IN 2008. NOTE THAT AWARD VALUE IN COLUMN 'G' IS THE TOTAL FOR 4 NOS. CONTRACTS AWARDED.
37 | CLEARING OF WEEDS, TREES, LANDSCAPING AND BEAUTIFICATION OF NORTH BANK ESTATE, MAKURDI,BENUE STATE. | DITTO | RESTRICTED TENDERING | FHA NOTICE BOARD | MESSRS ENVIRONMENTAL & CLIMATE CHANGE SEE ATTACHED ANNEXURE XV | 3982000 | 8 WEEKS | 99%
38 | CONSTRUCTION OF 2 NOS. 2 - BEDROOM BLOCK OF FLATS AT YENAGOA,BAYELSA STATE. | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 18TH NOV,2010 | 2 NUMBER AWARDEES M/S LIVOK & M/S NESTIBEX OIL AND GAS SEE ATTACHED ANNEXURE XVI (LOT 6) | 122118238 | 42 WEEKS | 5% | NOTE THAT AWARD VALUE IN COLUMN 'G' IS THE TOTAL FOR 2 NOS. CONTRACTS AWARDED.
39 | CONSTRUCTION OF 20 NOS. 4 - BEDROOM DETACHED DUPLEX AT YENAGOA,BAYELSA STATE. | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 18TH NOV,2010 | 20 NUMBER AWARDEES SEE ATTACHED ANNEXURE XVI (LOT 7) | 672474380 | 38 WEEKS | 5% | NOTE THAT AWARD VALUE IN COLUMN 'G' IS THE TOTAL FOR 20 NOS. CONTRACTS AWARDED.
40 | CONSTRUCTION OF 16 NOS. 3 - BEDROOM TERRACED DUPLEX AT YENAGOA,BAYELSA STATE. | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 18TH NOV,2010 | 16 NUMBER AWARDEES SEE ATTACHED ANNEXURE XVI (LOT 8) | 1290446080 | 42 WEEKS | 5% | NOTE THAT AWARD VALUE IN COLUMN 'G' IS THE TOTAL FOR 16 NOS. CONTRACTS AWARDED.
41 | PROVISION OF EXTERNAL ELECTRIFICATION WORKS AT YENAGOA, BAYELSA STATE. | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 18TH NOV,2010 | M/S NEXEN NIGERIA LTD SEE ATTACHED ANNEXURE XVI (LOT 10) | 71527475.25 | 24 WEEKS | 0%
42 | CONSTRUCTION OF INDEPENDENT WATER STATION & PROVISION OF EXTERNAL MECHANICAL WORKS AT YENAGOA, BAYELSA STATE. | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 18TH NOV,2010 | MESSRS LABOL INDUSTRIES LTD SEE ATTACHED ANNEXURE XVI (LOT 11) | 82713650.25 | 24 WEEKS | 0%
43 | CONSTRUCTION OF 14NOS. 3 - BEDROOM BLOCK OF FLATS AT AWKA, ANAMBRA STATE. | PROCEEDS FROM SALE OF FHA HOUSES | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 27TH JUNE,2011 | 14 NUMBER AWARDEES SEE ATTACHED ANNEXURE XVII (LOT 1) | 1060330271 | 46 WEEKS | 0% | NOTE THAT AWARD VALUE IN COLUMN 'G' IS THE TOTAL FOR 14 NOS. CONTRACTS AWARDED.
44 | CONSTRUCTION OF 10NOS. 4 - BEDROOM SEMI-DETACHED DUPLEX AT AWKA, ANAMBRA STATE. | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 27TH JUNE,2011 | 10 NUMBER AWARDEES SEE ATTACHED ANNEXURE XVII (LOT 2) | 421528118 | 36 WEEKS | 0% | NOTE THAT AWARD VALUE IN COLUMN 'G' IS THE TOTAL FOR 10 NOS. CONTRACTS AWARDED.
45 | CONSTRUCTION OF ROADS & DRAINS AT AWKA, ANAMBRA STATE. | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 27TH JUNE,2011 | MESSRS MASTER HOLDINGS NIGERIA LTD SEE ATTACHED ANNEXURE XVII (LOT 3) | 162051254.47 | 36 WEEKS | 0%
46 | PROVISION OF EXTERNAL ELECTRIFICATION WORKS AT AWKA, ANAMBRA STATE. | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 27TH JUNE,2011 | M/S MAKS INDUSTRIES LTD. SEE ATTACHED ANNEXURE XVII (LOT 4) | 73326664.95 | 20 WEEKS | 0%
47 | CONSTRUCTION OF INDEPENDENT WATER SUPPLY & PROVISION OF EXTERNAL MECHANICAL WORKS AT AWKA, ANAMBRA STATE. | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 27TH JUNE,2011 | M/S NEXEN NIGERIA LTD SEE ATTACHED ANNEXURE XVII (LOT 5) | 79596158.73 | 12 WEEKS | 0%
48 | CONSTRUCTION OF 15 NOS. 2 - BEDROOM SEMI-DETACHED BUNGALOWS AT MAKURDI, BENUE STATE. | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 27TH JUNE,2011 | 15NO NUMBER. AWARDEES SEE ATTACHED ANNEXURE XVII (LOT 6) | 175896831 | 8 WEEKS | 0% | NOTE THAT AWARD VALUE IN COLUMN 'G' IS THE TOTAL FOR 15 NOS. CONTRACTS AWARDED.
49 | CONSTRUCTION OF 50 NOS. 3 - BEDROOM DETACHED BUNGALOWS AT MAKURDI, BENUE STATE. | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 27TH JUNE,2011 | 50 NUMBER. AWARDEES SEE ATTACHED ANNEXURE XVII (LOT 7) | 330363550 | 6 WEEKS | 0% | NOTE THAT AWARD VALUE IN COLUMN 'G' IS THE TOTAL FOR 50 NOS. CONTRACTS AWARDED.
50 | CONSTRUCTION OF ROADS & DRAINS AT MAKURDI, BENUE STATE. | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 27TH JUNE,2011 | MESSRS SECURA INVESTMENT LTD SEE ATTACHED ANNEXURE XVII (LOT 8) | 135634947.18 | 36 WEEKS | 0%
51 | PROVISION OF EXTERNAL ELECTRIFICATION WORKS AT MAKURDI, BENUE STATE. | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 27TH JUNE,2011 | M/S CCII MARKETING NIGERIA LTD SEE ATTACHED ANNEXURE XVII (LOT 9) | 39175218.51 | 16 WEEKS | 0%
52 | CONSTRUCTION OF INDEPENDENT WATER SUPPLY & PROVISION OF EXTERNAL MECHANICAL WORKS AT MAKURDI, BENUE STATE. | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 27TH JUNE,2011 | MESSRS ZIHABIT LTD SEE ATTACHED ANNEXURE XVII (LOT 10) | 87001853.4 | 12 WEEKS | 0%
53 | CONSTRUCTION OF 15 NOS. 2 - BEDROOM SEMI-DETACHED BUNGALOWS AT GOMBE, GOMBE STATE. | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 27TH JUNE,2011 | 15NO NUMBER. AWARDEES SEE ATTACHED ANNEXURE XVII (LOT 11) | 177682180.5 | 8 WEEKS | 10% | NOTE THAT AWARD VALUE IN COLUMN 'G' IS THE TOTAL FOR 15 NOS. CONTRACTS AWARDED.
54 | CONSTRUCTION OF 50 NOS. 3 - BEDROOM DETACHED BUNGALOWS AT GOMBE, GOMBE STATE. | PROCEEDS FROM SALE OF FHA HOUSES | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 27TH JUNE,2011 | 50 NUMBER. AWARDEES SEE ATTACHED ANNEXURE XVII (LOT 12) | 347852450 | 6 WEEKS | 10% | NOTE THAT AWARD VALUE IN COLUMN 'G' IS THE TOTAL FOR 50 NOS. CONTRACTS AWARDED.
55 | CONSTRUCTION OF ROADS & DRAINS AT GOMBE, GOMBE STATE. | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 27TH JUNE,2011 | MESSRS PERL CONSTRUCTION NIGERIA LTD SEE ATTACHED ANNEXURE XVII (LOT 13) | 18TH OCT, 2011 N143,124,355.05 | 36 WEEKS | 0%
56 | PROVISION OF EXTERNAL ELECTRIFICATION WORKS AT GOMBE, GOMBE STATE. | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 27TH JUNE,2011 | M/S SCHWEIZZER LUGANO NIGERIA LTD SEE ATTACHED ANNEXURE XVII (LOT 14) | 31109324.4 | 16 WEEKS | 0%
57 | CONSTRUCTION OF INDEPENDENT WATER SUPPLY & PROVISION OF EXTERNAL MECHANICAL WORKS AT GOMBE, GOMBE STATE. | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 27TH JUNE,2011 | MESSRS WATER BASE ENGINEERING LTD SEE ATTACHED ANNEXURE XVII (LOT 15) | 74725855.05 | 12 WEEKS | 0%
58 | CONSTRUCTION OF 9 NOS. 3 - BEDROOM TERRACED DUPLEX AT APO, GUDU DISTRICT, ABUJA. | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 27TH JUNE,2011 | 9NO NUMBER. AWARDEES SEE ATTACHED ANNEXURE XVII (LOT 16) | 761842191.69 | 36 WEEKS | 0% | NOTE THAT AWARD VALUE IN COLUMN 'G' IS THE TOTAL FOR 9 NOS. CONTRACTS AWARDED.
59 | CONSTRUCTION OF 23 NOS. 4 - BEDROOM SEMI-DETACHED DUPLEX AT APO, GUDU DISTRICT, ABUJA. | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 27TH JUNE,2011 | 23NO NUMBER. AWARDEES SEE ATTACHED ANNEXURE XVII (LOT 17) | 1387740420 | 36 WEEKS | 0% | NOTE THAT AWARD VALUE IN COLUMN 'G' IS THE TOTAL FOR 23 NOS. CONTRACTS AWARDED.
60 | CONSTRUCTION OF 25 NOS. 4 - BEDROOM DETACHED DUPLEX AT APO, GUDU DISTRICT, ABUJA. | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 27TH JUNE,2011 | 25NO NUMBER. AWARDEES SEE ATTACHED ANNEXURE XVII (LOT 18) | 851223637.5 | 36 WEEKS | 0% | NOTE THAT AWARD VALUE IN COLUMN 'G' IS THE TOTAL FOR 25 NOS. CONTRACTS AWARDED.
61 | CONSTRUCTION OF 5 NOS. 5 - BEDROOM DETACHED TRIPLEX AT APO, GUDU DISTRICT, ABUJA. | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 27TH JUNE,2011 | 5NO NUMBER. AWARDEES SEE ATTACHED ANNEXURE XVII (LOT 19) | 252162735 | 46 WEEKS | 0% | NOTE THAT AWARD VALUE IN COLUMN 'G' IS THE TOTAL FOR 5 NOS. CONTRACTS AWARDED.
62 | CONSTRUCTION OF ROADS & DRAINS AT APO, GUDU DISTRICT, ABUJA. | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 27TH JUNE,2011 | MESSRS S & M NIGERIA LTD SEE ATTACHED ANNEXURE XVII (LOT 20) | 188950377 | 36 WEEKS | 0%
63 | PROVISION OF EXTERNAL ELECTRIFICATION WORKS AT APO, GUDU DISTRICT, ABUJA. | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 27TH JUNE,2011 | M/S C.ROLLINS INV CO. NIGERIA LTD SEE ATTACHED ANNEXURE XVII (LOT 21) | 97004985 | 24 WEEKS | 0%
64 | PROVISION OF EXTERNAL MECHANICAL WORKS AT APO, GUDU DISTRICT, ABUJA. | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 27TH JUNE,2011 | MESSRS REAL JANE NIGERIA LTD SEE ATTACHED ANNEXURE XVII (LOT 22) | 34521298.35 | 6 WEEKS | 0%
65 | RENOVATION OF FHA TRANSIT CAMP, KADO ESTATE, PHASE II, ABUJA. | PROCEEDS FROM SALE OF FHA HOUSES | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 27TH JUNE,2011 | MESSRS EMMACHICO & SONS LTD SEE ATTACHED ANNEXURE XVII (LOT 24) | 10972451 | 8 WEEKS | 0%
66 | CONSTRUCTION OF ACCESS ROAD INTO GONIN-GORA ESTATE, KADUNA, KADUNA STATE | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 27TH JUNE,2011 | MESSRS FIBOG ENERGY LTD SEE ATTACHED ANNEXURE XVII (LOT 25) | 27255126.65 | 24 WEEKS | 25%
67 | REHABILITATION OF ROADS, GRASS VERGE ON SELECTED COMMISSIONING ROUTES & OTHER ROADS IN GWARINPA II ESTATE, ABUJA. | DITTO | RESTRICTED TENDERING | FHA NOTICE BOARD | MESSRS FRANK A.CONSTRUCTION LTD SEE ATTACHED ANNEXURE XVIII | 4106319.25 | 4 WEEKS | 100%
68 | CLEARING, GRADING AND LEVELING OF FHA LAND AT APO, GUDU DISTRICT ABUJA. | DITTO | RESTRICTED TENDERING | FHA NOTICE BOARD | MESSRS FRANK A.CONSTRUCTION LTD SEE ATTACHED ANNEXURE XIX | 4905654.6 | 3 WEEKS | 90%
69 | CLEARING, GRADING AND LEVELING OF FHA LAND AT NORTH BANK ESTATE, MAKURDI, BENUE STATE. | DITTO | RESTRICTED TENDERING | FHA NOTICE BOARD | MESSRS CHINCHECK CONSTRUCTION LTD SEE ATTACHED ANNEXURE XX | 4607583.75 | 3 WEEKS | 0%
70 | PROPOSED IMROVEMENT ON MAIN ENTRANCE GATE AT FHA HEADQUARTERS,ASOKORO, ABUJA. | DITTO | RESTRICTED TENDERING | FHA NOTICE BOARD | M/S ROYAL M/S LTD SEE ATTACHED ANNEXURE XXI | 4417468 | 2 WEEKS | 99%
71 | CLEARING, GRADING AND LEVELING OF FHA LAND AT GOMBE, GOMBE STATE. | DITTO | RESTRICTED TENDERING | FHA NOTICE BOARD | MESSRS PERL CONSTRUCTION NIGERIA LTD SEE ATTACHED ANNEXURE XXII | 4367979 | 3 WEEKS | 70%
72 | CLEARING, GRADING AND LEVELING OF FHA LAND AT AWKA, ANAMBRA STATE. | DITTO | RESTRICTED TENDERING | FHA NOTICE BOARD | MESSRS KJE (NIGERIA) LTD SEE ATTACHED ANNEXURE XXIII | 4705470 | 3 WEEKS | 0%
73 | CONSTRUCTION OF ROADS & DRAINS AT YENAGOA, BAYELSA STATE. | DITTO | OPEN TENDERING | THE GUARDIAN & DAILY TRUST NEWSPAPERS OF 18TH NOV,2010 | MESSRS SALEM CAT LTD SEE ATTACHED ANNEXURE XXIV | 282480660 | 36 WEEKS | 0% | APPROVAL FOR CONTRACT AWARD GRANTED BY MINISTERIAL TENDERS BOARD
74 | DIRECT PROCUREMENT OF GOODS | FHA 2011 BUDGET | DIRECT PROCUREMENT | NOT APPLICABLE | SEE ATTACHED ANNEXURE XXV | 177501696.74 | NOT APPLICABLE | 100% | PROCUREMENT TRANSACTION WAS FOR VARIOUS GOODS FROM DIFFERENT VENDORS FOR PERIOD COVERING JANUARY-DECEMBER 2011
12186722991.43

## ICRC
THE PRESIDENCY
Infrastructure Concession Regulatory Commission, Abuja
2011 Summary of transactions per Procurement Category
S/N | Description | Goods | Works | Consultancy Services | Non-Consultancy Services | Total Amount Expended
1 | Amount expended on each procurement category | 34451846.74 | 263705122.2435 | 71854580.78 | 8906250 | 378917799.7635
FEDERAL REPUBLIC OF NIGERIA
THE PRESIDENCY
Infrastructure Concession Regulatory Commission, Abuja
Procurement Activities for the period January to December 2011
S/N | Item Procured | Contract Value | Procurement Method | Contractor/Address | Contract Date | Delivery Completion Date | Activity delivered by | Payment Status | Remarks
C | Consulting Services
1 | Consultancy for the design and implementation of ICT Backbone infrastruture for the ICRC Head Office Building (Assignment / Lot 1) | 2029261.11 | QUALITY & COST BASED SELECTION (QCBS) | SUNNET SYSTEMS LIMITED, No 50, Anthony Enahoro Street, Utako District, Abuja, FCT. | 26th October 2011 | 28th December 2011 | Kabiru Yusuf & Sola Ogunsola | On-going | Project is 100% completed and usage by Commission has since taken off.
2 | Consultancy for the design and implementation of ICT Backbone infrastruture for the ICRC Head Office Building (Assignment / Lot 2) | 46283030.85 | QUALITY & COST BASED SELECTION (QCBS) | SUNNET SYSTEMS LIMITED, No 50, Anthony Enahoro Street, Utako District, Abuja, FCT. | 26th October 2011 | 14th February 2012 | Kabiru Yusuf & Sola Ogunsola | On-going | Project is 95% completed and usage by Commission has since taken off.
3 | Consultancy for the design and implementation of ICT Backbone infrastruture for the ICRC Head Office Building (Assignment / Lot 3) | 23542288.82 | QUALITY & COST BASED SELECTION (QCBS) | Y-COM TECHNOLOGIES LIMITED, No 9, N'djamena Crescent, Off Aminu Kano Crescent, Wuse 2, Abuja, FCT. | 26th October 2011 | 14th February 2012 | Kabiru Yusuf & Sola Ogunsola | On-going | Project is 95% completed and usage by Commission has since taken off.
GROSS AMOUNT |  | 71854580.78
FEDERAL REPUBLIC OF NIGERIA
THE PRESIDENCY
Infrastructure Concession Regulatory Commission, Abuja
Procurement Activities for the period January 2011 to March 2012
S/N | Item Procured | Contract Value | Procurement Method | Contractor/Address | Contract Date | Delivery Date | Activity delivered by | Payment Status | Remarks
A | Goods
1 | Printing and Supply of ICRC Establishment Act 2005. | 189000 | National Shopping | Mediaserve Prints Ltd, 18 Oke Agbe Street, Off Samuel Akintola Boulevard, Garki II, Abuja. | 1st February 2011 | 28th February 2011 | Kabiru Yusuf & Muktar Usman | Fully Paid
2 | Printing and Supply of ICRC Information Brochures, Fliers & Folders. | 364140 | National Shopping | Expo Solutions Ltd, Asokoro Shopping Mall, Plot 1552 YY Danjuma Street, Asokoro, Abuja. | 1st February 2011 | 28th February 2011 | Kabiru Yusuf & Muktar Usman | Fully Paid
3 | Printing and Supply of ICRC Letterheaded paper & National PPP Policy. | 1092000 | National Shopping | Garkida Press Ltd, Plot 742 Kade Street, Off Aminu Kano Crescent, Wuse II, Abuja. | 1st February 2011 | 28th February 2011 | Kabiru Yusuf & Muktar Usman | Fully Paid
4 | Supply and Installation of HP Desktop and Laptop Computers. | 2388750 | National Shopping | Junaid Integrated Services Limited | 1st February 2011 | 28th February 2011 | Kabiru Yusuf & Muktar Usman | Fully Paid
5 | Supply and Instalaltion of Office Furniture (Workstations). | 1983660 | National Shopping | Fovak Nigeria Ltd, Plot 36, Logokoma District, Abuja | 1st February 2011 | 28th February 2011 | Kabiru Yusuf & Muktar Usman | Fully Paid
6 | Printing and Supply of ICRC Staff Handbook. | 378000 | National Shopping | Garkida Press Ltd, Plot 742 Kade Street, Off Aminu Kano Crescent, Wuse II, Abuja. | 14th May 2011 | 23rd May 2011 | Kabiru Yusuf & Muktar Usman | Fully Paid | x
7 | Purchase of office stationeries. | 1732500 | National Shopping | Celesonic Nigeria Limited, Efab Shopping Mall, Garki, Abuja. | 15th August 2011 | 31st August 2011 | Kabiru Yusuf & Sola Ogunsola | Fully Paid
8 | Purchase of Stationeries & Computer Consumables. | 2460675 | National Shopping | Bonitech Computers Limited, Suite 24, Zone 3 Shopping Complex, Abuja. | 13th June 2011 | 30th June 2011 | Kabiru Yusuf & Muktar Usman | Fully Paid
9 | Printing of ICRC 2010 Annual Report & Accounts. | 472500 | National Shopping | Mediaserve Prints Ltd, 18 Oke Agbe Street, Off Samuel Akintola Boulevard, Garki II, Abuja. | 28th July 2011 | 30th August 2011 | `Kabiru Yusuf & Sola Ogunsola | Fully Paid
10 | Supply of office furniture | 7926121.74 | Direct Procurement | Julius Berger Nigeria PLC | 23rd December 2011 | 28th December 2011 | Kabiru Yusuf | Fully Paid
11 | Procurement of 1 unit 400 KVA generator for the head office building | 12209500 | Restricted Tendering Procedure | Topclass Generators Nig Ltd., 26, Agadez Crescent, Off Aminu Kano Crescent, Wuse Abuja. | 13th February 2012 | 15th February 2012 | Kabiru Yusuf & Muktar Usman | About 80% Paid
12 | Rental of one (1) unit of 350Kva Generator for a two month period. | 3255000 | National Shopping | PeggyLee Ventures Limited, No 23 Mambollo Street, Wuse Zone 2, Abuja. | 22nd December 2011 | 28th December 2011 | Kabiru Yusuf & Sola Ogunsola | Fully Paid
GROSS AMOUNT |  | 34451846.74
FEDERAL REPUBLIC OF NIGERIA
THE PRESIDENCY
Infrastructure Concession Regulatory Commission, Abuja
Procurement Activities for the period January to December 2011
S/N | Item Procured | Contract Value | Procurement Method | Contractor/Address | Contract Date | Delivery Date | Payment Status | Procurement staff. | Remarks
D | Non Consulting Services
1 | Provision of movement / relocation services from 13, Suleiman Barau Crescent to the new head office building at Plot 1270, Ayangba Street, Area 11, Garki, Abuja. | 1406250 | National Shopping | Domme Facilities Management Limited, No 1 Adebayo Munis Close, Off Residence Road, Gbagada Phase II, Lagos. | 22nd December 2011 | 28th December 2011 | Completed | Kabiru Yusuf & Sola Ogunsola
2 | Provision of Event Manager for International Conference on African Regional Infrastrucure | 7500000 | Restricted Tendering | Anfield Logistics Limited. | 2011-05-01 |  | On-going | Sola Ogunsola & Muktar Usman | On-going
GROSS AMOUNT |  | 8906250
FEDERAL REPUBLIC OF NIGERIA
THE PRESIDENCY
Infrastructure Concession Regulatory Commission, Abuja
Procurement Activities for the period January to March 2012
S/N | Item Procured | Contract Value | Procurement Method | Contractor/Address | Contract Date | Delivery Date | Payment Status | Activity delivered by | Remarks
B | Works
1 | ICRC Head Office Building Remodelling Project (Lot 1 - Civil Construction & Related Works) | 154411008.15 | National Competitive Bidding | Paul-B Nigeria PLC, 51, Parakou Street, Wuse II FCT abuja | 21st February 2011 | 29th February 2012 | On-going | Kabiru Yusuf | Project is 95% completed and Commission has since moven into the building. Payment made from 2010 & 2011 Capital Vote
2 | ICRC Head Office Building Remodelling Project (Lot 2 - Partitioning & Related Works) | 81526830 | National Competitive Bidding | Syndicated Metal Industry Nig Ltd, 29 Parakou Street, Wuse II FCT Abuja | 21st February 2011 | 29th February 2012 | On-going | Kabiru Yusuf | Project is 95% completed and Commission has since moven into the building. Payment made from 2010 & 2011 Capital Vote
3 | ICRC Head Office Building Remodelling Project (Project Architect Fees) | 9240011.361 | National Competitive Bidding | Ericon, Bello & Associates, No 20 Ekoro Oruro River Street, Off Osun Crescent, Off IBB Way, Maitama, Abuja, FCT. | 24th June 2010 | 29th February 2012 | On-going | Kabiru Yusuf | Project is 95% completed and Commission has since moven into the building. Payment made from 2010 & 2011 Capital Vote
4 | ICRC Head Office Building Remodelling Project (Project Structural Engineer's Fees) | 4822623.0465 | National Competitive Bidding | Shelter Engineers, No 27 Ali Akilu Road, Kaduna. | 24th June 2010 | 29th February 2012 | On-going | Kabiru Yusuf | Project is 95% completed and Commission has since moven into the building. Payment made from 2010 & 2011 Capital Vote
5 | ICRC Head Office Building Remodelling Project (Project Mechanical & Electrical Engineer's Fees) | 6695398.794 | National Competitive Bidding | Gams & Abel Nigeria Limited, No 12A, Sani Sambo Avenue, Unguwan Sarki, GRA, Kaduna. | 24th June 2010 | 29th February 2012 | On-going | Kabiru Yusuf | Project is 95% completed and Commission has since moven into the building. Payment made from 2010 & 2011 Capital Vote
6 | ICRC Head Office Building Remodelling Project (Project Quantity Surveyor's Fees) | 4727138.3145 | National Competitive Bidding | Prime & Bell Partnerships, 15A, Rimi Road, Kaduna. | 16th July 2010 | 29th February 2012 | On-going | Kabiru Yusuf | Project is 95% completed and Commission has since moven into the building. Payment made from 2010 & 2011 Capital Vote
7 | ICRC Head Office Building Remodelling Project (Project Manager's Fees) | 2282112.5775 | National Competitive Bidding | Muhammed & Co, C9 24, Waff Road, Kaduna. | 25th March 2011 | 29th February 2012 | On-going | Kabiru Yusuf | Project is 95% completed and Commission has since moven into the building. Payment made from 2010 & 2011 Capital Vote
GROSS AMOUNT |  | 263705122.2435

## FML & P
PROCUREMENT RECORDS
PROCURING ENTITY (MDA):
MINISTRY: |  |  | FEDERAL MINISTRY OF LABOUR AND PRODUCTIVITY
FINANCIAL YEAR: |  |  | 2011
|  | BASIC DATA |  |  |  | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | ADVERTISEMENT DATE AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT PERIOD | CONTRACT VALUE(N) | BUDGETARY PROVISION (N) | AMOUNT PAID AS AT | EXPECTED COMPLETION DATE | % OF COMPLETION AS AT | REMARKS
1 | Renovation of Offices of Honourable Minister and Perm. Sec | 25th Aug., 2011 - This Day & Daily Trust | MTB | Open Competition | 21st Sept., 2011 | Touch of Class Divine Connection | 2011-10-11 | 2 weeks | 21005213 | 181000000 | 21005213 | 23rd Nov. 2011 | 100%
2 | Supply and Installation of Furniture items to the Office os the Honourable Minister and Perms. Sec. | 25th Aug., 2011 - This Day & Daily Trust | MTB | Open Competition | 21st Sept., 2011 | Yeilah Prime Ltd. | 2011-10-11 | 2 weeks | 10095225 | 181000000 | 10095225 | 23rd Nov. 2011 | 100%
3 | Renovation of Offices of Directors' Offices | 25th Aug., 2011 - This Day & Daily Trust | MTB | Open Competition | 21st Sept., 2011 | Zuriel Star Ent. | 2011-10-11 | 2 weeks | 9214904.04 | 181000000 | 9214904.04 | 23rd Nov. 2011 | 100%
4 | Supply and Installation of Furniture items to the Directors' Offices | 25th Aug., 2011 - This Day & Daily Trust | MTB | Open Competition | 21st Sept., 2011 | Yeilah Prime Ltd. | 2011-10-11 | 2 weeks | 8381289 | 181000000 | 8381289 | 23rd Nov. 2011 | 100%
5 | Renovation of Deputy Directors' Offices | 25th Aug., 2011 - This Day & Daily Trust | MTB | Open Competition | 21st Sept., 2011 | Zuriel Star Ent. | 2011-10-11 | 2 weeks | 8912755.95 | 181000000 | 8912755.95 | 23rd Nov. 2011 | 100%
6 | Supply and Installation of furniture items to Deputy Directors' Offices | 25th Aug., 2011 - This Day & Daily Trust | MTB | Open Competition | 21st Sept., 2011 | Dionik Buiness Solution Ltd. | 2011-10-11 | 2 weeks | 12362438 | 181000000 | 12362438 | 23rd Nov. 2011 | 100%
7 | Renovation of Assistant Directors' Offices | 25th Aug., 2011 - This Day & Daily Trust | MTB | Open Competition | 21st Sept., 2011 | Dan Maikarfi Const. Ltd. | 2011-10-11 | 2 weeks | 12765847.5 | 181000000 | 12765847.5 | 23rd Nov. 2011 | 100%
8 | Supply and Installation of furniture items to Assistant Directors' Offices | 25th Aug., 2011 - This Day & Daily Trust | MTB | Open Competition | 21st Sept., 2011 | Pacific Crystal Ltd. | 2011-10-11 | 2 weeks | 25203134.01 | 181000000 | 25203134.01 | 23rd Nov. 2011 | 100%
9 | Supply of Computer Equipment | 25th Aug., 2011 - This Day & Daily Trust | MTB | Open Competition | 21st Sept., 2011 | Simdi W. A. Ltd. | 2011-10-11 | 2 weeks | 25703400 | 181000000 | 25703400 | 23rd Nov. 2011 | 100%
10 | Supply of Safety Items | 25th Aug., 2011 - This Day & Daily Trust | MTB | Open Competition | 21st Sept., 2011 | Touch of Class Divine Connection | 2011-10-11 | 2 weeks | 7399840 | 181000000 | 7399840 | 23rd Nov. 2011 | 100%
11 | Supply of Office Equipment | 25th Aug., 2011 - This Day & Daily Trust | MTB | Open Competition | 21st Sept., 2011 | G-Men Supplies & Services Ltd. | 2011-10-11 | 2 weeks | 9056700 | 181000000 | 9056700 | 23rd Nov. 2011 | 100%
12 | Supply of Stationeries | 25th Aug., 2011 - This Day & Daily Trust | MTB | Open Competition | 21st Sept., 2011 | Sifgate Int'l Ltd. | 2011-10-11 | 2 weeks | 5612250 | 181000000 | 5612250 | 23rd Nov. 2011 | 100%
13 | Renovation of 12 No. Toilets | N/A | MTB | Open Competition | 19th Dec., 2011 | Simpson Ventures | 2011-10-11 | 2 weeks | 3250000 | 181000000 | 3250000 | 3rd Jan. 2012 | 100%
14 | Procurement of Law Books | N/A | PS | RFQ | 19/10/11 | Henry Hinson Ltd. | 2011-10-11 | 2 weeks | 1664145 | 2472951 | 16641451 | 2011 | 100%
15 | National work-Place HIV/AIDS Responses | N/A | MTB | N/A | N/A | N/A | N/A | N/A | 2641126 | 5806522 | 2641126 | 2011 | 100% | Contracts were not awarded. In-house staff were used based on BPP Certificate of "No Objection" Ref. No. BPP/S.I/II/SP/Vol.II/149 dated 26th Aug., 2001.
16 | National Programme on Elimination of the Worst Form of Child Labour | N/A | MTB | N/A | N/A | N/A | N/A | N/A | 5806387 | 5806522 | 5806387 | 2011 | 100% | ""
17 | Nationwide Survey on the Elimination of Child Labour, Human Trafficking and Forced Labour | N/A | MTB | N/A | N/A | N/A | N/A | N/A | 3227800 | 10451740 | 3227800 | 2011 | 100% | ""
18 | Establishment of Occupational Safety and Health Institute and Labouratories in Umuahia (Cleaning of Site and Foundation Laying etc. | N/A | MTB | N/A | N/A | N/A | N/A | N/A | 4645218 | 4645218 | 4645218 | 2011 | 100% | ""
19 | Survey on Conduct of ILO October Enquiry of selected food. | N/A | MTB | N/A | N/A | N/A | N/A | N/A | 2396932 | 2396932 | 2396932 | 2011 | 100% | ""
179344604.5

## FCTA
FEDERAL CAPITAL TERRITORY ADMINISTRATION
BUREAU OF PUBLIC PROCUREMENT, PRESIDENCY, ABUJA PROCUREMENT RECORDS FOR FY 2011
S/N | CONTRACT NO. | DATE OF CONTRACT | CONTRACT DESCRIPTION | QTY (FOR GOODS ONLY) | TYPES OF CONTRACT | CONTRACTOR,S NAME & LOCATION | CONTRACT VALUES AMOUNT & CURRENCY | PROC. MATHOD (OPEN/SELECTIVE) | ORIGINAL COMPLETION DATE (MM/DD/YY) | ACTUAL COMPLETION DATE (MM/DD/YY) | AMT PAID TO DATE | BPP CERTIFICATE OF "NO OBJECTION" (IF ANY) FEC APPROVAL
SDA: AREA COUNCIL SERVICE COMMISSION DESK OFFICER :ROSE N.AGBAKWU PHONE :08036188077
S/N | CONTRACT NO. | DATE OF CONTRACT | CONTRACT DESCRIPTION | QTY (FOR GOODS ONLY) | TYPES OF CONTRACT | CONTRACTOR,S NAME & LOCATION | CONTRACT VALUES AMOUNT & CURRENCY | PROC. MATHOD (OPEN/SELECTIVE) | ORIGINAL COMPLETION DATE (MM/DD/YY) | ACTUAL COMPLETION DATE (MM/DD/YY) | AMT PAID TO DATE | BPP CERTIFICATE OF "NO OBJECTION" (IF ANY) FEC APPROVAL
1 | BPP/S.1/CCM/11/VOL.11/088 | 31ST MARCH 2011 | AREA COUNCILS TRAINING INSTITUTE |  | CONSTRUCTION OF ADMINISTRATIVE BLOCK | M/S CHIEFGA AND COMPANY LTD.PLOT R 84 SAMUEL AKINTOLA BOULEVARD GARKI 11, ABUJA | N605,281,711.05 | OPEN | NIL | NIL | NIL | NA
SDA: ABUJA ENTERPRISE AGENCY AEA | [5 empty] | DESK OFFICER: SHEHU ABDULKADIR |  |  | PHONE NUMBER: 08037911040
p | CONTRACT NO | DATE OF CONTRACT | CONTRACT DESCRIPTION | QTY ( FOR GOODS ONLY) | TYPES OF CONTRACT | CONTRACTOR'S NAME & LOCATION | CONTRACT VALUES-AMOUNT & CURRENCY | PROC. METHOD (OPEN/SELECTIVE) | ORIGINAL COMPLETION DATE(MM/DD/YY) | ACTUAL COMPLETION DATE(MM/DD/YY) | AMT PAID TO DATE | BPP CERTIFICATE OF "NO OBJECTION" (IF ANY)/FEC APPROVAL
1 |  |  | SUPPLY OF 3 UTILITY VEHICLES | 3 | SUPPLY OF UTILITY VEHICLE | ELIZADE NIGERIA LTD | N15,435,000.00 | DIRECT PROCUREMENT |  |  |  | CERTIFICATE OF NO OBJECTION
2 |  |  | SUPPLY OF 1 UTILITY VEHICLES | 1 | SUPPLY OF UTILITY VEHICLE | PEGEOUT AUTOMOBILE NIGERIA LTD | N5,662,830.00 | DIRECT PROCUREMENT |  |  |  | CERTIFICATE OF NO OBJECTION
SDA: ACSS | [5 empty] | DESK OFFICER: MR. IBE PROSPECT C. |  |  |  | PHONE: 08095493055
SN | CONTRACT NO | DATE OF CONTRACT | CONTRACT DESCRIPTION | QTY(FOR GOODS ONLY) | TYPES OF CONTRACT | CONTRACTOR'S NAME & LOCATION | CONTRACT VALUES, AMOUNT (=N=) | PROC.METHOD(OPEN/SELECTIVE) | ORIGINAL COMPLETION DATE (MM/DD/YY) | ACTUAL COMPLETION DATE(MM/DD/YY) | AMOUNT PAID TO DATE (=N=) | BPP CERTIFICATE OF "NO OBJECTION" (IF ANY) FEC APPROVAL
1 | FCTA/ACSS/1065/07/11 | 2011-12-04 | SUPPLY OF OFFICE MATERIALS TO ACSS |  | GOODS | VIGOUR INTERNATIONAL VENTURES LTD, HOUSE 68, 3RD AVENUE, GWARIMPA-ABUJA | 183750 | NATIONAL SHOPPING | 19/04/2011 | 19/04/2011 | 183750 | NOT APPLICABLE
2 | FCTA/ACSS/1065/01/11 | 2011-12-04 | SUPPLY OF ACCOUNTING MATERIALS TO ACSS |  | GOODS | ENYI UNIVERSAL STANDARDS LIMITED, SUITE GF 10, NOBLE PLAZA, MOSHOOD ABIOLA WAY, ABUJA | 329011 | NATIONAL SHOPPING | 19/04/2011 | 19/04/2011 | 329011 | NOT APPLICABLE
3 | FCTA/ACSS/1065/06/11 | 2011-12-04 | SUPPLY OF OFFICE MATERIALS(LOT 6) |  | GOODS | ANASON ENTERPRISES LIMITED, NO.14 AHMADU BELLO WAY, KADUNA | 1750665 | NATIONAL SHOPPING | 19/04/2011 | 19/04/2011 | 1750665 | NOT APPLICABLE
4 | FCTA/ACSS/1065/03/11 | 2011-12-04 | SUPPLY OF ACCOUNTING MATERIALS (LOT 3) |  | GOODS | GENTS FICKY ENTERPRISES, NO 7 VICTOR MASI CLOSE, JABI ABUJA | 356081 | NATIONAL SHOPPING | 19/04/2011 | 19/04/2011 | 356081 | NOT APPLICABLE
5 | FCTA/ACSS/1065/05/11 | 2011-12-04 | SUPPLY OF OFFICE MATERIALS (LOT 5) |  | GOODS | FAZIMAH ASSOCIATES, PLOT 762, AGADEZ CRESCENT, WUSE II, ABUJA | 1860548 | NATIONAL SHOPPING | 19/04/2011 | 19/04/2011 | 1860548 | NOT APPLICABLE
6 | FCTA/ACSS/1065/04/11 | 2011-12-04 | SUPPLY OF STATIONARY ITEMS |  | GOODS | REMIGHT CONSULT LIMITED, BLK B14, SHOP 5, NEW EXT. WUSE MARKET, ABUJA | 2422875 | NATIONAL SHOPPING | 19/04/2011 | 19/04/2011 | 2422875 | NOT APPLICABLE
7 | FCTA/ACSS/1065/02/11 | 2011-12-04 | SUPPLY OF ACCOUNTING MATERIALS (LOT 2) |  | GOODS | WEBDOTS LIMITED, HS 102, 693 ROAD, GWARIMPA, ABUJA | 378472 | NATIONAL SHOPPING | 19/04/2011 | 19/04/2011 | 378472 | NOT APPLICABLE
8 | FCTA/ACSS/1065/11 | 2011-12-04 | SUPPLY OF OFFICE MATERIALS (LOT 9) |  | GOODS | NAH BUTI & CO. HUT 47, GAMES VILLAGE, ABUJA | 1556704 | NATIONAL SHOPPING | 19/04/2011 | 19/04/2011 | 1556704 | NOT APPLICABLE
SDA: ASO RADIO SERVICES, ABUJA DESK OFFICER: CHUKS ONUBOGU PHONE: 07033005070
S/No | CONTRACT NO | DATE OF CONTRACT | CONTRACT DESCRIPTION | QTY(GOODS ONLY) | TYPES OF CONTRACT | CONTRACTOR'S NAME & LOCATION | CONTRACT VALUES- AMOUNT & CURRENCY (Naira) | PROC. METHOD (OPEN/ SELECTIVE ETC) | ORIGINAL COMPLETION DATE (DD/MM/YY) | ACTUAL COMPLETION DATE (DD/MM/YY) | AMT PAID TO DATE | BPP CERTIFICATE OF "NO OBJECTION" (IF ANY)/FEC APPROVAL
1 | FCTA/TB/(2010)55 | 24/12/2010 | SUPPLY & INSTALLATION OF WIRE GUYED MAST & ANTENNA SYSTEM | 1 | GOODS | ELCALPEMOS TECHNOLOGIES LTD KADUNA | 78104250 | NATIONAL COMPETITIVE BIDDING | 2011-05-03 | 2011-10-04 | 11715637 | N/A
2 | FCTA/TB/(2010)56 | 24/12/2010 | SUPPLY & INSTALLATION OF FM RADIO STEREO TRANSMITTER | 2 | GOODS | ELCALPEMOS TECHNOLOGIES LTD KADUNA | 76308750 | NATIONAL COMPETITIVE BIDDING | 2011-01-13 | 2011-03-21 | 33650000 | N/A
4 | FCTA/TB/(2010)62 | 24/12/2010 | ERCTION OF DIGITAL BILLBOARD | 1 | GOODS | ELCALPEMOS TECHNOLOGIES LTD KADUNA | 18952500 | NATIONAL COMPETITIVE BIDDING | 2011-01-21 |  | 2842875 | N/A
5 | HM/FCT/MO/304/Vol.1/136F | 24/12/2010 | PROVISION OF ICT FACILITIES & AREA LOCAL NETWORK | N/A | SERVICES | SELAC VENTURES LTD LAGOS | 5099965.5 | NATIONAL COMPETITIVE BIDDING | 2011-01-21 | 2011-02-05 | 4099965.5 | N/A
3 | HM/FCT/MO/304A | 18/11/2010 | PROVISION OF WATER SUPPLY SYSTEM | 1 | GOODS | SIM CONCERNS LTD ABUJA | 4, 170,600.00 | NATIONAL COMPETITIVE BIDDING | 2011-02-10 | 2011-05-25 | NIL | N/A
6 | FCTA/TB/(2010) 58 | 24/12/2010 | SUPPLY & INSTALLATION OF UNINTERRUPTED POWER SUPPLY | 1 | GOODS | ELCALPEMOS TECHNOLOGIES LTD KADUNA | 10473750 | NATIONAL COMPETITIVE BIDDING | 2011-01-13 | 2011-03-21 | NIL | N/A
S/No | CONTRACT NO | DATE OF CONTRACT | CONTRACT DESCRIPTION | QTY(GOODS ONLY) | TYPES OF CONTRACT | CONTRACTOR'S NAME & LOCATION | CONTRACT VALUES- AMOUNT & CURRENCY ( Naira) | PROC. METHOD (OPEN/ SELECTIVE ETC) | ORIGINAL COMPLETION DATE (MM/DD/YY) | ACTUAL COMPLETION DATE (MM/DD/YY) | AMT PAID TO DATE | BPP CERTIFICATE OF "NO OBJECTION" (IF ANY)/FEC APPROVAL
7 | FCTA/TB/(2010)64 | 29/12/2010 | SUPPLY OF OFFICE EQUIPMENT | N/A | SERVICES | SOLABIG NIG LTD ABUJA | 29901060 | NATIONAL COMPETITIVE BIDDING | 2011-01-18 | 2011-05-04 | NIL | N/A
8 | FCTA/TB/(2010)65 | 29/12/2010 | SUPPLY OF UTILITY VEHICLES | 10 | GOODS | ASD MOTORS NIG LTD | 40396961.6 | NATIONAL COMPETITIVE BIDDING | 2011-05-01 | 2011-05-03 | NIL | N/A
9 | HM/FCT/MO304/Vol./136G | 24/12/2010 | ERECTION OF STANDARD BILLBOARDS | 2 | SERVICES | PRIMO WONDERS LTD KADUNA | 5691000 | NATIONAL COMPETITIVE BIDDING | 2011-02-18 | 2011-03-05 | NIL | N/A
SDA: ASO TELEVISION SERVICES DESK OFFICER: NKWOPARA HENRY OSONDU PHONE: 08035137940
S/N | CONTRACT NO. | DATE OF CONTRACT | CONTRACT DESCRIPTION | QTY (FOR GOODS ONLY) | TYPE OF CONTRACT | CONTRACTORS NAME AND LOCATION | CONTRACTOR’S VALUES AMOUNT & CURRENCY | PROC. METHOD (OPEN/ SELECTIVE) | ORIGINAL COMPLETION DATE (MM/DD/YY) | ACTUALCOMPLETION DATE (MM/DD/YY) | AMT PAID TO DATE | BPP CERTIFICATE OF “NO OBJECTION” (IF ANY) FEC APPROVAL
1 | FCTA/TB/ 53 | 2010-12-29 | Supply of Furniture for new administrative Building for ASO Television Services | NA | Goods | M/S Ayioza Associates Ltd, Suite 38 Mardu Plaza, Wuse Zone 5, Abuja | N14,574,000= | Open | 2011 | 2011 | N14,574,000=
NA
2 | FCTA/TB/ 54 | 2010-12-29 | Supply of Laptops and desktops Computers for ASO Television Services | 2012-10-10 | Goods | M/S Ethel Ventures Ltd, Hall A&B Poly Plaza, Wuse II, Abuja | N 3,788,925 | Open | 2011 | 2011 | N3,788,925 | NA
3 | FCTA/TB/ 52 | 2010-12-24 | Supply of 150 KVA Uninterrupted Power Supply to ASO Television | 1 | Goods | M/S Selac Ventures ltd, 6 Pepple Street Lagos | N 14,616,000= | Open | 2011 | 2011 | N14,616,000= | NA
4 | FCTA/TB/ 51 | 2010-12-24 | Supply & Installation of 100KVA Power Transformer and 60KVA sound proof Generators including 2no 600A changeover switch to ASO Television Services | TXF=1 | Works | M/S Kotco Energy Nig. Ltd, 55 Kumasi Street, Wuse II, Abuja | N 14,679,000= | Open | 2011 | 2011 | N14,679,000= | NA
Gen.=2
CO =2
5 | FCTA/TB(2011) 121 | 2011-03-31 | Construction of New Office Complex for ASO Television Services. | 1 Unit | Works | M/S Geroma Nig. Ltd, Plot 7, Urugnay Street, Off Aminu Kano Crescent, Wuse II, Abuja | N 61,685,410.50 | Open | 2011 | On-going | Nil | NA
6 | FCTA/TB(2011) 124 | 2011-03-31 | Construction of Transmitter and studio Building for ASO TV Services | 1 Unit | Works | M/S Geroma Nig. Ltd, Plot 7, Urugnay Street, Off Aminu Kano Crescent, Wuse II, Abuja | N 18,989,497.50 | Open | 2011 | On-going | N2,848,424.63 | NA
7 | FCTA/TB(2011) 122 | 2011-06-21 | Automation of Broadcasting Equipment | NA | Works | M/S Ecalpemos Technologies Ltd, 31 Gwari Avenue, Kaduna | N 79,590,000= | Open | 2011 | Not yet mobilized | Nil | NA
S/N | CONTRACT NO. | DATE OF CONTRACT | CONTRACT DESCRIPTION | QTY (FOR GOODS ONLY) | TYPE OF CONTRACT | CONTRACTORS NAME AND LOCATION | CONTRACTOR’S VALUES AMOUNT & CURRENCY | PROC. METHOD (OPEN/ SELECTIVE) | ORIGINAL COMPLETION DATE (MM/DD/YY) | ACTUALCOMPLETION DATE (MM/DD/YY) | AMT PAID TO DATE | BPP CERTIFICATE OF “NO OBJECTION” (IF ANY) FEC APPROVAL
8 | FCTA/TB(2011) 120 | 2011-06-21 | Supply & Installation of TV Studio Facilities and control room | NA | Works | M/S Ecalpemos Technologies Ltd, 31 Gwari Avenue, Kaduna | N 126,911,400= | Open | 2011 | Not yet mobilized | Nil | NA
9 | FCTA/TB(2011) 126 | 2011-03-21 | Furnishing of Studio & Transmitter Building | NA | Goods | M/S Ikporo Nig. Ltd, 25/26 Owners Occupier Housing Estate, Kubwa Abuja | N 4,725,000= | Open | 2011 | Not yet mobilized | Nil | NA
10 | FCTA/TB(2011) 119 | 2011-06-21 | Supply of 6 Nos Operational/Utility Vehicles | 6 Nos | Goods | M/S Shaw Brothers Overseas Ltd | N 21,593,250= | Open | 2011 | Not yet mobilized | Nil | NA
Suite D63 Mumay Plaza , Area 10 Garki Abuja
11 | FCTA/TB(2011) 123 | 2011-06-21 | Supply & Installation of 1NO 10 KW & 2 Nos 3KW TV Transmitters | 3 Nos | Works | M/S Transtec Computers System Ltd, No. 5/7 Ali Akilu Road, Oceanic Bank Premises, By Alkali Road Kaduna | N 276,842,528. | Open | 2011 | Not yet mobilized | Nil | NA
55
12 | FCTA/TB(2011) 128 | 2011-03-31 | Provision & Installation of Cooling Systems | NA | Goods | M/S Intergrated Seed Resources Ltd, Suite 22 Garki II Shopping Complex, Abuja | N 27,676,000= | open | 2011 | Not yet mobilized | Nil | NA
13 | Completed all Procurement Procedures | Not Awarded | Supply of TV Transmitters Spare Parts | NA | Goods | M/S Transtec Computers System Ltd, No. 5/7 Ali Akilu Road, Oceanic Bank Premises, By Alkali Road Kaduna | N 84,149,546.25 | open |  |  | Nil | NA
14 | Completed all Procurement Procedures | Not awarded | Provision and Commissioning of Outside Broadcast DNSG Microwave Link Equipment | 1 Unit | Works | M/S Ecalpemos Technologies Ltd, 31 Gwari Avenue, Kaduna | N 82,027,050.00 | open |  |  | Nil | NA
SDA: Dept. of EPRS DESK OFFICER: H.U.Bagudu PHONE NUMBER: 08023120910
S/N | CONTRACT NO | DATE OF CONTRACT | CONTRACT DESCRIPTION | QTY (FOR GOODS ONLY) | TYPES OF CONTRACT | CONTRACTOR'S NAME & LOCATION | CONTRACT VALUES-AMOUNT & CURRENCY | PROC. METTHOD (OPEN/SELECTIVE) | ORIGINAL COMPLETION DATE (MM/DD/YY) | ACTUAL COMPLETION DATE (MM/DD/YY) | AMT PAID TO DATE | BPP CERTIFICATE OF "NO OBJECTION" (IF ANY)/FEC APPROVAL
1 | FCTA/TB/(2010)13 | 3rd DEC.,2010 | Purchase of 3NO. Utility Vehicles | 3 NO | GOODS | MS RAJIF VENTURES NIG. LTD. | N19,382,937.00 | OPEN COMPETITION | 24/12/2010 | OCT. 2011 | N19,382,937.00 | NA
SDA: | EDUCATION SECRETARIAT HQRTS |  |  |  | DESK OFFICER: | [5 empty] | PHONE:
S/N | CONTRACT NO. | DATE OF CONTRACT | CONTRACT DESCRIPTION | QTY (FOR GOODS ONLY) | TYPES OF CONTRACT | CONTRACTOR'S NAME & LOCATION | CONTRACT VALUES AMOUNT & CURRENCY | PROC. METHOD (OPEN/SELECTIVE) | ORGINAL COMPLETION DATE (MM/DD/YY) | ACTUAL COMPLETION DATE(MM/DD/YY) | AMOUNT PAID TO DATE | BPP CERTIFICATE OF "NO OBJECTION " (IF ANY) FEC APPROVAL
1 | NIL | NIL | Completion of DPI Zonal Office at Bwari |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
2 | NIL | NIL | Computerization of Department of Policy and Implementation Headquarters and other Zonal offices |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
3 | NIL | NIL | Expansion and renovation of DPI Head Office, Jabi |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
4 | NIL | NIL | Construction of Clinic at Abuja University of Technology, Abaji |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
5 | NIL | NIL | Construction of Library Block at Abuja University of Technology, Abaji |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
6 | NIL | NIL | Construction of Kitchen/Cafeteria at Abuja University of Technology, Abaji |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
7 | NIL | NIL | Construction of Multi-purpose Hall at Abuja University of Technology, Abaji |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
8 | NIL | NIL | Completion of Laboratories at Abuja University of Technology, Abaji |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
9 | NIL | NIL | Furnishing of Classrooms at Abuja University of Technology, Abaji |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
10 | NIL | NIL | Furnishing of Laboratories at Abuja University of Technology, Abaji |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
11 | NIL | NIL | Furnishing of Offices at Abuja University of Technology, Abaji |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
12 | NIL | NIL | Provision of Walkways & Soft Landscaping at Abuja University of Technology, Abaji |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
13 | NIL | NIL | Paving/Landscaping of 4 Bedroom take off office at Abuja University of Technology, Abaji |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
14 | NIL | NIL | Furnishing of transit quarters at Abuja University of Technology, Abaji |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
15 | NIL | NIL | Expansion of 4 Bedroom take off office at Abuja University of Technology, Abaji |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
16 | NIL | NIL | Upgrading of Internal Road network and clearing of Drains at Abuja University of Technology, Abaji |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
17 | NIL | NIL | Completion of Hostel Block at Abuja University of Technology, Abaji |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
18 | NIL | NIL | Provision of Borehole, ground and overhead water tanks at Abuja University of Technology, Abaji |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
19 | NIL | NIL | Supply o hardware for Computerization to Department of Policy & Implementation, Jabi |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
SDA: | AGENCY FOR MASS EDUCATION |  |  |  | DESK OFFICER: | [5 empty] | PHONE:
S/N | CONTRACT NO. | DATE OF CONTRACT | CONTRACT DESCRIPTION | QTY (FOR GOODS ONLY) | TYPES OF CONTRACT | CONTRACTOR'S NAME & LOCATION | CONTRACT VALUES AMOUNT & CURRENCY | PROC. METHOD (OPEN/SELECTIVE) | ORGINAL COMPLETION DATE (MM/DD/YY) | ACTUAL COMPLETION DATE(MM/DD/YY) | AMOUNT PAID TO DATE | BPP CERTIFICATE OF "NO OBJECTION " (IF ANY) FEC APPROVAL
1 | NIL | NIL | Construction of 1no. block of 2 classrooms, VTC Karshi |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
2 | NIL | NIL | Construction of 1 block of 2 classrooms, VTC Bwari |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
3 | NIL | NIL | Provision of adult learners furniture to VTC, women & literacy Centres at Karsh |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
4 | NIL | NIL | Provision of adult learners furniture to VTC, women & literacy Centres at Bwari |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
5 | NIL | NIL | Construction of 1 no. VTC library, Kwali |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
6 | NIL | NIL | Equipping of VTC library, Kwali |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
7 | NIL | NIL | Furnishing of VTC library, Kwali |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
8 | NIL | NIL | Construction of 1 no. Agric Workshop, VTC Kwali |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
9 | NIL | NIL | Construction of Science laboratory, VTC Bwari |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
10 | NIL | NIL | Construction of Science laboratory, VTC Abaji |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
11 | NIL | NIL | Completion of Wood/metal workshop at old site, Karshi |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
12 | NIL | NIL | Construction of 1no. ICT laboratory, VTC Abaji |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
13 | NIL | NIL | Furnishing of 1 no. Agric. Workshop, Kwali |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
14 | NIL | NIL | Equipping of 1 no. Agric. Workshop, Kwali |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
15 | NIL | NIL | Furnishing of science laboratory, Bwari |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
16 | NIL | NIL | Furnishing of Science Laboratory, Abaji |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
17 | NIL | NIL | Equipping of Science Laboratory, Bwari |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
18 | NIL | NIL | Equipping of Science Laboratory, Abaji |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
19 | NIL | NIL | Furnishing of ICT Laboratory, Abaji |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
20 | NIL | NIL | Equipping of ICT laboratory, Abaji |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
21 | NIL | NIL | Construction of Block of Water System toilet, Flushing of borehole and reticulation to toilets at VTC, Bwari |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
22 | NIL | NIL | Construction of Block of Water System toilet, Flushing of borehole and reticulation to toilets at VTC, Kuje |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
23 | NIL | NIL | Construction of Block of Water System toilet, Flushing of borehole and reticulation to toilets at VTC, Kwali |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
24 | NIL | NIL | Construction of Block of Water System toilet, Flushing of borehole and reticulation to toilets at VTC, Gwagwalada |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
25 | NIL | NIL | Construction of Block of Water System toilet, Flushing of borehole and reticulation to toilets at VTC, Karshi |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
26 | NIL | NIL | Construction of perimeter fence gate & gatehouse at old site of VTC Karshi |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
27 | NIL | NIL | Completion of perimeter fence at VTC, Abaji. |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
28 | NIL | NIL | Provision of office furniture to AME Headquarters, Asokoro |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
SDA: | EDUCATION RESOURCE CENTRE |  |  |  | DESK OFFICER: | [5 empty] | PHONE:
S/N | CONTRACT NO. | DATE OF CONTRACT | CONTRACT DESCRIPTION | QTY (FOR GOODS ONLY) | TYPES OF CONTRACT | CONTRACTOR'S NAME & LOCATION | CONTRACT VALUES AMOUNT & CURRENCY | PROC. METHOD (OPEN/SELECTIVE) | ORGINAL COMPLETION DATE (MM/DD/YY) | ACTUAL COMPLETION DATE(MM/DD/YY) | AMOUNT PAID TO DATE | BPP CERTIFICATE OF "NO OBJECTION " (IF ANY) FEC APPROVAL
1 | NIL | NIL | Renovation of City Library, Wuse Zone 4 |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
2 | NIL | NIL | Construction of Administrative Block at Teacher Development Centre, Abaji |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
3 | NIL | NIL | Supply and installation of 2no. Generators to newly completed library at Bwari and Teachers Development Centres at Kwali |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
4 | NIL | NIL | Construction of Block wall fence, gate, gatehouse, generator house and landscaping at newly completed TDD and District library, Kwali |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
5 | NIL | NIL | Up-grading of internet facilities at ERC Hqtrs Library |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
6 | NIL | NIL | Up-grading of internet facilities at City library, Wuse Zone 4 |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
7 | NIL | NIL | Up-grading of internet facilities at Gudu District library |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
8 | NIL | NIL | Supply of office furniture to District Library at Bwari |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
9 | NIL | NIL | Supply of office furniture to District Library at Kwali |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
10 | NIL | NIL | Supply of equipment to Children Library Gudu |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
11 | NIL | NIL | Furnishing of Children Library Gudu |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
12 | NIL | NIL | Supply of Library Books to Gudu Children Library |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
13 | NIL | NIL | Rehabilitation of ERC Damaged Building |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
14 | NIL | NIL | Furnishing of Chalet Building at ERC |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
15 | NIL | NIL | Furnishing of Teacher Development Centre Kwali |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
16 | NIL | NIL | Supply of office equipment to District Library Bwari |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
17 | NIL | NIL | Supply of equipment for the production of instructional materials to the EIT Resource Room at the ERC |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
18 | NIL | NIL | Supply of office equipment to the ERC |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
19 | NIL | NIL | Supply of equipment to the Printing Press at ERC |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
20 | NIL | NIL | Supply of Air Conditioners to Central Store/Exam Processing Room/TDC at ERC, Zone 7, Wuse-Abuja |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
21 | NIL | NIL | Fencing of Teacher Development Centre, Abaji |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
SDA: | AGENCY FOR SCIENCE AND TECHNOLOGY |  |  |  | DESK OFFICER: | [5 empty] | PHONE:
S/N | CONTRACT NO. | DATE OF CONTRACT | CONTRACT DESCRIPTION | QTY (FOR GOODS ONLY) | TYPES OF CONTRACT | CONTRACTOR'S NAME & LOCATION | CONTRACT VALUES AMOUNT & CURRENCY | PROC. METHOD (OPEN/SELECTIVE) | ORGINAL COMPLETION DATE (MM/DD/YY) | ACTUAL COMPLETION DATE(MM/DD/YY) | AMOUNT PAID TO DATE | BPP CERTIFICATE OF "NO OBJECTION " (IF ANY) FEC APPROVAL
1 | NIL | NIL | Supply of Materials to Agency for Science and Technology |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
2 | NIL | NIL | Supply of Library Books & Periodicals for Agency for Science and Technology |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
3 | NIL | NIL | Supply of Computer Materials for Agency for Science and Technology |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
4 | NIL | NIL | Renovation of Agency for Science and Technology Site Office, Area 11 |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
5 | NIL | NIL | Supply of Materials for participation in Junior/Senior Science Olympiad, Project Fairs and Exhibition to Agency for Science & Technology |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
6 | NIL | NIL | Supply of food stuff materials for GSTC, Garki |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
7 | NIL | NIL | Upgrading of software for Computer System in Agency for Science and Technology office and GSTC, Garki |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
8 | NIL | NIL | Construction of 1No. Production Centre at GSTC, Garki for Accreditation |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
9 | NIL | NIL | Procurement of Instructional Materials and Statutory Record Books for the two GSTC Utako & Garki |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
10 | NIL | NIL | Provision of Perimeter fence, gate & gate house at GSTC, Kwali |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
11 | NIL | NIL | Construction of Administrative Block at GSTC, Kwali |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
12 | NIL | NIL | Construction of classrooms at GSTC, Kwali |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
13 | NIL | NIL | Construction of Workshops at GSTC, Kwali |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
14 | NIL | NIL | Construction of Hostels at GSTC, Kwali |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
15 | NIL | NIL | Clearing of land for take-off of GSTC, Kwali |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
16 | FCT/EDUC/TB/2011/01/AWA/021 | 30/12/111 | Supply and Installation of materials and equipment for Virtual Library, as well as installation and reticulation of e-Board at GSSS, Pyakasa in Maitama |  |  | M/S King General Enterprises Ltd | 61352098 | Selective | 6 WKS | 6 WKS | NIL | BPP CERTIFICATE OF "NO OBJECTION "
17 | FCT/EDUC/TB/2011/01/AWA/022 | 30/12/111 | Furnishing and supply of equipment of Laboratories at GSSS, Pyakasa in Maitama |  |  | M/S Great Comac Investment Ltd | 30593616.23 | Selective | 4 WKS | 4 WKS | NIL | BPP CERTIFICATE OF "NO OBJECTION "
18 | FCT/EDUC/TB/2011/01/AWA/023 | 30/12/111 | Supply & Installation of Specialized Workshop Equipment to GSSS, Pyakasa in Maitama |  | WORKS | M/S Tenac (Nig) Ltd | 60254206.1 | Selective | 5 WKS | 5 WKS | NIL | BPP CERTIFICATE OF "NO OBJECTION "
19 | FCT/EDUC/TB/2011/01/AWA/024 | 30/12/111 | Furnishing and equipping of Library, Administrative /Multipurpose Hall, staff Quarters, Classroom, hostels and Kitchen/Dinning at GSSS Pyakasa in Maitama |  |  | M/S P.P Madus Nig. Ltd. | 132134373 | Selective | 8 WKS | 8 WKS | NIL | BPP CERTIFICATE OF "NO OBJECTION "
20 | FCT/EDUC/TB/2011/01/AWA/025 | 30/12/111 | Provision of Power Source and Security Light as well as Supply & Installation of Standby Generators for GSSS, Pyakasa in Maitama |  | WORKS | M/S Constructii Proactii | 34962169.2 | Selective | 12 WKS | 12 WKS | NIL | BPP CERTIFICATE OF "NO OBJECTION "
21 | FCT/EDUC/TB/2011/01/AWA/026 | 30/12/111 | Upgrading of Fence, Gate and Gate House, Provision of Water Reservoir and Sporting facilities as well as Civil Works & Landscaping at GSSS Pyakasa in Maitama |  | WORKS | M/S Martsonic Nig Ltd | 224034603.87 | Selective | 24 WKS | 24 WKS | NIL | BPP CERTIFICATE OF "NO OBJECTION "
22 | FCT/EDUC/TB/2011/01/AWA/027 | 30/12/111 | Construction of houses for the Vice Principal and Matron as well as renovation of Principal's House at GSSS, Pyakasa in Maitama |  | WORKS | M/S Sagasco Investment Ltd | 43099918.58 | Selective | 12 WKS | 12 WKS | NIL | BPP CERTIFICATE OF "NO OBJECTION "
23 | FCT/EDUC/TB/2011/01/AWA/028 | 30/12/111 | Provision of Internet facilities to a block of 24 classroom at GSSS, Pyakasa in Maitama |  | WORKS | M/S Forgate Nig Ltd | 25284000 | Selective | 6 WKS | 6 WKS | NIL | BPP CERTIFICATE OF "NO OBJECTION "
SDA: | COLLEGE OF EDUCATION |  |  |  | DESK OFFICER: | [5 empty] | PHONE:
S/N | CONTRACT NO. | DATE OF CONTRACT | CONTRACT DESCRIPTION | QTY (FOR GOODS ONLY) | TYPES OF CONTRACT | CONTRACTOR'S NAME & LOCATION | CONTRACT VALUES AMOUNT & CURRENCY | PROC. METHOD (OPEN/SELECTIVE) | ORGINAL COMPLETION DATE (MM/DD/YY) | ACTUAL COMPLETION DATE(MM/DD/YY) | AMOUNT PAID TO DATE | BPP CERTIFICATE OF "NO OBJECTION " (IF ANY) FEC APPROVAL
1 | NIL | NIL | Construction of school of Voc. & Tech. Education at the Permanent Site of College of Education, Zuba |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
2 | NIL | NIL | Provision of street light and upgrading of lightning facilities (sub-station) at at the Permanent Site of College of Education, Zuba |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
3 | NIL | NIL | Hard landscaping of school of Sciences at the Permanent Site of College of Education, Zuba |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
4 | NIL | NIL | Provision of 100KVA Sound proof (wilsion) Perkin, installation and Generator House at the Permanent Site of College of Education, Zuba |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
5 | NIL | NIL | Furnishing of School of Sciences at the Permanent Site of College of Education, Zuba |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
6 | NIL | NIL | Construction of road to Library Complex and Parking Area at the Permanent Site of College of Education, Zuba |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
SDA: | SECONDARY EDUCATION BOARD |  |  |  | DESK OFFICER: | [5 empty] | PHONE:
S/N | CONTRACT NO. | DATE OF CONTRACT | CONTRACT DESCRIPTION | QTY (FOR GOODS ONLY) | TYPES OF CONTRACT | CONTRACTOR'S NAME & LOCATION | CONTRACT VALUES AMOUNT & CURRENCY | PROC. METHOD (OPEN/SELECTIVE) | ORGINAL COMPLETION DATE (MM/DD/YY) | ACTUAL COMPLETION DATE(MM/DD/YY) | AMOUNT PAID TO DATE | BPP CERTIFICATE OF "NO OBJECTION " (IF ANY) FEC APPROVAL
1 | NIL | NIL | Construction of Admin Block at GSS Mpape |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
2 | NIL | NIL | Construction of Admin Block at GSS Pai |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
3 | NIL | NIL | Construction of Admin Block at GSS Kabusa |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
4 | NIL | NIL | Construction of Admin Block at GSS Dei-Dei |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
5 | NIL | NIL | Construction of Admin/Library Block (Storey Building) at GMSS Jikwoyi |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
6 | NIL | NIL | Construction of Admin/Library Block (Storey Building) at GSS Jabi |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
7 | NIL | NIL | Construction of Admin/Library Block (Storey Building) at GDSS Karu |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
8 | NIL | NIL | Construction of Library at GSS Jiwa |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
9 | NIL | NIL | Construction of Library at GSS Byazhin |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
10 | NIL | NIL | Construction of a block of 8 Classrooms at GSS Mpape |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
11 | NIL | NIL | Construction of a block of 4 Resource Rooms at GMSS Jikwoyi |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
12 | NIL | NIL | Construction of a block of 8 Classrooms at GSS Dei-Dei |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
13 | NIL | NIL | Construction of a block of 8 Classrooms at GSS Kabusa |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
14 | NIL | NIL | Construction of Kitchen & Dining Hall at GMSS Jikwoyi |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
15 | NIL | NIL | Construction of Kitchen & Dining Hall at GGSS Dukpa |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
16 | NIL | NIL | Construction of Hostel Block (Storey Building) at GMSS Jikwoyi |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
17 | NIL | NIL | Construction of Hostel Block at GSS G/Lada |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
18 | NIL | NIL | Construction of Hostel Block at GSS Gawu |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
19 | NIL | NIL | Construction of Perimeter Fencing/Gate & Gatehouse at GSS Byazhin |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
20 | NIL | NIL | Construction of Part Perimeter Fencing/Gate & Gatehouse at GSS Rubochi |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
21 | NIL | NIL | Construction of Part Perimeter Fencing/Gate & Gatehouse at GSS Airport |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
22 | NIL | NIL | Re-construction of Perimeter Fencing at GSS Wuse |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
23 | NIL | NIL | Construction of Part Perimeter Fencing/Gate & Gatehouse at GSS Gwagwa |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
24 | NIL | NIL | Re-construction/Renovation of Perimeter Fencing at GSS Karu |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
25 | NIL | NIL | Construction of Part Perimeter Fencing/Gate & Gatehouse at GSS Gudun Karya |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
26 | NIL | NIL | Completion/Renovation of Perimeter Fencing at GSS Bwari |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
27 | NIL | NIL | Construction of Part Perimeter Fencing/Gate & Gatehouse at GSS Zuba |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
28 | NIL | NIL | Construction of Part Perimeter Fencing/Gate & Gatehouse at GSS Mpape |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
29 | NIL | NIL | Completion of Admin Block at GDSS Bwari |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
30 | NIL | NIL | Completion of Admin Block at GDSS Dutse |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
31 | NIL | NIL | Completion of Multi-purpose Hall at GDSS Bwari |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
32 | NIL | NIL | Completion of Kitchen/Dining Hall at GSS G/Lada |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
33 | NIL | NIL | Construction of Admin Block At GSS Yangoji |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
34 | NIL | NIL | Renovation of Hostel at GSS T/Maje |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
35 | NIL | NIL | Renovation/Furnishing of Laboratory at GSS G/Lada |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
36 | NIL | NIL | Renovation/External Works at SEB Headquarters |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
37 | NIL | NIL | Rehabilitation of Sporting Facilities at GSS Garki |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
38 | NIL | NIL | Provision of Civil Works at GMSS Jikwoyi |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
39 | NIL | NIL | Provision of Civil Works at GGSS Dukpa |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
40 | NIL | NIL | Provision of Civil Works at GDSS Bwari |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
41 | NIL | NIL | Provision of Sporting Facilities at GSS Kuje |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
42 | NIL | NIL | Supply of Encyclopaedia of Science & Technology to All FCT SSS |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
43 | NIL | NIL | Establishment of e-Learning Model Centre (GMSS Jikwoyi) |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
44 | NIL | NIL | Expansion of e-Learning Model Centre (GSS Jabi) |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
45 | NIL | NIL | Expansion of e-Learning Model Centre (SFG G/Lada) |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
46 | NIL | NIL | Provision of 29-Seater School Bus to GDSS Dutse & GSS Gaube |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
47 | NIL | NIL | Provision of 29-Seater School Bus to GSS Pai & GSS Dei-Dei |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
48 | NIL | NIL | Provision of 29-Seater School Bus to GSS Mpape & GSS Kabusa |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
49 | NIL | NIL | Provision of 29-Seater School Bus to GSS Apo & GSS Hajj Camp |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
50 | NIL | NIL | Provision of 29-Seater School Bus to GMSS Jikwoyi & SFG G/Lada |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
51 | NIL | NIL | Provision of Water Tanker to GSS Yaba |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
52 | NIL | NIL | Provision of Water Tanker to GSS Shere |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
53 | NIL | NIL | Supply of Magnetic Board to FCT SSS in AMAC |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
54 | NIL | NIL | Supply of Magnetic Board to FCT SSS in Bwari & G/Lada Area Councils |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
55 | NIL | NIL | Supply of Magnetic Board to FCT SSS in Abaji & Kwali, Kuje Area Councils |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
56 | NIL | NIL | Supply of Biological Models to FCT SSS in AMAC |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
57 | NIL | NIL | Supply of Biological Models to FCT SSS in Bwari & G/Lada Area Councils |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
58 | NIL | NIL | Supply of Biological Models to FCT SSS in Kuje, Abaji & Kwali Area Councils |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
59 | NIL | NIL | Furnishing/Equipping of FCT SEB Headquarters |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
60 | NIL | NIL | Furnishing/Finishing of Science Laboratory at GSS Kwali |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
61 | NIL | NIL | Upgrading of Networking & Installation of e-Accounting Software at SEB Headquarters |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
62 | NIL | NIL | Provision of ICT Facilities for e-Accounting System to FCT SEB Headquarters |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
63 | NIL | NIL | Completion of Perimeter Fencing at GSS G/Lada |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
64 | NIL | NIL | Completion of Perimeter Fencing at GSS Jibi |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
65 | NIL | NIL | Completion of Perimeter Fencing at GSS Kuje |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
66 | NIL | NIL | Construction of Blocks (A) & (B) of Water System Toilet at GSS Mpape |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
67 | NIL | NIL | Construction of Blocks (A) & (B) of Water System Toilet at GSS Pai |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
68 | NIL | NIL | Construction of Blocks (A) & (B) of Water System Toilet at GSS Dei-Dei |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
69 | NIL | NIL | Construction of Blocks (A) & (B) of Water System Toilet at GSS Kabusa |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
70 | NIL | NIL | Construction of Blocks (A) & (B) of Water System Toilet at GDSS Dutse |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
71 | NIL | NIL | Construction of Blocks (A) & (B) of Water System Toilet at GSS Apo |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
72 | NIL | NIL | Construction of Blocks (A) & (B) of Water System Toilet at GSS Kuje |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
73 | NIL | NIL | Construction of Blocks (A) & (B) of Water System Toilet at GDSS Karu |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
74 | NIL | NIL | Construction of Blocks of (A) & (B) Water System Toilet at GDSS G/Lada |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
75 | NIL | NIL | Construction of Blocks of (A) & (B) Water System Toilet at GSS Yangoji |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
76 | NIL | NIL | Construction of Blocks of (A) & (B) Water System Toilet at GSS Karu |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
77 | NIL | NIL | Construction of Blocks of (A) & (B) Water System Toilet at GSS Airport |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
78 | NIL | NIL | Construction of Blocks of (A) & (B) Water System Toilet at GSS Wuse |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
79 | NIL | NIL | Construction of Blocks of (A) & (B) Water System Toilet at GSS Karshi |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
80 | NIL | NIL | Completion of Civil Works at GSS Jiwa |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
81 | NIL | NIL | Furnishing of Library at GSS Wuse & GSS T/Wada |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
82 | NIL | NIL | Furnishing of Library at GSS Garki |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
83 | NIL | NIL | Up-grading of FCT SEB ICT Centre |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
84 | NIL | NIL | Supply of Science Equipment & Reagents to GMSS Jikwoyi |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
85 | NIL | NIL | Supply of Science Equipment & Reagents to GSS Gwarinpa |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
86 | NIL | NIL | Supply of Science Equipment & Reagents to GSS Dei-Dei |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
87 | NIL | NIL | Supply of Science Equipment & Reagents to GSS Yangoji |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
88 | NIL | NIL | Supply of Science Equipment & Reagents to GSS Shere |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
89 | NIL | NIL | Supply of Science Equipment & Reagents to MSS Maitama |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
90 | NIL | NIL | Supply of Science Equipment & Reagents to GSS Lugbe |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
91 | NIL | NIL | Supply of Science Equipment & Reagents to GSS Karshi |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
92 | NIL | NIL | Supply of Science Equipment & Reagents to GSS Jibi |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
93 | NIL | NIL | Supply of Science Equipment & Reagents to GSS Abaji |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
94 | NIL | NIL | Supply of Science Equipment & Reagents to GSS Dangara |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
95 | NIL | NIL | Supply of Home Economics Materials to GSS Dei-Dei |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
96 | NIL | NIL | Supply of Home Economics Materials to GMSS Jikwoyi |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
97 | NIL | NIL | Supply of Home Economics Materials to GSS Kawu |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
98 | NIL | NIL | Supply of Home Economics Materials to GSS Jikwoyi |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
99 | NIL | NIL | Supply of Home Economics Materials to GSS Kwali |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
100 | NIL | NIL | Supply of Home Economics Materials to GSS Mabushi |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
101 | NIL | NIL | Supply of Home Economics Materials to GSS Gawu |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
102 | NIL | NIL | Supply of Home Economics Materials to GSS G/Karya |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
103 | NIL | NIL | Supply of Home Economics Materials to GSS Kubwa |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
104 | NIL | NIL | Supply of Home Economics Materials to GSS Gaube |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
105 | NIL | NIL | Supply of Agric Science Materials to GGSS Abaji, GSSS Abaji, GSS Gawu & GSS Yaba |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
106 | NIL | NIL | Supply of Agric Science Materials to GDSS Bwari, GSS Bwari, GSS Byazhin & GSS Dei-Dei |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
107 | NIL | NIL | Supply of Agric Science Materials to GDSS Dutse, GGSS Dutse, GSS Jibi & GSS Kawu |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
108 | NIL | NIL | Supply of Agric Science Materials to GSS Kubwa, GSS Mpape, GSS Shere & GSS Zuba |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
109 | NIL | NIL | Supply of Agric Science Materials to GSS Dobi, GGSS Dukpa, GDSS G/Lada & SFG G/Lada |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
110 | NIL | NIL | Supply of Agric Science Materials to GSS G/Lada, GSS Hajj Camp, GSS T/Maje & GSS Kwali |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
111 | NIL | NIL | Supply of Agric Science Materials to GSS G/Karya, GSS G/Gwarda, GSS Gaube & GGSSS Kuje |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
112 | NIL | NIL | Supply of Agric Science Materials to GSS Kuje, GSS Rubochi, GSS Dangara & GSS Yangoji |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
113 | NIL | NIL | Supply of Agric Science Materials to GSS Airport, GSS Apo, ADSS Asokoro & GSS Wuse |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
114 | NIL | NIL | Supply of Agric Science Materials to GSS Gwagwa, GSS Gwarinpa, GSS Jabi & GSS Jikwoyi |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
115 | NIL | NIL | Supply of Agric Science Materials to GSS Jiwa, GSS Kabusa, GSS Karshi & GDSS Karu |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
116 | NIL | NIL | Supply of Agric Science Materials to GSS Karu, GSS Lugbe, GSS Mabushi & ADSS Maitama |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
117 | NIL | NIL | Supply of Agric Science Materials to MSS Maitama, GSS Nyanya, GSS T/Wada & GMSS Jikwoyi |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
118 | NIL | NIL | Supply of Library Reference Books to GSS Shere |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
119 | NIL | NIL | Supply of Library Reference Books to GMSS Jikwoyi |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
120 | NIL | NIL | Supply of Library Reference Books to GSS Apo |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
121 | NIL | NIL | Supply of Library Reference Books to GSS Kwali |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
122 | NIL | NIL | Supply of Library Reference Books to GGSSS Kuje |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
123 | NIL | NIL | Supply of Library Reference Books to GSS Gaube |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
124 | NIL | NIL | Supply of Library Reference Books to GSS G/Karya |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
125 | NIL | NIL | Supply of Library Reference Books to GSS Mpape |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
126 | NIL | NIL | Supply of Library Reference Books to GSS Pai |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
127 | NIL | NIL | Installation of Language Laboratory in GGSS Dukpa |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
128 | NIL | NIL | Installation of Language Laboratory in GMSS Jikwoyi |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
129 | NIL | NIL | Installation of Language Laboratory in MSS Maitama |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
130 | NIL | NIL | Installation of Language Laboratory in GGSS Abaji |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
131 | NIL | NIL | Supply of Computer systems & accessories to GSS Gawu & GSS Apo |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
132 | NIL | NIL | Supply of Computer systems & accessories to GDSS Bwari & GSS Dobi |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
133 | NIL | NIL | Supply of Computer systems & accessories to GDSS Dutse-Alhaji & GSS Byazhin |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
134 | NIL | NIL | Supply of Computer systems & accessories to GSS Hajj Camp & GGSS Dukpa |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
135 | NIL | NIL | Supply of Computer systems & accessories to GSS T/Maje & ADSS Asokoro |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
136 | NIL | NIL | Supply of Soccer & Athletics Materials to all FCT SSS |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
137 | NIL | NIL | Supply of Volleyball & Basketball Materials to all FCT SSS |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
138 | NIL | NIL | Supply of Badminton & Hockey Materials to all FCT SSS |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
139 | NIL | NIL | Supply of Clinic Equipment to SEB HQ |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
140 | NIL | NIL | Supply of Clinic Equipment to GGSS Abaji, GSSS Abaji, GSS Gawu, & GSS Yaba |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
141 | NIL | NIL | Supply of Clinic Equipment to GSS Bwari, GGSS Dutse, GSS Shere & GSS Dobi |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
142 | NIL | NIL | Supply of Clinic Equipment to GGSS Dukpa, GSS G/Lada, SFG G/Lada & GSS T/Maje |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
143 | NIL | NIL | Supply of Clinic Equipment to GSS G/Karya, GSS G/Gwarda, GGSSS Kuje & GSS Kuje |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
144 | NIL | NIL | Supply of Clinic Equipment to GSS Rubochi, GSS Dangara, GSS Kwali & GSS Karshi |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
145 | NIL | NIL | Supply of Clinic Equipment to GSS Garki, GSS Wuse, GSS T/Wada & GMSS Jikwoyi |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
146 | NIL | NIL | Provision of Utility Vehicle (Hilux) |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
147 | NIL | NIL | Provision of Utility Vehicle (Toyota Highlander) |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
148 | NIL | NIL | Supply of Materials for the Visually Impaired to FCT SSS |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
149 | NIL | NIL | Supply of Materials for the Hearing Impaired to FCT SSS |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
150 | NIL | NIL | Supply of Materials for the Physically Challenged to FCT SSS |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
151 | NIL | NIL | Supply of Research/Survey Materials to SEB HQ |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
152 | NIL | NIL | Supply of Chalk to FCT SSS in AMAC |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
153 | NIL | NIL | Supply of Chalk to FCT SSS in Bwari & G/Lada Area Councils |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
154 | NIL | NIL | Supply of Chalk to FCT SSS in Kuje, Abaji & Kwali Area Councils |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
155 | NIL | NIL | Provision of 150 sets of Double Bunk Bed/Mattress to GSS Dobi |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
156 | NIL | NIL | Provision of 150 sets of Double Bunk Bed/Mattress to GSS T/Maje |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
157 | NIL | NIL | Provision of 150 sets of Double Bunk Bed/Mattress to GSS G/Karya |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
158 | NIL | NIL | Provision of 150 sets of Double Bunk Bed/Mattress to GSS Dangara |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
159 | NIL | NIL | Provision of 150 sets of Double Bunk Bed/Mattress to GMSS Jikwoyi |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
160 | NIL | NIL | Provision of 50KVA Generator Set to GSS Jabi |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
161 | NIL | NIL | Provision of 50KVA Generator Set to GSS Pai |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
162 | NIL | NIL | Provision of 50KVA Generator Set to GSS T/Maje |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
163 | NIL | NIL | Provision of 50KVA Generator Set to GSS Dobi |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
164 | NIL | NIL | Provision of 50KVA Generator Set to GMSS Jikwoyi |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
165 | NIL | NIL | Provision of Admin/Staffroom Furniture to GSS Mpape |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
166 | NIL | NIL | Provision of Admin/Staffroom Furniture to GSS Pai |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
167 | NIL | NIL | Provision of Admin/Staffroom Furniture to GSS Dei-Dei |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
168 | NIL | NIL | Provision of Admin/Staffroom Furniture to GSS Kabusa |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
169 | NIL | NIL | Provision of Admin/Staffroom furniture to GSS Abaji |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
170 | NIL | NIL | Provision of Admin/Staffroom furniture to GSS Kubwa |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
171 | NIL | NIL | Provision of Admin/Staffroom furniture to GGSS Dutse |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
172 | NIL | NIL | Provision of Admin/Staffroom furniture to GSS G/Lada |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
173 | NIL | NIL | Provision of Admin/Staffroom furniture to GSS Kuje |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
174 | NIL | NIL | Provision of Admin/Staffroom furniture to GSS Bwari |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
175 | NIL | NIL | Provision of Admin/Staffroom furniture to GSS Garki |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
176 | NIL | NIL | Provision of Admin/Staffroom furniture to GSS Gwarinpa |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
177 | NIL | NIL | Provision of 4 sets of classroom furniture to GSS Dobi |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
178 | NIL | NIL | Provision of 4 sets of classroom furniture to MSS Maitama |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
179 | NIL | NIL | Provision of 8 sets of classroom furniture to GSS Kubwa |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
180 | NIL | NIL | Provision of 8 sets of classroom furniture to GSS Hajj Camp |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
181 | NIL | NIL | Provision of 8 sets of classroom furniture to GSS Rubochi |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
182 | NIL | NIL | Provision of 8 sets of classroom furniture to GGSS Abaji |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
183 | NIL | NIL | Provision of 8 sets of classroom furniture to GMSS Jikwoyi |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
184 | NIL | NIL | Provision of 12 sets of classroom furniture to GSS Lugbe |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
185 | NIL | NIL | Provision of 8 sets of Classroom Furniture to GSS Mpape |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
186 | NIL | NIL | Provision of 8 sets of Classroom Furniture to GSS Pai |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
187 | NIL | NIL | Provision of 8 sets of Classroom Furniture to GSS Dei-Dei |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
188 | NIL | NIL | Provision of 8 sets of Classroom Furniture to GSS Kabusa |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
189 | NIL | NIL | Provision of Solar Powered Boreholes to GSS Mpape |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
190 | NIL | NIL | Provision of Solar Powered Boreholes to GSS Pai |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
191 | NIL | NIL | Provision of Solar Powered Boreholes to GSS Dei-Dei |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
192 | NIL | NIL | Provision of Solar Powered Boreholes to GSS Kabusa |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
193 | NIL | NIL | Provision of Solar Powered Borehole to GSS Dobi |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
194 | NIL | NIL | Provision of Solar Powered Borehole to GMSS Jikwoyi |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
195 | NIL | NIL | Provision of Solar Powered Borehole to GSS Gawu |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
196 | NIL | NIL | Provision of Solar Powered Borehole to GGSS Dutse |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
197 | NIL | NIL | Provision of Solar Powered Borehole to GGSS Abaji |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
198 | NIL | NIL | Provision of Solar Powered Borehole to GSS Dangara |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
199 | NIL | NIL | Supply of Stationery Items to FCT SEB Headquarters |  | WORKS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
SDA: | UNIVERSAL BASIC EDUCATION BOARD |  |  |  | DESK OFFICER: | [5 empty] | PHONE:
S/N | CONTRACT NO. | DATE OF CONTRACT | CONTRACT DESCRIPTION | QTY (FOR GOODS ONLY) | TYPES OF CONTRACT | CONTRACTOR'S NAME & LOCATION | CONTRACT VALUES AMOUNT & CURRENCY | PROC. METHOD (OPEN/SELECTIVE) | ORGINAL COMPLETION DATE (MM/DD/YY) | ACTUAL COMPLETION DATE(MM/DD/YY) | AMOUNT PAID TO DATE | BPP CERTIFICATE OF "NO OBJECTION " (IF ANY) FEC APPROVAL
1 | NIL | NIL | Supply of 10 sets of classroom furniture, JSS Naharati |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
2 | NIL | NIL | Supply of 10 sets of classroom furniture, JSS Oroo |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
3 | NIL | NIL | Supply of 10 sets of classroom furniture, JSS Agyana |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
4 | NIL | NIL | Supply of 10 sets of classroom furniture, JSS Shere |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
5 | NIL | NIL | Supply of 10 sets of classroom furniture, Wuse Zone 3 |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
6 | NIL | NIL | Supply of 10 sets of classroom furniture, JSS Wuse Zone 5 |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
7 | NIL | NIL | Supply of 10 sets of classroom furniture, JSS Pasali |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
8 | NIL | NIL | Supply of 10 sets of classroom furniture, JSS Bukpe |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
9 | NIL | NIL | Supply of 10 sets of classroom furniture, JSS Pandagi |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
10 | NIL | NIL | Supply of 5 sets of classroom furniture, JSS Dobi |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
11 | NIL | NIL | Supply of 5 sets of classroom furniture, Lungu Primary School |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
12 | NIL | NIL | Supply of 5 sets of classroom furniture, Katampe Primary School |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
13 | NIL | NIL | Supply of 5 sets of classroom furniture, Karmo Sabo Primary School |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
14 | NIL | NIL | Supply of 5 sets of classroom furniture, Agyana Primary School |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
15 | NIL | NIL | Supply of 5 sets of classroom furniture, Paikon Kore Primary School |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
16 | NIL | NIL | Supply of 5 sets of classroom furniture, Buga Primary School |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
17 | NIL | NIL | Supply of 5 sets of classroom furniture, Yanbabu Primary School |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
18 | NIL | NIL | Supply of 5 sets of classroom furniture, Anguwan Gwandara Primary School |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
19 | NIL | NIL | Supply of 5 sets of classroom furniture, Dobi Primary School |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
20 | NIL | NIL | Supply of 5 sets of classroom furniture, Kwaku Primary School |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
21 | NIL | NIL | Supply of 5 sets of classroom furniture, Farakuti Primary School |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
22 | NIL | NIL | Supply of 5 sets of classroom furniture, Tufa Primary School |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
23 | NIL | NIL | Supply of 5 sets of classroom furniture, Gyedna Primary School |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
24 | NIL | NIL | Supply of 5 sets of classroom furniture, Passo Primary School |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
25 | NIL | NIL | Supply of 5 sets of classroom furniture, Kiyi Primary School |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
26 | NIL | NIL | Supply of 5 sets of classroom furniture, Igu Primary School |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
27 | NIL | NIL | Supply of 5 sets of classroom furniture, Shere Primary School |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
28 | NIL | NIL | Supply of 5 sets of classroom furniture, Kuchiko Primary School |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
29 | NIL | NIL | Supply of 5 sets of classroom furniture, Dutse Bukpama Primary School |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
30 | NIL | NIL | Supply of 5 sets of classroom furniture, Leda |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
31 | NIL | NIL | Purchase of office equipment and furniture, UBEB |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
32 | NIL | NIL | Supply of 10,000 copies of Computer Science Textbooks, JSS |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
33 | NIL | NIL | Supply of 10,000 copies of Introductory Technology Textbooks, JSS |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
34 | NIL | NIL | Supply of 10,000 copies of I.R.S Textbooks, JSS |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
35 | NIL | NIL | Supply of 10,000 copies of C.R.S Textbooks, JSS |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
36 | NIL | NIL | Supply of 10,000 copies of Physical and Health Education Textbooks, JSS |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
37 | NIL | NIL | Supply of 10,000 copies of Civic Education Textbooks, JSS |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
38 | NIL | NIL | Supply of 10,000 copies of Agricultural Science Textbooks, JSS |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
39 | NIL | NIL | Supply of 10,000 copies of Business Education Textbooks, JSS |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
40 | NIL | NIL | Supply of 10,000 copies of Mathematics Textbooks, JSS |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
41 | NIL | NIL | Supply of 10,000 copies of English Textbooks, JSS |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
42 | NIL | NIL | Supply of 25,000 copies of Computer Science Textbooks, Primary |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
43 | NIL | NIL | Supply of 25,000 copies of Basic Science Textbooks, Primary |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
44 | NIL | NIL | Supply of 25,000 copies of I.R.S. Textbooks, Primary |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
45 | NIL | NIL | Supply of 25,000 copies of C.R.S. Textbooks, Primary |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
46 | NIL | NIL | Supply of 25,000 copies of P.H.E Textbooks, Primary |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
47 | NIL | NIL | Supply of 25,000 copies of Civic Education Textbooks, Primary |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
48 | NIL | NIL | Supply of 25,000 copies of Agricultural Science Textbooks, Primary |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
49 | NIL | NIL | Supply of 25,000 copies of Social Studies Textbooks, Primary |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
50 | NIL | NIL | Supply of 25,000 copies of Mathematics Textbooks, Primary |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
51 | NIL | NIL | Supply of 25,000 copies of English Textbooks, Primary |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
52 | NIL | NIL | Provision of 561 first aid box and materials to all primary and jss @20,000 per school, Primary and JSS |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
53 | NIL | NIL | Purchase of 10nos 15-seater buses for schools monitoring of projects and programmes @ 6.6m, UBEB |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
54 | NIL | NIL | Provision of e-learning equipments to JSS in rural schools, JSS |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
55 | NIL | NIL | Provision of e-learning equipments to JSS in rural schools, JSS |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
56 | NIL | NIL | Provision of e-learning equipments to JSS in rural schools, JSS |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
57 | NIL | NIL | Provision of e-learning equipments to JSS in rural schools, JSS |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
58 | NIL | NIL | Provision of e-learning equipments to JSS in rural schools, JSS |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
59 | NIL | NIL | Provision of e-learning equipments to JSS in rural schools, JSS |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
60 | NIL | NIL | Provision of e-learning equipments to JSS in rural schools, JSS |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
SDA: | FCT SCHOLARSHIP BOARD |  |  |  | DESK OFFICER: | [5 empty] | PHONE:
S/N | CONTRACT NO. | DATE OF CONTRACT | CONTRACT DESCRIPTION | QTY (FOR GOODS ONLY) | TYPES OF CONTRACT | CONTRACTOR'S NAME & LOCATION | CONTRACT VALUES AMOUNT & CURRENCY | PROC. METHOD (OPEN/SELECTIVE) | ORGINAL COMPLETION DATE (MM/DD/YY) | ACTUAL COMPLETION DATE(MM/DD/YY) | AMOUNT PAID TO DATE | BPP CERTIFICATE OF "NO OBJECTION " (IF ANY) FEC APPROVAL
| NIL | NIL | Supply of office equipment & Furniture to FCT Scholarship Board |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
| NIL | NIL | Computerization/networking and installation of internet to FCT Scholarship Board |  | GOODS | NIL | NIL | OPEN | NIL | NIL | NIL | NIL
SDA: __________________ DESK OFFICER: _______________________ PHONE: __________________
S/N | CONTRACT NO. | DATE OF CONTRACT | CONTRACT DESCRIPTION | QTY. (FOR GOODS ONLY) | TYPES OF CONTRACT | CONTRACTOR'S NAME & LOGATION | CONTRACT VALUES AMOUNT & CURRENCY | PROC. METHOD (OPEN/ SELECTIVE) | ORIGINAL COMPLETION DATE (MM/DD/YY) | ACTUAL COMPLETION DATE (MM/DD/YY) | AMOUNT PAID TO DATE | BPP CERTIFICATE OF "NO OBJECTION" (IF ANY) FEC APPROVAL
1 | FCDA/F&A/SC/S/42 | 2011-12-10 | Repair of vehicle | NA | Maintenance | M/s ARK Globa Ltd. | N1,675,000.00 | NS | 30/12/2011 | NIL | NIL | NA
2 | FCDA/F&A/SC/47 | 24/11/2011 | Repair of vehicle | NA | Maintenance | M/s Obilly Leather World Ltd. | N1.710,000.00 | NS | 30/12/2011 | NIL | NIL
3 | FCDA/PROC/RPD/ GEN/0182 | 14/12/2011 | Purchase of 5No tyres | 5No | Maintenance | DE EPICO (W.A) LTD. | N240,000.00 | DP | 14/12/2011 | 22/12/2011 | N240,000.00 | NA
4 | FCDA/FED/SC/160/Vol.II | 2011-10-11 | Maintenance on Xerox copiers | 25 No | Maintenance services | M/s Xerox | N3,612,343.38 | DP | Dec. 2012 | Dec. 2012 | N3,612,343.38 | BPP "Cert. of No Objection"
PROCURING ENTITY (MDA): FCT-MUSLIM PILGRIMS WELFARE BOARD, ABUJA.
FINANCIAL YEAR: 2011
BASIC DATA CONTRACT AWARD CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | ADVERTISEMENT DATE AND MEDIA | APROVAL THRESHOLD | PROCURMENET METHOD | BID OPENING DATE | CONTRACTOR | DATE OF CONTRACT AWARD | DATE OF CONTRACT COMMENCEMENT | CONTRACT PERIOD | CONTRACT VALUE (N) | BUDGETARY PROVISION (N) | AMOUNT PAID | EXPECTED COMPLETION DATE | % OF COMPLETION AS AT | REMARKS
AS AT
1 | Construction of office complex at Gudu District | Daily trust May3rd, 2010. | MTB | NCB | 2010-06-01 | Berdotez Associates Ltd | 2011-06-21 | 2012-01-27 | 12 months | N292,648,261.92 | N100m | FEB.,2012 | 2013-01-26 | MARCH
|  | Peopledaily | [9 empty] | N43,897,239.29 |  | 2012
|  | May 3rd, 2010. | [11 empty] | 5%
2 | Supply of Office | Federal Tenders Board(23/8/2010), | MTB | NCB | 2010-09-30 | Nig.Engr Works LTD. | 2011-03-06 | 2011-04-06 | 2 Weeks | N4,926,076.05 | N5m |  | 2011-04-20 | 2011
| Equipment | Peoples Daily | [9 empty] | N4,926,076.05 |  | 100%
Aug.,19 2010.
3 | Fire fighting | Notice Board | Board CEO | Shopping | 2011-04-18 | Naset fire equipment Ltd. | 2011-04-21 | 2011-04-24 | 5 days | N166,110 | N1.7m | N166,110 | 2011-04-30 | 2011
|  | 2011-04-13 | [11 empty] | 100%
4 | Office Equipment (Area Council) | Notice Board | Board CEO | Shopping | 2011-05-24 | Zaisal Global services Ltd | 2011-06-24 | 2011-06-28 | 2 weeks | N606,690 | N1.7m | 606.69 | 2011-07-08 | 2011
|  | 2011-05-17 | [11 empty] | 100%
5 | Office Equipment (head quarter) | Notice Board | Board CEO | Shopping | 2011-06-30 | Khuemen computer and services Ltd | 2011-07-21 | 2011-07-21 | 2 weeks | N975,000 | N1.7m | 975000 | 2011-07-18 | 2011
|  | 2/6/011 | [11 empty] | 100%
5 | Cleaning services | Notice Board | Board CEO | Shopping | 2011-08-02 | Shazus Dry Cleanin.Ltd | 2011-08-26 | 6/9//2011 | 12 months | N231,000/mth | N1,275,000 | N924,000 | 2012-08-31 | 2011
|  | 2011-07-15 | [11 empty] | 72%
SDA: FCT PENSION DEPARTMENT |  |  |  | DESK OFFICER: A.Y. ADAMU |  |  | DESK OFFICER: A.Y. ADAMU |  |  |  | PHONE: 08099744691
S/N | CONTRACT NO. |  | DATE OF |  | CONTRACT |  | QTY (FOR | TYPES OF | CONTRACTOR'S |  | CONTRACT | PROC | ORIGINAL | ACTUAL
|  |  | CONTRACT |  | DESCRIPTION |  | GOODS | CONTRACT | NAME & |  | VALUES | METHOD | COMPLETION | COMPLETI
[7 empty] | ONLY) |  | LOCATION |  | AMOUNT & | (OPEN/ | DATE | ON DATE
[11 empty] | CURRENCY | SELECTIVE | (MM/DD/YY) | (MM/DD/YY
1 | FCTA/TB(2011) |  | 02.11.2011 |  | PROCUREMEN |  |  | DIRECT PRO | M/S LANRE SHIT |  | N4,887,750. | SELECTIVE | 31.10.2011 | 06.12.2011
| 12 |  |  |  | T OF UTILITY |  |  | CUREMENT | TU MOTORS |  | 0
[5 empty] | VEHICLE |  |  |  | NIG. LTD PLOT
1504 MABUSHI
ABUJA
SDA: FCT WATER BOARD DESK OFFICER: Engr. A. O. Akande PHONE: 08065381144
S/N | CONTRACT NO. | DATE OF CONTRACT | CONTRACT DESCRIPTION | QTY (FOR GOODS ONLY) | TYPES OF CONTRACT | CONTRACTOR'S NAME & LOCATION | CONTRACT VALUES AMOUNT & CURRENCY | PROC. METHOD (OPEN/SELECTIVE) | ORIGINAL COMPLETION DATE (MM/DD/YY) | ACTUAL COMPLETION DATE (MM/DD/YY) | AMT PAID TO DATE | BPP CERTIFICATE OF "NO OBJECTION" (IF ANY) FEC APPROVAL
1 | FCT/WB/17/S.395/T/135 | 24 Nov, 2011 | Rehabilitation of LUD Treatment Plant II | — | Works | M/S Cupero Nig Ltd Plot 14 close 'B' link road U/Rimi GRA, Kaduna, Kaduna State | 1018980566.82 | OPEN | 23 March, 2013 | On-Going | NIL | BPP/RP7/10/Vol.1/465
2 | FCT/TB/(2011)14(4) | 3 Nov, 2011 | Supply of Laboratory Reagents | LS | Goods | Messrs Onyishi Intl Ltd No1 Aso Road , Mararaba Gurku, Karu LGA Nassarawa State. | N42,827,938.90 | OPEN | 2 Nov, 2012 | Completed | NIL | BPP/S.1/Vol. IX/11/094
3 | FCT/TB/(2011)14(3) | 3 Nov, 2011 | Supply of Water Treatment Chemicals (Gaseous Chlorine) | 220Cylinders | Goods | Messrs Gojac Nig Co. Ltd Plot 16 Olorungbon Street Anthony Village, Lagos | N97,873,545.00 | OPEN | 2 Nov, 2012 | Completed | NIL | BPP/S.1/Vol.IX/11/094
4 | FCT/TB/(2011)14(1) | 3 Nov, 2011 | Supply of Water Treatment Chemicals (Aluminium Sulphate) | 1180Tons | Goods | Messrs Eco Water W. A. Mngt. Ltd 122-132 Oshodi-Apapa Expressway Isolo, Lagos | N97,881,000.00 | OPEN | 2 Nov, 2012 | Completed | NIL | BPP/S.1/Vol. IX/11/094
5 | FCT/TB/(2011)14(2) | 3 Nov, 2011 | Supply of Water Treatment Chemicals (HTH & LIME) | 480Tons Lime & 1000 Drums HTH | Goods |  | N87,318,000.00 | OPEN | 2 Nov, 2012 | Completed | NIL | BPP/S.1/Vol. IX/11/094
SDA: LEGAL SERVICES SECRETARIAT DESK OFFICER: C. M. MAKOJI PHONE: 08055408505
S/N | CONTRACT NO. | DATE OF CONTRACT | CONTRACT DESCRIPTION | QTY (FOR GOODS ONLY) | TYPES OF CONTRACT | CONTRACTOR’S NAME & LOGATION | CONTRACT VALUES AMOUNT & CURRENCY | PROC. METHOD (OPEN/SELECTIVE) | ORIGINAL COMPLETION DATE (MM/DD/YY) | ACTUAL COMPLETION DATE (MM/DD/YY) | AMT PAID TO DATE | BPP CERTIFICATE OF “NO OBJECTION” (IF ANY) FEC APPROVAL
1 | FCTA/LSS/TB/2011/35 | 2011-12-05 | Supply of 2No Peugeot expert Tepee utility vehicles | 2 | Supply | M/S PAN NIG. LTD Plot 1144, Pan Drive Kakuri Industrial Estate, Kaduna | N11,235,000.00 | Direct | 2011-12-26 |  | NIL | BPP/S.1/11/SP/Vol. II/161
2 | FCTA/LSS/TB/2011/36 | 2011-12-13 | Supply of 1No Peugeot 308 pack Manual Transmission | 1 | Supply | M/S PAN NIG. Ltd Plot 1144, Pan Drive, kakuri Industrial Estate, Kaduna. | N3,924,601.80 | Direct | 2012-01-03 |  | NIL | BPP/S.1/11/SP/Vol. II/161
3 | FCTA/LSS/TB/2011/37 | 2011-12-26 | Supply of 1No Toyota Hilux 4 x 4 double cabin and 1No Toyota Hilux 2 x 4 Double Cabin |  | Supply | M/S Kojo Motors | N10,012,500.00 | Direct | 2012-01-16 |  | NIL | BPP/S.1/11/SP/Vol. II/161
Plot 1209, Cadastral Zone B06 Mabushi District, Abuja
SDA: Security Services Department. Desk Officer: Ogu Emmanuel. Phone No: 08059651354
S/N | Contract No. | Date of Contract | Contract Description | Qty (For Goods Only) | Types of Contract | Contractor’s Name & Location | Contract Values Amount & Current | Proc. Method (Open/ | Original Completion Date (MM/DD/YY) | Actual Completion Date (MM/DD/YY | Amount Paid to Date | BPP Certificate of “No Objection” (If any) FEC Approval
Selective)
1 | FCTA/TB (2010) 87 | 19th January | Award of contract for furnishing of 40nos. operational containers | 40nos. | Goods | M/S Sidewell International Limited | N89,491,416 | Open Bidding | 4weeks | On going | Nil | Nil
2 | FCTA/ TB (2010)/85 | 8th March 2011 | Award for the supply and installation of communication Gadgets | 1no. | Goods | M/S Ceeray Integrated Services Limited | N 91,786,563.25 | Open Bidding | 4weeks | On going | Nil | Nil
3 | FCT/AMMC/UA/335/1/45 | 2011-12-01 | Proposal for supply and installation of Sky Star Aerial Surveillance Equipment 1no. Sky Star Tactical Aerostat |  | Goods | International Security Consultant and Allied Services Limited | N 295,000,650.00 | Selective | Nil | On going | Nil | Yes
DETAILS OF CONTRACTS AWARDED BY MDAs 2009, 2010 & 2011
S/N | PROJECT | CONTRACTOR | DATE OF AWARD | DURATION | CONTRACT SUM | TOTAL AMOUNT CERTIFIED | % COMPLETION | AMOUNT PAID | REMARKS/COMMENTS
1 | Construction of Perimeter Fencing & Gate House For MDGs Supported Youth Centre at Nyanya FCT-Abuja. | SECURITY & COMM. NIG. LTD. |  | 70% | 14000000
2 | Landscaping For MDGs Supported Youth Centre at Nyanya FCT-Abuja. | SAAT & SECURITY NIG. LTD. |  | 100% | 8950000
3 | Construction of Perimeter Fencing & Gate House For MDGs Supported Youth Centre at G/lada FCT-Abuja. | MAFOZO VENTURES NIG. LTD. |  | 0% | 13150000
4 | Landscaping For MDGs Supported Youth Centre at G/lada FCT-Abuja. | LARAI INTERNATIONAL RESOURCES LTD. |  | 0% | 8500000
5 | Construction of Market Stalls at Yangoji, FCT-Abuja. | GRACECOM INTEGRATED SERVICES LTD. |  | 60% | 18500000
6 | Procurement of Equipment at Yangoji Pal Centre. | ROMBERG LTD. |  | 100% | 4500000
7 | Rehabilitation & Equipping of FCT, VCT, Bwari. | MARI-TARI NIG. LTD. |  | 80% | 140000000
SDA: TRANSPORTATION SECRETARIAT DESK OFFICER: KUMSAL N. WUYEP Phone: 08023352552 .
DEPARTMENT OF TRANSPORTATION
S/NO | CONTRACT NO | DATE OF CONTRACT | CONTRACT DESCRIPTION | QTY (FOR GOODS ONLY) | TYPES OF CONTRACT | CONTRACTOR'S NAME AND LOCATION | CONTRACT VALUES AMOUNT AND CURRENCY | PROCURE-MENT METHOD (OPEN/ SELECTIVE) | ORIGINAL COMPLETION DATE (MM/DD/YY) | ACTUAL COMPLETION DATE (MM/DD/YY) | AMOUNT PAID TO DATE | BPP CERTIFICATE OF "NO OBJECTION" (IF ANY) FEC APPROVAL
1 | EC 19(07)39/F EC/200/TS/1 | 25th May 2007 | Design and development of 60.67 km of Standard Gauge Rail track within FCT. | Nil | Works | Messrs China Civil Engineering Construction Corporation (CCECC) Nig. Limited. Abuja | US$841,645,898 | Selective | 25th May, 2011 | 25th December, 2015 | N22,682,022,780.32 | FEC APROVAL
2 | EC 27(10) 5 | 31st Aug. 2010. | Project Management Services for the Supervision of Lots 1 & 3 of Abuja Mass Rail Transit Project. | Nil | Consultant Services | Messrs Transurb Technirail Consults Limited. Abuja | N1,289,958,088.00 | Open | 31st Sept, 2014 | 31st Sept, 2014. | N555,618,522.36 | NO Objection: FEC APPROVAL
3 | FCTA/TB/(2009)76 | 24th Nov, 2009 | Survey of Abuja Traffic Information System. (Conducting Origin-Destination Studies) | Nil | Consultant Services | Messrs Channel Engineering Ltd. Kaduna | N52,313,310.00 | Open | July, 2010 | March, 2012 | N34,003,651.5 | NA
4 | SEC/TSTB/2011/AWD/07 | 14th Oct. 2011 | Supervision of the Construction of Four (4) Pedestrian Bridges along Nnamdi Azikiwe Expressway in FCT | Nil | Consultant Services | Messrs Daniel-Caleb Projects Ltd. Abuja | N46,650,008.51 | Open | March, 2011 | July, 2012 | NIL | NA
DEPARTMENT OF PUBLIC TRANSPORTATION
S/N | CONTRACT NO. | DATE OF CONTRACT | CONTRACT DESCRIPTION | QTY (FOR GOODS ONLY) | TYPES OF CONTRACT | CONTRACTOR'S NAME & LOCATION | CONTRACT VALUES, AMOUNT & CURRENCY | PROC. METHOD (OPEN/ SELECTIVE) | ORIGINAL COMPLETION DATE (MM/DD/YY) | ACTUAL COMPLETION DATE (MM/DD/YY) | AMT PAID TO DATE | BPP CERTIFICATE OF ''NO OBJECTION'' (IF ANY) FEC APPROVAL
1 | FCTA/TB/(2010)90 | 19th Jan. 2011 | Upgrading of 74 existing signalised intersections to LED and solar powered (LOT1). | NIL | Works | M/s Interproject Engineering Services Nig. Ltd / Abuja | N408563505 | Open | Feb;2013 |  | Nil | FCTA
2 | FCTA/TB/(2010)114 | 21st March, 2011 | Provision of Solar cat-eye for road signs-EFI power specification for Utako, Jabi, Garki, Wuse, Asokoro, Maitama & Central Business District. | NIL | Works | M/s favored Global Ltd/Abuja. | N407646618.75 | Open | March, 2012 |  | Mob. Advance N61,164,992.81 | FCTA
3 | FCTA/TB/(2011)97 | 22nd Feb., 2011 | Removal of Speed bumps and installation of New structure. | NIL | Works | M/s Solar Force Nig. Ltd/ Abuja. | N363893178.6 | Open | August, 2012 |  | Mob. Advance N54,597,476.79 | FCTA
4 | FCTA/TB/(2010)97 | 31st August, 2010 | Design & Construction of traffic light signals at 20-at-grade intersections in Abuja. | NIL | Works | M/s J. patel & Sons Nig. Ltd./ Abuja | N380816824.82 | Open | Oct.; 2011 |  | Nil | FCTA
NB: Actual completion date cannot be determined due to inadequate funding of the projects.
DEPARTMENT OF ADMIN AND FINANCE
S/N | CONTRACT NO. | DATE OF CONTRACT | CONTRACT DESCRIPTION | QTY (FOR GOODS ONLY) | TYPES OF CONTRACT | CONTRACTOR'S NAME & LOCATION | CONTRACT VALUES, AMOUNT & CURRENCY | PROC. METHOD (OPEN/ SELECTIVE) | ORIGINAL COMPLETION DATE (MM/DD/YY) | ACTUAL COMPLETION DATE (MM/DD/YY) | AMT PAID TO DATE | BPP CERTIFICATE OF ''NO OBJECTION'' (IF ANY) FEC APPROVAL
1 | SEC/TSTB/2011/12 | 12th Dec, 2011 | Design & installation of Accounting Software | NIL | Works | M/s Kor Computer & General Ent. | N9,750,000.00 | Open | 23rd December, 2011 | 24th December, 2011 | Nil | N/A
2 | SEC/TSTB/2011/13 | 12th Dec, 2011 | Supply of Computers and Accessories | 8 Desktop 6 Laptops | Goods | M/s Go-Tech Computer Systems & General Ent. | N9,889,000.00 | Open | 23rd December, 2011 | 23rd December, 2011 | Nil | N/A
3 | SEC/TSTB/2011/11 | 12th Dec, 2011 | Supply of Toyota Hilux Vehicle | 1 No. | Goods | M/s Elizade Nigeria Ltd. | N5,145,000.00 | Open | 23rd December, 2011 | 30th January, 2012 | Nil | N/A

## SGOFPS
PROCURING ENTITY(MDA) : FED MIN OF JUSTICE
PROCURING ENTITY(MDA) : |  | SOLICITOR-GENERAL OF THE FEDERATION AND PERMANENT SECRETARY
MINISTRY: JUSTICE |  | JUSTICE
FINANCIAL YEAR |  | 2010 | 2010
| BASIC DATA CONTRACT AWARD CONTRACT IMPLEMENTATION |  |  |  | CONTRACT AWARD CONTRACT IMPLEMENTATION | [5 empty] | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION |  | ADVERTISMENT DATE AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | CONTRACTOR | DATE OF CONTRACT AWARD | DATE OF CONTRACT COMMENCEMENT | CONTRACT PERIOD | CONTRACT VALUE (N) | BUDGETRY PROVISION (N) | AMONUT PAID AS AT | EXPECTED COMPLETION DATE | % OF COMPLETION AS AT | REMARKS
1 | Construction of |  | Punch News- |  | Competitive | 13th | Trenko | March 25th | 28th March, | Subject to | 2013885691.53 |  | 302,082,
| Customized |  | Paper Aug. 23rd |  | Bidding | August, | International | 2011 | 2011 | budgetary |  |  | 853.73 | 1 Year | 15%
| Library |  | 2010 |  |  | 2010 | (Nig.) Ltd. |  |  | funding
| Infrastructure and |  | Fed. Tenders | FEC
| Purchase of Law |  | Journal June 14,
| Books |  | 2010
Daily Trust, 10th
May, 2010
2 | Acquisition of Law |  |  |  |  | June | Odade | 30th Nov.,
| Books, Law Reports |  | " | MTB | " | 30th | Investment | 2010 | 2nd Dec., | 6 Weeks | 14400000 | 14400 | 14400000 | Completed | 100%
| and Periodicals |  |  |  |  | 2010 | Ltd. |  | 2010 |  |  | 0
3 | Establishment of |  | " | MTB | " | 6th June, | Alteq.ICT | 30th Nov., | 1st Dec., | 10 Weeks | 22500000 | 22500000 | 22,500,000. 22,500,000 | Completed | 100%
| Justice Data Bank |  |  |  |  | 2010 | Ltd. | 2010 | 2010
4 | Renovation of Makurdi |  | Daily Trust, 10th
| & Akure Zonal Offices |  | May, 2010 | Accounting | Open Competitive |  | Praisegate | 30th Dec., | 30th Dec., | 2 Weeks | 2692249 | 2692249 | 2692249 | Completed | 100%
|  |  | Punch 10th May, | Officer | Bidding | 18th )ct., | Global Ventures | 2010 | 2010
|  |  | 2010 |  |  | 2010 | Ltd
Fed. Tenders
Journal 14th June
2010
| Renovation of Kano |  |  | Accounting | " | 18th Oct., | Sahil Engr. | 30th Dec., | 30th Dec., |  | 3274335.9 |  | 3274335 | Completed | 100%
| and Sokoto Zonal |  | " | Officer |  | 2010 | Services Ltd. | 2010 | 2010 | 2 Weeks | 3274335.9 |  | 90
Offices
| Renovation of Yola |  |  |  | Open Competitive | " | El-Jalil (Nig) | " | " | 2 Weeks | 2644015 | 2644015 | 2644015 | Completed | 100%
| Maiduguri |  | " | " | Bidding |  | Ltd.
Zonal Offices
| Renovation of Enugu |  |  |  |  | 18th Oct., | Simpson | 30th Dec., | 30/Dec., |  | 3413768 | 3,413, | 3,413, | Completed | 100%
| and Owerri Zonal |  | " | " | " | 2010 | Ventures | 2010 | 2010 | 2 Weeks | 60 | 768.6 | 768.6
Offices
Renovation of
| Portharcourt and |  |  | Accounting | Open Competitive | 18th Oct., | Hinorm Investment | 30th Dec., | 30th Dec., |  | 3901199.5 | 3901199.5 | 3901199 | Completed | 100%
| Benin Zonal Offices |  | " | Officer | Bidding | 2010 | Ltd. | 2010 | 2010 | 3 Weeks |  |  | 50
PROCURING ENTITY(MDA) :
PROCURING ENTITY(MDA) : |  | FED MIN OF JUSTICE
MINISTRY: JUSTICE |  | JUSTICE
FINANCIAL YEAR |  | 2010 | 2011
| BASIC DATA CONTRACT AWARD CONTRACT IMPLEMENTATION |  |  |  | CONTRACT AWARD CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION |  | ADVERTISMENT DATE AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | CONTRACTOR | DATE OF CONTRACT AWARD | DATE OF CONTRACT COMMENCEMENT | CONTRACT PERIOD |  | BUDGETRY PROVISION (N) | AMONUT PAID AS AT | EXPECTED COMPLETION DATE | % OF COMPLETION AS AT | REMARKS
1 | Procurement |  | Punch 29th Aug. | Ministerial | Open | 10th | Messrs | 8th Dec., | 8th Oct., | 2 Weeks | 10243117 | 10262690 | 10243117
| of Computers, |  | 2011 | Tenders | Competitive | Oct., | Information | 2011 | 2011 |  | 50 |  | 50 | Completed | 100%
| Database Manage- |  | Leadership | Board | Bidding | 2011 | Management
| ment System, ICT/ |  | Newspaper |  |  |  | Resources
| Justice Data Bank |  | 29th Aug., |  |  |  | Nig. Ltd.
| Equipment |  | 2011
Federal Tenders
Journal
5th Sept., 2011
2 | Acquisition of |  |  | Accounting | Open | 10th | 02 Interactive | 17th Nov., | 17th Nov., | 4 Weeks | 2677450 | 2700708 | 2,677,450Completed |  | 100%
| Law Books, Law |  | " | Officer | Competitive | Oct., | Ltd. | 2011 | 2011
| Reports and |  |  |  | Bidding | 2011
Periodicals
3 | Rehabilitation of | [5 empty] | Messrs | 16th Nov., | 21st Nov. | 3 Weeks2,305,700 |  | 6481695 | 6,305,900 " |  | 100%
| Office Building |  | " | " | " | " | Hinorm | 2011 | 2011
| Lagos Liaison | [5 empty] | Investment
| Office. | [5 empty] | Ltd.
2082906271.83
Note on H6: :
Note on H52: :

## FMOT
PROCURING ENTITY (MDA) : |  | COUNCIL FOR THE REGULATION OF FREIGHT FORWARDING IN NIGERIA
MINISTRY :
FINANCIAL YEAR : |  | 2011
| BASIC DATA |  |  |  |  | CONTRACT AWARD | [5 empty] | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | ADVERTISEMENT DATE AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | CONTRACTOR | DATE OF CONTRACT AWARD | DATE OF CONTRACT COMMENCEMENT | CONTRACT PERIOD | CONTRACT VALUE (=N=) | BUDGETARY PROVISION (=N=) | AMOUNT PAID AS AT Dec. 2011 | EXPECTED COMPLETION DATE | PERCENTAGE OF COMPLETION AS AT January 2012 | REMARKS
1 | CONSULTANCY SERVICE FOR THE ESTABLISHMENT OF MICROFINANCE BANK | IOTH OCTOBER, 2011,DAILY TRUST, VANGUARD&FED. TENDER JOURNAL | CRFFN | COST AND QUALITY BASE SELECTION | OCT.24TH ,2011 | UNIS MULTILINKS INVESTMENTS LTD | DEC. 14TH, 2011 | DEC.15TH, 2011 | 3WEEKS | 33000000 | 35000000 | 29700000 | 2012-01-01 | 84.85% | N5,300,000 balance outstanding
2 | CONSULTANCY SERVICE FOR THE ESTABLISHMENT OF COOPERATIVE SOCIETY | IOTH OCTOBER, 2011,DAILY TRUST, VANGUARD&FED. TENDER JOURNAL | CRFFN | LEAST COST SELECTION | OCT.24TH ,2011 | UNIS MULTILINKS INVESTMENTS LTD | DEC. 14TH, 2011 | DEC.15TH, 2011 | 3WEEKS | 4800000 | 5000000 | - | 2012-01-01 | - | -
3 | PURCHASE OF COMPUTER AND COMPUTER EQUIPMENTS | 13TH OCTOBER,2011, VANGUARD, DAILY TRUST& FED. TENDER JOURNAL | CRFFN | NATIONAL COMPETITIVE BIDDING | OCT.13TH ,2011 | PILOT KIRK PROCUREMENT SERVICES LTD. | DEC. 14TH, 2011 | DEC. 15TH, 2011 | 3WEEKS | 5400000 | 5401416 | - | 2012-01-01 | - | -
4 | PURCHASE OF KITS FOR SECURITY PERSONNEL | 13TH OCTOBER,2011, VANGUARD, DAILY TRUST& FED. TENDER JOURNAL | CRFFN | NATIONAL COMPETITIVE BIDDING | OCT.13TH ,2011 | CAPITALWOOD INDUSTRIES LTD. | DEC. 14TH, 2011 | DEC. 15TH, 2011 | 3WEEKS | 3150000 | 5401416 | 3150000 | 2012-01-01 | 58.31% | N2,251,416 balance outstanding
5 | SUPPLY OF COMPUTER SOFTWARE | 13TH OCTOBER,2011, VANGUARD, DAILY TRUST& FED. TENDER JOURNAL | CRFFN | NATIONAL COMPETITIVE BIDDING | OCT.13TH ,2011 | YET TO BE AWARDED | YET TO BE AWARDED | DEC. 15TH, 2011 | 3WEEKS | 2700708 | 2700708 |  |  |  | Contract Awarded
6 | SUPPLY OF PRINTERS | 13TH OCTOBER,2011, VANGUARD, DAILY TRUST& FED. TENDER JOURNAL | CRFFN | NATIONAL COMPETITIVE BIDDING | OCT.13TH ,2011 | YET TO BE AWARDED | YET TO BE AWARDED | DEC. 15TH, 2011 | 3WEEKS | 3267857 | 3267857 |  |  |  | Contract Awarded
7 | SUPPLY OF UTILITY VEHICLES | 7TH NOVEMBER , 2011& DAILY TRUST , VANGUARD & FED. TENDER JOURNAL | CRFFN | NATIONAL COMPETITIVE BIDDING | DEC.19TH,2011 | PILOT KIRK PROCUREMENT SERVICES LTD. | DEC. 14TH, 2011 | DEC. 15TH, 2011 | 3WEEKS | 32178637.6 | 35757374 | 21150000 | 2012-01-01 | 59.15% | N14,607,374 balance outstanding
8 | PURCHASE OF PHOTOCOPYING MACHINES | N/A | CEO | NATIONAL SHOPPING | OCT.13TH ,2011 | AKIN SHARP SERVICES LTD. | DEC. 14TH, 2011 | DEC.15TH, 2011 | 3WEEKS | 1485389 | 1966010 | 1336850 | 2012-01-01 | 66.97% | N659,160 balance outstanding
85982591.6

## FMOWA
PROCUREMENT RECORDS
PROCURING ENTITY (MDA)
MINISTRY: FEDERAL MINISTRY OF WOMEN AFFAIRS AND SOCIAL DEVELOPMENT, ABUJA
FINANCIAL YEAR: 2011
| BASIC DATA |  |  |  |  | CONTRACT AWARD | [5 empty] | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | ADVERTISEMENT DATE AND MEDIA | APPROVAL THRESHOLD | PROC. METHOD | BID OPENING DATE | CONTRACTOR | DATE OF CONTRACT AWARD | DATE OF CONTRACT COMMENCEMENT | CONT. PERIOD | CONTRACT VALUE (N) | BUDGETARY PROVISION (N) | AMOUNT PAID AS AT | EXPTD COMPTN DATE | % OF COMPTN AS AT | REMARKS | REMKS
1 | Supply of Physsically Impaired Equipment | Tenders Journal, Dec. 13, 2010/ Thisday Nov. 30, 2010 |  | OCB | 2011-12-01 | M/s Simdi West Africa Ltd. | 31/03/2011 | 31/03/11 | 2 Wks | 15212600 | 43795620 | 15212600 | 2Wks | Completed
2 | Supply of Braille Equipment and Material | Tenders Journal, Dec. 13, 2010/ Thisday Nov. 30, 2010 | MTB Approval | OCB | 2011-12-01 | M/s Waniyos Investment Ltd. | 28/03/2011 | 28/03/11 | 2 Wks | 26116278 | 29179080 | 26116278 | 2Wks | Completed
3 | Procurement of Empowerment Equipment for V.V.F Victims - Bauchi State | Ministry's Notice Board (November 2nd, 2011) | Permanent Secretary | OCB | 16/11/11 | M/s Dubrick Nig. Ltd | 14/12/2011 | 14/12/11 | 1Wk | 3061312.5 | 25257493.77 | 3061312.5 | 1Wk | Completed
4 | Procurement of Empowerment Equipment for V.V.F Victims - Ogun State | Ministry's Notice Board (November 2nd, 2011) | Permanent Secretary | OCB | 16/11/11 | M/s Socio Global Investment Ltd | 14/12/2011 | 14/12/11 | 1Wk | 3061312.5 | 25257493.77 | 3061312.5 | 1Wk | Completed
5 | Procurement of Empowerment Equipment for V.V.F Victims - Imo State | Ministry's Notice Board (November 2nd, 2011) | Permanent Secretary | OCB | 16/11/11 | M/s Positive Technologies Ltd | 14/12/2011 | 14/12/11 | 1Wk | 3055500 | 25257493.77 |  | 1Wk | Completed
6 | Landscaping and External Workss OVC Centre Makurdi Benue State | Ministry's Notice Board (November 2nd, 2011) | Permanent Secretary | OCB | 16/11/11 | M/s JIL Engineering Associates Ltd | 14/12/2011 | 14/12/11 | 1Wk | 3587670 | 3620569 | 3587670 | 1Wk | Completed
7 | Renovation and Rehabilitation Shelter Centre for Trafficked Chilodren at Samanda, Ibadan, Oyo State | Ministry's Notice Board (November 2nd, 2011) | Permanent Secretary | OCB | 16/11/11 | M/s Loma Multi-National Ltd | 14/12/2011 | 14/12/11 | 1Wk | 4956500 | 4957000 | 4956500 | 1Wk | Completed
8 | Supply of Clothing Materials to Old People's Home | Ministry's Notice Board (November 2nd, 2011) | Permanent Secretary | OCB | 16/11/11 | M/s Kings Favour Integrated Concept Ltd | 22/12/2011 | 22/12/11 | 1Wk | 4726000 | 5475700 | 4726000 | 1Wk | Completed
9 | Supply of Toiletries to Old People's Home | Ministry's Notice Board (November 2nd, 2011) | Permanent Secretary | OCB | 16/11/11 | M/s Judyk Ventures (Nig.) Ltd | 15/12/2011 | 15/12/11 | 1Wk | 481, 950.00 | 481950 | 481, 950.00 | 1Wk | Completed
10 | Supply of Beverages to Old People's Home | Ministry's Notice Board (November 2nd, 2011) | Permanent Secretary | OCB | 16/11/11 | M/s Eagle Eye Logistics Services Ltd | 15/12/2011 | 15/12/11 | 1Wk | 1532000 | 1532250 | 1532000 | 1Wk | Completed
11 | Supply of Food Items to Old People's Home | Ministry's Notice Board (November 2nd, 2011) | Permanent Secretary | OCB | 16/11/11 | M/s Gold Burns Ltd | 15/12/2011 | 15/12/11 | 1Wk | 2511125 | 2514375 | 2511125 | 1Wk | Completed
12 | Renovation of Gate House and Fence | Ministry's Notice Board (November 2nd, 2011) | Permanent Secretary | OCB | 16/11/11 | M/s Patsoj Nig. Ent. | 15/12/2011 | 15/12/11 | 1Wk | 4197260 | 4273357 | 4197260 | 1Wk | Completed
13 | Installation of Mosquito Nets in 9 No. Building, Rug and Venetian Blinds in the Admin Block and Principal Office | Ministry's Notice Board (November 2nd, 2011) | Permanent Secretary | OCB | 16/11/11 | M/s Bandi Engineering & Construction Ltd. | 14/12/2011 | 14/12/11 | 1Wk | 4982745 | 4982745 | 4982745 | 1Wk | Completed
14 | Supply, Installation and Powering of 1No. 1000KVA Perkijns Generator | Ministry's Notice Board (November 2nd, 2011) | MTB Approval | OCB | 16/11/11 | M/s D.P&B Investment Ltd. |  |  | 1Wk | 7195750 | 25447944.39 | 7195750 | 1Wk | Completed
15 | Supply of Grinding/Smoothing Machine (Fuel Type) 5.5HP/5.0HP Honda Brand with Accessories | Ministry's Notice Board (November 2nd, 2011) | Permanent Secretary | OCB | 16/11/211 | M/s Major Baja Ventures Ltd | 14/12/2011 | 14/12/11 | 1Wk | 4218240 | 4218240 | 4218240 | 1Wk | Completed
16 | Supply of Sewing Machines (Butterfly with Folding Top - China) and 50Nos. Butterfly Over-Lock Machines GNY 113 | Ministry's Notice Board (November 2nd, 2011) | Permanent Secretary | OCB | 16/11/11 | M/s De-Merit Technology Ltd | 15/12/2011 | 15/12/11 | 1Wk | 3016000 | 3016000 | 3016000 | 1Wk | Completed
17 | Supply of Welding Machines (ESAB) 140 German Made | Ministry's Notice Board (November 2nd, 2011) | Permanent Secretary | OCB | 16/11/11 | M/s Green Belt Integrated Concepts | 15/12/2011 | 15/12/11 | 1Wk | 2925000 | 2925000 | 2925000 | 1Wk | Completed
18 | Supply of Sparying Machines with Accessories i.e. Compressor and Hair Barbing Clippers (WAHL) Super Tapper USA | Ministry's Notice Board (November 2nd, 2011) | Permanent Secretary | OCB | 16/11/11 | M/s Meebra Ventures | 15/12/2011 | 15/12/11 | 1Wk | 2225500 | 2225500 | 2225500 | 1Wk | Completed
19 | Nationwide Survey on Approved Schools, Remand Homes and Borstals | Ministry's Notice Board (November 2nd, 2011) | Permanent Secretary | OCB |  | Inter-Gender Development Centre | 22/12/2011 | 22/12/11 |  | 4924000 | 5000000 | 4924000 |  | Completed
20 | Supply of Office Equipment | Ministry's Notice Board (November 2nd, 2011) | Permanent Secretary | OCB |  | Raamalton Nig. Ltd. | 13/09/2011 | 13/09/11 | 2 Wks | 3813105 |  | 3813105 | 2Wks | Completed
21 | Cleaning and Janitorial Services for Federal Ministry of Women Affairs and Social Development |  | MTB Approval | OCB |  | Yougotek Limited | 13/09/2011 | 13/09/11 | 1 Yr | 5798761.08 | 8460486.22 | 5798761.08 | 31/12/2011 | Completed
22 | Provision of Non Security Documents | Ministry's Notice Board (August 24th, 2011) | Permanent Secretary | OCB | 2011-06-09 | Mark and Chain Ventures Ltd. | 13/09/2011 | 13/09/11 | 2 Wks | 4759000 | 9229638 | 4759000 | 2Wks | Completed
23 | Supply of Toner Inks | Ministry's Notice Board (August 24th, 2011) | Permanent Secretary | OCB | 2011-06-09 | Adansa Services Ltd. | 13/09/2011 | 13/09/11 | 2 Wks | 4856250 | 60735823 | 4856250 | 2Wks | Completed
24 | Supply of Electronic Items | Ministry's Notice Board (August 24th, 2011) | Permanent Secretary | OCB | 2011-06-09 | Hydermax Consulting Ltd | 13/09/2011 | 13/09/11 | 2 Wks | 4798500 | 60735823 | 4798500 | 2Wks | Completed
25 | Supply of Stationery Items | Ministry's Notice Board (August 24th, 2011) | Permanent Secretary | OCB | 2011-06-09 | Demerit Technology Ltd | 13/09/2011 | 13/09/11 | 2 Wks | 3223800 | 60735823 | 3223800 | 2Wks | Completed
26 | Supply of Motor Vehicle Parts | Ministry's Notice Board (August 24th, 2011) | Permanent Secretary | OCB | 2011-06-09 | U.B.G Nig. Ltd. | 13/09/2011 | 13/09/11 | 2 Wks | 4394395 | 16321911 | 4394395 | 2Wks | Completed
27 | Supply of Computer/Photocopy Machine Accessories | Ministry's Notice Board (August 24th, 2011) | Permanent Secretary | OCB | 2011-06-09 | JAFS Nig. Ltd. | 13/09/2011 | 13/09/11 | 2 Wks | 4980850 | 16321911 | 4980850 | 2Wks | Completed
28 | Supply of Electrical Items | Ministry's Notice Board (August 24th, 2011) | Permanent Secretary | OCB | 2011-06-09 | I-Mma Nig. Ent. | 13/09/2011 | 13/09/11 | 2 Wks | 3989500 | 16321911 | 3989500 | 2Wks | Completed
29 | Supply of Office Furniture | Ministry's Notice Board (August 24th, 2011) | Permanent Secretary | OCB | 2011-06-09 | AB Net Work Communication Ltd. | 13/09/2011 | 13/09/11 | 2 Wks | 4978500 | 7048070 | 4978500 | 2Wks | Completed
30 | Supply and Laying of Rugs and Fixing of Window Blinds | Ministry's Notice Board (August 24th, 2011) | Permanent Secretary | OCB | 2011-06-09 | Major Baja Ventures Ltd. | 2011-07-10 | 2011-07-10 | 1Wk | 578, 340.00 | 7048070 | 578, 340.00 | 1Wk | Completed
31 | Supply of Food Stuff to the Nigeria Farm Craft Centre for the Blind (NFCB) Isheri, Lagos | Ministry's Notice Board (August 24th, 2011)/National Dailies/Tender Journal | MTB Approval | OCB | 2011-06-09 | BEC Industrial Catering Company Nig. Ltd. | 19/09/2011 | 19/09/11 | 18 Wks | 8472418.38 | 25447944.39 | 8472418.38 | 18Wks | Completed
32 | Provision of Uniforms, Raincoats and Boots for Drivers, Cooks and Store Officers of the Ministry | Ministry's Notice Board (Sept. 5th, 2011) | Permanent Secretary | OCB | 2011-06-09 | Drisson Nig. Ltd. | 13/09/2011 | 13/09/11 | 3 Wks | 1398712 | 11,907.362.00 | 1398712 | 3Wks | Completed
33 | Supply of some Skill Acquisition Equipment to the Ministry's Shelter for Distress Women located at Kurudu, Abuja. | Ministry's Notice Board (August 24th, 2011) | Permanent Secretary | OCB | 2011-06-09 | Feli-Mich Nig. Ltd. | 2011-04-11 | 2011-04-11 | 2Wks | 2995676.25 | 5482652.84 | 2995676.25 | 2Wks | Completed
34 | Supply of 3Nos. Emergency Boat Ambulances with Basic Accessories for the Reduction of Maternal and Child Mortality in Riverine Areas of Nigeria |  | BPP No Objection | DP |  | M/s John Holt Plc. | 13/12/2011 | 13/12/11 | 2 Wks | 20900000 | 102118845 | 62700000 | 2Wks | Completed
180864260.71

## Sheet5 (hidden)
PROCUREMENT RECORDS
PROCUREMENT ENTITY (MDA):
FINANCIAL YEAR:2011
S/NO | CONTRACT DESCRIPTION | ADVERT DATE & MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | CONTRACTOR | DATE OF CONTRACT AWARD | DATE OF CONTRACT COMMEN CEMENT | CONTRACT PERIOD | CONTRACT VALUE (N) | BUDGETARY PROVISION (N) | AMOUNT PAID AS AT FEB. 2012. | EXPECTED COMPL. DATE | % OF COMPL. AS AT | REMARKS
1 | Acquisition of Fire Proof File Racks Cabinet for the Ministry`s Registries at Abuja, FCT | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | Angular Panel Nig. Ltd | 13/12/2011 | 15/12/2011 | 4 Weeks | 8400000 | 10035958 | 8400000 | 14/01/2012 | 100%
2 | Procure. & Installation of Fire Extinguishers & other Fire Accessories/Equipment for Brown, Green & Forestry Building & Special Climate Change Unit Building | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | HGR Nig. Ltd, | 13/12/2011 | 21/12/2011 | 4 Weeks | 4920000.75 | 5995893 | 4920000 | 20/01/2012 | 100%
3 | Purchase of Equipment for Survey of Soil Quality | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | Cingular Tech. Investment Ltd, | 13/12/2011 | 23/12/2011 | 4 Weeks | 10713150 | 10802832 | 10713150 | 22/01/2012 | 100%
4 | Procurement of Training Equipment | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | McQuintus Ltd, | 13/12/2011 | 23/12/2011 | 4 Weeks | 2507295 | 4051062 | 2507295 | 22/01/2012 | 100%
5 | Reh., Improvement & Equipment of the Dilapidated Accounts Office (Fed. Min. of Env., Hqtrs, 36 States & FCT Account Offices) | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | Cube Networks Engineering Ltd., | 13/12/2011 | 30/12/2011 | 4 Weeks | 17650500 | 44014161 | 17650500 | 28/01/2012 | 100%
6 | Renovation & Equipping of the Fed. Min. of Env. Staff Canteen at Green Building in Maitama & Brown Building on Independence Way, Central Business District in Abuja | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | Kesim Investment Ltd., | 13/12/2011 | 27/12/2011 | 4 Weeks | 21157010 | 25996721 | 21157010 | 26/01/2012 | 100%
7 | Renovation & Equipping of the Federal Ministry of Environment Staff Clinic at Green Building in Maitama along Aguiyi Ironsi Way, Abuja | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | XYZ Engineering Ltd., Suite | 13/12/2011 | 28/12/2011 | 4 Weeks | 4711844.7 | 5446248 | 4711844.7 | 27/01/2012 | 100%
8 | Egbe Erosion\Flood Control, Egbe Road, Ekiti State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Camel Construction Co. Ltd. | 23/12/2011 | 2011 | 6 Weeks | 13933670.33 | 17728532 | 2090050.59 | March, 2012 | 15% | New Project
9 | Erosion at Akama Oghe | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Enap Builders Nig. Ltd. | 23/12/2011 | 2011 | 6 Weeks | 18324012 | 20000000 | 2748601.03 | March, 2012 | 15% | "
10 | Jakara Erosion Control in Kano Municipal, Kano State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Tiamin Multi Service & Global Ltd. | 23/12/2011 | 2011 | 10 Weeks | 21290893.56 | 26592798 | 3193634.03 | March, 2012 | 15% | "
11 | Isinbode Erosion & Flood Control Project, Isinbode Ekiti East LGA, Ekiti State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Simdi West Africa Ltd. | 23/12/2011 | 2011 | 4 Weeks | 21730893.56 | 26592798 | 3259595 | March, 2012 | 15% | "
12 | Ayesan/Eyingu Road, Erosion & Flood Control Project in Ondo State | 22/08/2011.Daily Trust,The Nation& Federal Tenders Journal | MTB | NCB | 22/09/2011 | M/s Micheal Jacob Ltd. | 23/12/2011 | 2011 | 10 Weeks | 31204082.64 | 35457064 | 4680612.4 | March, 2012 | 15% | "

## FMWR
LIST OF CONTRACTS AWARDED IN YEAR 2011.
S/NO. | DATE | TITLE OF REPORT | NAME OF BENEFICIARY | CONTRACT SUM (N) | PURPOSE OF REPORT | PAR/DEPT.
1 | 2nd February, 2011 | Award of Contract for the Construction of Regional Water Quality Control Laboratories in the Six Geo-Political Zones. (a) LOT C1 - Sokoto (b) LOT C2 - Maiduguri | a)Messrs Barwa Engr. Coy. Ltd. b)Messrs b)Akhanaton Holding Ltd. | 472052491.6 | a) MTB Approval b)MTB Approval | a)WQ&S b)WQ&S
2 | 2nd February, 2011 | (c) LOT C3 - Makurdi (d) LOT C4 - Aba (e) LOT C5 - Port Harcourt (f) LOT C6 - Warri | c)Messrs Gabalen Nig. Ltd. d)Messrs Fordmark Int’l Services Ltd. e)Messrs Japollyn Nig. Ltd. f) Messrs Risken-Sero Nig. Ltd. | 940384211.15 | c)MTB Approval d)MTB Approval e)MTB Approval f)MTB Approval | c)WQ&S d)WQ&S e)WQ&S f)WQ&S
3 | 2nd February, 2011 | Award of Contract for the Construction of Wannune Earth Dam Project in Benue State. | Messrs Doliz Brown Group Ltd. | 867430352.25 | MTB Approval | DR&O
4 | 10th February, 2011 | Award of Contract for the Construction of Danmadi Erosion Control Project in Tambuwal Local Government Area of Sokoto State. | Messrs Dasna Int. Company Ltd. | 368917534.76 | MTB Approval | S.R RBDA
5 | 10th February, 2011 | Award of Contract for the Supply of Toyota Avensis 2.0 A/T Leather with Alloy Wheel. | Messrs Mandillas Ent. Ltd. | 6603975 | MTB Approval | WQC&S
6 | 2nd March 2011 | Award of Contract/Review of Contract for the Completion of Hadejia Valley Irrigation Project Phase 1, Stage 1, in Jigawa State | Messrs CGC Nig Ltd | 9661396999.52 | FEC of Wednesday, 3rd January 2011 | I&D
7 | 28th April, 2011 | Award of contract for the Construction of Water Supply Scheme at Asa Dam Area, Surulere L.G.A Oyo State. | Messrs Sabbyn Nig. Ltd. | 617899832.46 | MTB Approval | OORBDA
8 | 28th April, 2011 | Award of contract for the Extension of Engineering Supervision of Oyan Dam Rehabilitation works. | Messrs Yves Bee Nig. Ltd. | 14582423.08 | MTB Approval | Water Supply
9 | 28th April, 2011 | Award of contract for the Construction of Drainage and Farmland Reclamation (Lot C8) at the following locations: (a) Donga, Taraba State (b) Ilushi Ega, Edo State | a)Messrs A.G. Vision Consult Ltd. B)Messrs M. Jacobs | 478853705.44 | a)MTB Approval b)MTB Approval | a)I & D b)I & D
10 | 28th April, 2011 | (c) Agbarho, Delta State (d) Mamu-Awka, Anambra State (e) Koton Karfe, Kogi State. (f) Obinda, Benue State. | c)Messrs Mesom Inv. Ltd. d)Messrs Ebony Stack Nig. Ltd. e) Messrs Techno Int’l Co. Ltd. f) Messrs T.B. Marvin Int. Ltd. | 903732119.09 | c)MTB Approval d)MTB Approval e)MTB Approval f)MTB Approval | c) I & D d)I & D e)I & D f)I & D
11 | 28th April, 2011 | Award for the Construction of Small Earth Dams (Lot C9) at the following locations: (a) Upu-Itor Okete Dam, Benue State (b) Aloshi Earth Dam, Nasarawa State. (c) Rafin Soja Earth Dam, Taraba State. (d) Iyemero Earth Dam, Ekiti State. (e) Ayingba Earth Dam, Kogi State. | a)Messrs Viche Res. Nig. Ltd. b) Messrs Enatec Nig. Ltd. C) Messrs Badik Inter d) Messrs Intel Engr. Serv. Ltd. E) Messrs Omarc White Nig. Ltd. | 1762734246.9 | a) MTB Approval b) MTB Approval c) MTB Approval d) MTB Approval e) Step Down | a) DRO b) DRO c) DRO d) DRO e) DRO
12 | 28th April, 2011 | Award for the Supply of Goods for use in the Headquarters and Six Laboratories located in Minna, Akure, Lagos, Enugu, Gombe and Kano (Lot B1). | Messrs San Klau Nig. Ltd. | 20006175 | MTB Approval | WQ&S
13 | 28th April, 2011 | Award of contract for the Establishment of a Functional Library for FMWR. | Messrs Pee Why & Co. | 24314566.5 | MTB Approval | Ministry
14 | 28th April, 2011 | Award of contract for the Procurement of 6 Nos. Packaged Water Treatment Plant for East Bomo Community in Bayelsa State. | Messrs J. R. Gushing Wells Nig. Ltd. | 90211882.95 | MTB Approval | Water Supply
15 | 16th May, 2011 | Award of Contract for the Extension of Engineering Supervision of Oyan Dam Rehabilitation. | Messrs Yves Bee Nig. Ltd. | 13088653.85 | MTB Approval | I & D
16 | 16th May, 2011 | Award of Contract for the Construction of Drainage and Farmland Reclamation (Lot C8). (a) At Otueke Ogbia LGA Bayelsa State (b) At Peremabri Bayelsa State | Messrs Benham Construction Co. Ltd. B)Messrs 1st Project Perspective Ltd. | 515445547.35 | MTB Approval b)MTB Approval | I & D b)I & D
17 | 16th May, 2011 | Award of Contract for the Construction/Upgradding of Takum Regional Water Supply Project. | Messrs CGC Nig. Ltd. | 263388795.18 | MTB Approval | Water Supply
18 | 16th May, 2011 | Approval for Certification of “No Objection” for the Construction of Otueke Regional Water. | Messrs Nairda Ltd. | 4522845505 | Recommended to BPP. | Water Supply
19 | 16th May, 2011 | Award of Contract for the Construction of Okrika Water Supply Scheme. | Messrs Benham Construction Co. Ltd. | 830240136 | MTB Approval | Water Supply
20 | 16th May, 2011 | Award of for the EU Assisted Small Towns Water Supply and Sanitation Programme for Supply of Project Operational Vehicles. | Messrs R. T. Briscoe Nig. Ltd. | 32945000 | MTB Approved 5 Nos. Vehicles. | Water Supply
21 | 16th May, 2011 | Award of Contract for Direct Procurement and Installation of 1 No. 7000KVA Generator for the Ministry Headquarter. | Messrs Afri Med Nig. (Marapco) Ltd. | 26450000 | MTB APPROVAL Approved 7,000 KVA Capacity with wiring auditing. | Water Supply
22 | 16th May, 2011 | Award for the Consultancy Contract for Otueke Water Supply Scheme in Bayelsa State. | Messrs Fibow Petroleum and Environmental Eng. Consult. Ltd. | 42195300 | MTB Approval | Water Supply
23 | 1ST July 2011 | Award for the Consultancy Services for the Completion of Water House, Maitama, Abuja | Messrs Astrospaces Consultancy Ltd. | 66286265.79 | MTB APPROVAL | Water Supply
24 | 1ST July 2011 | Award for the Consultancy Service for the Construction Supervision of Tada Shonga Irrigation Project, Kwara State | Messrs TC-International Associates Limited | 79722000 | MTB APPROVAL | Lower Niger Basin Dev. Authority.
25 | 1ST July 2011 | Award for the Consultancy Services Contract for the Expansion of Abeokuta Old Water Supply Scheme in Ogun State | Messrs Sshwed Associates | 18744000 | MTB APPROVAL | Water Supply
26 | 1ST July 2011 | Award of Contract for supply of 10 Nos EZ570 EP/Printers | Messrs Vanatu Limited | 18595500 | MTB APPROVAL | Procurement
27 | 1ST July 2011 | Award of Contract for Supply and install combined system software to the Ministry | Messrs Data Miners Consult Ltd. | 18900000 | MTB APPROVAL | Procurement
28 | 1ST July 2011 | Award for the Consultancy Services for the Construction and upgrading of Takum Water Supply Scheme in Taraba State | Messrs Tecs Int’l Ltd. | 7974750 | MTB APPROVAL | Water Supply
29 | 1ST July 2011 | Award for the Consultancy Services for the Construction and upgrading of Okirika Water Supply Scheme in Rivers State | Messrs Waterpit Nig. Ltd. | 16464000 | MTB APPROVAL | Water Supply
30 | 1ST July 2011 | Award for the Consultancy Services for the Roadmap for Water Resources Development in Nigeria projects in Deep Well Areas of the country | Messrs BGL Plc. | 47368424 | MTB APPROVAL | DPRS
31 | 1ST July 2011 | Award of Contract for the Construction of the Extension of Head quarter’s Office for the Ministry to Messrs CGC Nig. Ltd. | Messrs CGC Nig. Ltd. | 365959911.5 | MTB APPROVAL | DHR
32 | 10Th August, 2011 | Award of Contract for the Variation Order No. 2 on the Construction of Mashi Earth Dam Project in Katsina State. | Messrs Abuhalawa International Ltd. | 54969193.13 | MTB APPROVAL | DRO
33 | 10th August, 2011 | Award of Contract for Ratification of Provisional Award for Pre-Contract Consulting Services for Oji River Regional Water Supply Scheme in Enugu State. | Messrs Chido-Amajuoyi and Partners Limited | 24247500 | MTB APPROVAL | Water Supply
34 | 10th August, 2011 | Award of Contract for Ratification of Contract award for the Supply of 1No. Toyota Landcruiser 4.7LVX V8, Leather Seats, Power Steering. | Messrs Kojo Motors Limited | 22863425 | MTB APPROVAL | Water Supply
35 | 10th August, 2011 | Award of Contract for the Procurement of 1 No. Toyota Prado, 3Nos. Toyota Avensus & 3Nos. Toyota Hilux for the Project Office to be attached to various Multilateral and Bilateral Projects under the Department. | Messrs Kojo Motors Limited | 60355325 | MTB APPROVAL | WQC&S
36 | 10th August, 2011 | Award for Ratification of Contract for the Production of Electronic Media Jingles on Presidential Summit/Launching of the Roadmap on Water Sector for the FMWR. | Messrs Pacesetters Communications Ltd. | 8800000 | MTB APPROVAL | PRS
37 | 4th November, 2011 | Award of Contract for the review of contract for Construction of the Dadin Kowa Dam and Irrigation Canal | Messrs C.G.C Nig. Ltd. | 971729142.72 | MTB APPROVAL | UBRBDA, YOLA
38 | 4th November, 2011 | Award of Contract for the Revalidation of the Due Process Certificate No BPP/S.I/VOL.V/08/352 for the award of the Construction of Mararaban Donga Earth Dam in Mararaban Donga, Donga LGA, Taraba State. | Messrs Gusarco Investment Co. Ltd. | 430917196.5 | MTB APPROVAL | UBRBDA, YOLA
39 | 4th November, 2011 | Award of Contract for the Construction of a Dam at Erio-Ekiti West LGA, Ekiti State. | Messrs Tripod Resources Ltd. | 576359536.32 | MTB APPROVAL | BORBDA, BENIN
40 | 4th November, 2011 | Award of Contract for the Construction of Erosion Control Works at Ajassor, Etung LGA, Cross River State. | Messrs Emostrade Nig. Ltd. | 287680396.5 | MTB APPROVAL | CRBDA
41 | 4th November, 2011 | Award of contract for the Construction of Mkpara Otop Flood and Erosion Control Project, Phase III, Odukpani LGA, Cross River State. | Messrs Zenith Construction Nig. Ltd. | 457172619.75 | MTB APPROVAL | CRBDA
42 | 4th November, 2011 | Award of Contract for the Extension of Services of Messrs Aim Consultants Ltd. for Consultancy Supervision of the Completion of Hadejia Valley Irrigation Project. | Messrs AIM Consultants Ltd. | 97713833.44 | MTB APPROVAL | I & D
43 | 4th November, 2011 | Award of contract for the construction of Small Earth Dam at Iwo LGA, Osun State. | Messrs Alimentari Limited | 416376160.2 | MTB APPROVAL | O-ORBDA
44 | 4th November, 2011 | Award of contract for the Construction of Panseke-Onikolobo Water Supply Scheme at Abeokuta LGA, Ogun State. | Messrs Vuylsteke Metallic Construction Limited | 383431551.3 | MTB APPROVAL | O-ORBDA
45 | 4th November, 2011 | Award of Contract for the Construction of Water Supply Scheme at Ibara-Onikoko at Abeokuta South LGA, Ogun State. | Messrs Vuylsteke Metallic Construction Limited | 391418297.79 | MTB APPROVAL | O-ORBDA
46 | 4th November, 2011 | Award of Contract for the Construction and Development of Okoo Integrated Farming Project in Oyo State. | Messrs Turning Point Engineering Limited. | 449323875 | MTB APPROVAL | UNRBDA
47 | 4th November, 2011 | Award of Contract for the Construction of Akaeze Dam and Irrigation Project under the 2011 appropriation Act of the Anambra Imo River Basin Development | Messrs Anbeez Services Company Ltd. | 370113660 | MTB APPROVAL | AIRBDA
48 | 4th November, 2011 | Award of contract for the Construction of Dugwaba Dam in Hong LGA, Adamawa State. | Messrs Quartz Solar Energy System Ltd. | 753753009.4 | MTB APPROVAL | UBRBDA
49 | 4th November, 2011 | Award of Contract for the Construction of 7500M Length Kiri Dam Irrigation Main Canal, Adamawa State. | Messrs Muslac Techno Co. Ltd. | 829425374.41 | MTB APPROVAL | UBRBDA
50 | 8th December, 2011 | Award of Contract for the Supply of 2Nos. Toyota Hilux (2.7) WTI Pick-up Double Cabin. | Messrs Elim Motors Limited | 10199700 | MTB APPROVAL | PRS
51 | 8th December, 2011 | Award of contract for the supply of 4Nos. Toyota Hilux Pick-up 4 x 4 Double Cabin. | Messrs Elizade Nig. Ltd. | 20400000 | MTB APPROVAL | FIN & ACCTS.
52 | 8th December, 2011 | Award of contract for the supply of 1No. Toyota Hilux Pick-up (2.7 LIT) 4x4 Double Cabin. | Messrs Elim Motors Ltd. | 5099850 | MTB APPROVAL | PRS
53 | 8th December, 2011 | Award of contract for the supply of 1No. 18 seater Hiace Toyota Bus Model LH222L-LEMDE 01 | Messrs Globe Motors Ltd. | 7689000 | MTB APPROVAL | HRM
54 | 8th December, 2011 | Award of contract for the construction of a small Hydro-Power Project at Owena Dam Ifedore L.G.A Ondo State. | Messrs Dtec Nigeria Limited | 404751861.36 | MTB APPROVAL | BORBDA
55 | 8th December, 2011 | Award of Contract for the Construction of Earth Dam in Garkawa, Plateau State. | Messrs Hajaig Construction Nig. Ltd. | 343817810.8 | MTB APPROVAL | LBRBDA
56 | 8th December, 2011 | Award of contract for the Construction of Tafki Sauri (Abdallawa) Dam, Kaita LGA, Katsina State. | Messrs Fabuzilo International Biz Ltd. | 471241853.34 | MTB APPROVAL | SRRBDA
57 | 8th December, 2011 | Award of Contract for Up-Grading of Consultancy Services for Construction Supervision of Office Extension Building. | Messrs Adoc Associate | 38668370.49 | MTB APPROVAL | HRM
58 | 8th December, 2011 | Award of contract to formulize Review Scope of Works in the Contract Awarded to Messrs Hippo Nig. Ltd. to Accommodate the Construction of additional 2Nos. Motorized Boreholes Schemes in Ebonyi State. | Messrs Hippo Nigeria Ltd. | 25365928.94 | MTB APPROVAL | WATER SUPPLY
59 | 13th December, 2011 | Award of Contract for the Construction of Cham Dam and Development of 100HA Irrig. At Cham, Balanga LGA Gombe State. | Messrs Ceylon Construction Serv. Ltd. | 832677743.05 | MTB APPROVAL | UBRBDA
60 | 13TH December, 2011 | Award of Contract for the Development of A Climate Change Information Model for the National Hydrological Area V. | Messrs Brisq Business Ltd. | 9623250 | MTB APPROVAL | Climate Change Unit
61 | 13th December, 2011 | Award of Contract for the Rehabilitation of Ojirami Dam Water Supply Scheme and Recticulation Network, Edo State | Messrs Ehibass Nig. Ltd. | 1129349399.4 | NOT PRESENTED | DAMS
62 | 13th December, 2011 | Award of Contract for the Construction of 15 Nos. Hand Pump Boreholes in Birnin Magaji, Zamfara State. | Messrs Yecko Nig. Ltd. | 46589754.02 | MTB APPROVAL | WATER SUPPLY
63 | 13th December, 2011 | Award of contract for the Construction of Gimi Earth Dam in Kaduna State. Revised Estimated Total Cost (RETC). | Messrs Construction Products Nig. Ltd. | 982,246,428,03 | MTB APPROVAL | DAMS
64 | 13th December, 2011 | Award of Contract for retainership of Messrs Strides Publication as Publication Consultant for the Ministry. | Messrs Strides Publication | 36418000 | Approved with provision for an MOU for the renewal as part of the agreement on annual basis. | LEGAL UNIT
65 | 13th December, 2011 | Award of Contract for the review of the Scope of Works in the Contract Awarded to Messrs Atlantic Drilling Fluid Services Co. Ltd. to accommodate the construction of additional 2 Nos. Motorised Boreholes Scheme in Gabasawa Township, Kano. | Messrs Atlantic Drilling Fluid Serv. Ltd. | 15270160 | MTB APPROVAL | WATER SUPPLY
66 | 23rd December, 2011 | Award of contract for the Supply and Installation of 60 Nos. of Fire Extinguisher (50kg DCP; Fireball) to the Ministry. | Messrs Press Field Communications | 2993697 | MTB APPROVAL | HRM
67 | 23rd December, 2011 | Award of Contract for the Termination of Contract for Construction of IVO River Dam Project in Enugu State. | Messrs D.A. Construction | 2143301160.6 | MTB APPROVAL | D&RO
68 | 23rd December, 2011 | Award of Contract for the Supervision of the Repairs of the Breached Section of the Emergency Spillway of Goronyo Dam. | Messrs Vibro Engineering Ltd. | 30399750.28 | MTB APPROVAL | D&RO
69 | 23rd December, 2011 | Award of Contract for the Rehabilitation of Ojirami Dam Water Supply Scheme and Reticulation Network in Edo State. | Messrs Atlantic Drilling Fluid Services Ltd. | 966661048.75 | MTB APPROVAL | WATER SUPPLY
70 | 23rd December, 2011 | Award of Contract for the Revised Estimated Total Project Cost of Completing Ukpilla Water Supply Project. | Messrs Rotary Group Ltd. | 789816713.76 | MTB APPROVAL | WATER SUPPLY
71 | 28th February, 2012 | Award of Contract for the Purchase of Project Vehicles. | Messrs Kojo Motors Ltd. | 14017500 | MTB APPROVAL | NWRI, KADUNA
72 | 28th February, 2012 | Award of Contract for the Direct Procurement of 6 Nos. Toyota Hilux 4x4WD D/C Pick-up and 2 Nos. Toyota Land Cruisers V8 Engine for the National Water Sanitation Programme | Messrs Elizade Motors Ltd. | 88460000 | MTB APPROVAL | WQC&S
73 | 28th February, 2012 | Award of Contract for Review of Price for the Construction of 5 Nos. Motorised Boreholes in Kogi East, Kogi State. | Messrs Hippo Nigerial Limited | 21668755.96 | MTB APPROVAL | WATER SUPPLY
74 | 9th March, 2012 | Award of Contract for the Rehabilitation of Ewohii Water Supply Scheme, Esan South-East L.G.A, Edo State. | Messrs Tomline Industrial Co. Ltd. | 503497417 | MTB APPROVAL | BORBDA
75 | 9th March, 2012 | Award of Contract for the Construction of Ella Water Supply Scheme, Esan-South East L.G.A of Edo State. | Messrs Belvine Ltd. | 507652897.5 | MTB APPROVAL | BORBDA
76 | 9th March, 2012 | Award of Contract for the Engagement of Consultancy Services for JICA Assisted Water Resources Master Plan Review Project. | Engr. Wakil Bukar | 6067672.8 | MTB APPROVAL | PRS
77 | 9th March, 2012 | Award of Contract for the Consultancy Services for Construction of Okrika Regional Water Supply Scheme. | Messrs PSE Consult | 79785000 | MTB APPROVAL | WATER SUPPLY
78 | 9th March, 2012 | Award of Contract for the Consultancy Services of Otueke Regional Water Supply Project. | Messrs Fibow Petroleum and Environmental Engr. Consult Limited | 55803500 | MTB APPROVAL | WATER SUPPLY
79 | 22nd March, 2012 | Award of Contract for the supply of 3 Nos. Nissan Pick-Up Cabin | Messrs Molach Nigeria Limited | 16005000 | MTB APPROVAL | PRS
80 | 22nd March, 2012 | Award of Contract for Clearance of Revised Estimated Total Cost (RETC) for the Execution of Contract Ceiling. | Messrs Cartlark International Limited | 53867435 | MTB APPROVAL | WATER SUPPLY
81 | 22nd March, 2012 | Award of Contract for the Reviser Estimated Total Cost of Federal University of Agriculture, Makurdi. | MessrsFravic Limited | 50664250 | MTB APPROVAL | WATER SUPPLY
38430208880.88

## ICPC
Independent Corrupt Practices and Other Related Offences Commission
INFORMATION ON CAPITAL PROCUREMENT FROM 1ST JANUARY -31ST DECEMBER, 2011
S/NO | CONTRACTOR | DATE OF CONTRACT AWARD | PROJECT DETAILS | UNIT PRICE | QUANTITY PRICE | REMARKS
I | Royas ventures Ltd | 2011-11-21 | Supply of 15 Nos. Board Room Chairs, Model NO:B9928(highest Grade)
|  |  | Supply of 200 Nos. Visitors Chairs with handle Model NO:6901C | 138862.5 | 2082937.5
–Supply of 3 sets of Visitors Waiting Chairs. Sample in Chairman’s Office.
II | White-Point Nig Ltd | 2011-11-21 | 1 No Conference Table with 14 chairs. Model- CT14 | 19687.5 | 3937500
Supply of 39 Nos. Executive Desks. Model NO: 1.8m sizeW1800xD900XH760mm
III |  |  | and 39 Nos. Executive Office Chairs -Model NO: 8821
| Anfani Integrated Services | 2011-11-21 |  | 190000 | 570000
Supply of 60 Nos. Air-Conditioners (Window)
|  |  | Panasonic 2 HP | 375000 | 375000
945000
Supply of 20 Nos. Air-Conditioners (split unit)
| Time –Limit Nig Ltd |  | Panasonic 2 HP
IV
|  | 2011-11-23 |  | 88412 | 3448.068
|  |  | Supply and Installation of 5 Nos. 5 ton package Air-conditioners, 5 Nos. at HQs . -Panasonic -5 ton package | 48412 | 1888068
5336136
Supply of 98 Nos Fans
| Strem Signage Ltd |  | KDK
V |  | 2011-11-21 | Supply of 8 Nos. Gubabi Fire proof safe. GBF 4x4 Drawers and 47 Nos.
|  |  | Office Filing Cabinet | 81240 | 4874400
4x4 Standard
Lysun Global Investment Ltd
2011-12-12
VI
|  |  |  | 108000 | 2160000
First City Engineering Ltd
2011-11-21
VII
378000
1890000
Clet & Cletta Nig Ltd
2011-12-06
VIII | Adekoi International
|  |  |  | 23800 | 2332400
| LTd | 2011-12-06
IX |  |  |  | 199500 | 1596000
|  |  |  | 22313 | 1048000
Computers
X | D-ApexTechnologies | 2011-11-23 | Provision of Branch Office LAN – for 7 State Offices(South), | 11504574 | 11504574
Provision of Branch Office LAN – for 7 State Offices(North),
xI | Datakums Ltd |  |  | 11091308 | 11091308
|  | 2011-11-23 | Provision of Remote Access and VPN
Electronic Document Management Software
|  |  |  | N5,823,750.00 | 5, 823,750.00
XII | Nu- Firma Ltd
|  | 2011-11-21 | Supply of 15 Nos. Desktop Computers
(3.2GHz, 4 GB , 500 GB , DVD\RW, , Win7, PRO, 20”TFT Flat Screen.
N6,693,000
|  |  | Supply of 27 Nos. Laptop Computers |  | 6693000
XIII | Jomed International Ltd | 2011-11-23 | HP Pavillion DM4-Inter Core 15-430M,( 2.26 GHz), 4 GB ,500 GB,DVD+/-RW 14” Screen, Wireless ,Webcam, Bluetooth, Finger Print , Wind 7.
Supply of 10 Nos. Scanners
| Digital Communication Konsult |  | (HP Scanjet -6350) | N142,080
XIV | Zinox Technologies Ltd | 2011-11-21 | Network document flatbed scanner | N213,135.16 | 2131200
5754649.32
XV
2011-11-21
Weco Systems International Ltd
N163,530
XVI
1635300
2011-11-21
|  |  | Computer Printers |  | 1811250
XVII |  |  | Supply of 60 Nos. Laserjet (Black &White. HP Laserjet 1566) | 30187.5
498750
| Task Systems Ltd | 2011-11-21 | And10 Nos. coloured) Printers
(HP Laserjet Pro Cp 1025n W)
49875
XVIII | Panabiz Nig Ltd | 21/11/11 | Photocopying Machines | N293,000 | 4981000
Supply of 17 Nos. Canon Photocopying Machines with speed limit of 20cpm
Features include :speed limit of 20cpm,
(A4 Size Copier/Printer,A4 Size Printing ,
25%-400% with Zoom,1x500 sheets,AVS13
Cassettes, Upgradable ,Metal Stand)
XIX | SCOA Nig Ltd |  | Power Generating Set
Supply 1 No. 40KVA Perkins (Sound Attenuated &
|  | 2011-11-21 | 100KVA Generators Perkins (Sound Attenuated , to be installed at the Lagos State Office).
|  |  |  | 5162000 | 5162000
ICPC Training Academy
XX | Artco Industries Ltd | 2011-11-21 | Supply of 4 Nos.Executive Office Chairs, Model No. 9929B
|  |  | 20 Nos. Visitors Chairs with Handle, -Model NO:9967B | 94080 | 376320
3 Nos. Visitors Waiting Chair, (Sample in Chairman’s Office)
|  |  | 4 Nos. Executive Desks, Model NO: 2.0m(SizeW2000x | 67200 | 1344000
D1000XH760mm
|  |  | 1 No. Conference Tables, Model NO:C1.SizeW6000xD2000XH760mm | 168000 | 504000
|  |  |  | 408800 | 1635200
Supply and Installation of 44 Nos. Air-Conditioners- (Split Unit) Panasonic 2 HP
|  |  | and 2 Nos. | 974400 | 974400
| Davoris Ltd |  | 5 ton package
Panasonic 5 tons (Installation at HQs)
XXI |  | 2011-11-21 |  | 95702.27 | 4210900
Supply & Installing of 700Sq M
|  |  | Window Blinds at the Academy,Keffi (vertical window blinds) | 391000 | 782000
Awa Royal Base Services Ltd
| Mango Investment Ltd |  | Supply of 44 Nos.Fans, KDK
XXII |  |  |  | 3281.25 | 2296875
|  | 2011-11-21 | 10 Nos Television with Blue gate Stabilizer . (Sony 32” x 300 LCD )with Blue gate Stabilizer
,10 Nos. Refrigerators, Thermocool ,one door-HR242)
10 Nos Water Dispenser,((Westpoin)t Shredding Machine.
XXIII |  |  | (Sanyo SBS610CC)
|  |  |  | 20000 | 880000
2011-11-21
| Warewater Ltd |  | Supply of 32 Nos. Beds (4x6)- with mattress-Mouka | 96000 | 960000
|  |  |  | 670000 | 670000
|  |  | Supply of 16 Nos. Reading Table . NAD 4 ft 001 Scratch Proof ,with Chair- D-017 | 330000 | 330000
| Chestino Investment Ltd |  | 16 Nos. Dressing table with Mirror, Drawers and stool,
2 Nos. Dining table with 8 dining Chairs,
|  |  |  | 16200 | 162000
8 Nos., Bathroom Mirror,
XXIV | Sougkata Enterprises Ltd
|  |  | Supply of 2Nos. Binding Machines .Unibind -XU 238 )with Accessories | 92812.5 | 2970000
2011-11-21
Messrs AKW
Engineering Ltd
XXV |  |  | 20 Nos. Office Filing Cabinet, 4x4 Standard
|  |  |  | 30800 | 492800
|  | 2011-11-21 | 8 Nos. Gubabi Safe GBF 4x4 Drawers | 70000 | 1120000
|  |  |  | 350000 | 700000
| Warewater Ltd |  | Supply of 160 Nos. Classroom Chairs, D-017 | 5600 | 44800
with writing Table -NAD 4 ft 001 Scratch Proof,
XXVI |  |  | Supply of 8 Nos. Photocopiers. :Copier with speed of up to 20cpm
Features include :speed limit of 20cpm,
| Panabiz International Ltd | 2011-11-21 | A4 Size Copier/Printer,A4 Size Printing ,
|  |  | 25%-400% with Zoom,1x500 sheets,AVS13 | 300000 | 600000
Cassettes, Upgradable ,Metal Stand
XXVII |  |  |  | 36750 | 735000
2011-11-21
Supply of 8 Nos. Desktop Computers.(3.2
| ICT Concept Ltd |  | GHz, 4 GB , 500 GB , DVD\RW, , Win7, PRO, 20”TFT Flat Screen) | 170625 | 1365000
Supply & Installation of 1 No. 500KVA Generator. Perkins ,Sound Attenuated
XVIII |  |  |  | 51250 | 8200000
2011-11-21
1 No. Box-light Multimedia Projector; Model X30N - 3000 Lumens with
| SCOA Nig Ltd |  | Trolleys; Projector Screen with 72x 72 Tripod Stand
; Projector Screen with 72x 72 Tripod
|  |  | Stand | 292876.26 | 2343010.06
XIX |  |  | 1 no. Lectern Public Address System (PAS), (PAS) with reading light ,Goose
neck mic and extra hand held
|  | 2011-11-21 | wireless mic, fully electric powered
| Mango Investment Ltd |  | 8 Nos. Rapido 4x6ft double-sided magnetic White Board, 4x8ft Pin(Notice) Board and
Flip chart Board with
Flip chart papers, Markers and
Board Cleaners.
8 Nos. Lectern (Rapido)
XXX |  |  |  | 158145.75 | 1265166
2011-11-21
|  |  |  | N16,656,000 | 16656000
XXXI
2011-11-21
XXXII |  |  |  | 326000
326000
2011-12-12
162000
162000
118025
944200
26000
208000
133559591.948

## NDLEA
PROCUREMENT RECORDS
PROCURING ENTITY (MDA): NATIONAL DRUG LAW ENFORCEMENT AGENCY
MINISTRY: JUSTICE
FINANCIAL YEAR: 2011
BASIC DATA | [5 empty] | CONTRACT AWARD | [5 empty] | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | ADVERTISEMENT DATE AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | CONTRACTOR | DATE OF CONTRACT AWARD | DATE OF CONTRACT COMENCEMENT | CONTRACT PERIOD | CONTRACT VALUE | BUDGETARY PROVITION (N) | AMOUNT PAID AS AT MARCH 2012 | EXPECTED COMPLETION DATE | % OF COMPLETION AS AT DEC. 2011 | REMARKS
1 | POWER GENERATING SET | Punch-26/07/11 & Daily Trust-27/07/11 | N250million | Competitive Bidding | 2011-05-10 | ROSSCOMM Nigeria Ltd | 2011-07-10 | 2011-10-10 | ON-GOING | 8426209 | 8426209 | 8426209 | DEC. 2011 | 100%
2 | SECURITY EQUIPMENT | Punch-26/07/11 & Daily Trust-27/07/12 | N250million | Competitive Bidding | 2011-05-10 | A & M Eko Nigeria Limited | 2011-07-10 | 2011-10-10 | ON-GOING | 15394036 | 15394036 | 11511635 | DEC. 2011 | 100%
3 | COMPLETION OF FENCING- IMO STATE COMMAND | Punch-26/07/11 & Daily Trust-27/07/13 | N250million | Competitive Bidding | 2011-05-10 | Inno Kenneth Nig. Co. Ltd. | 2011-07-10 | 2011-10-10 | ON-GOING | 10098434 | 10098434 | 0 | DEC. 2011 | 100% | NON RELEASE OF FUND
4 | RENOVATION OF ONDO STATE COMMAND | Punch-26/07/11 & Daily Trust-27/07/14 | N250million | Competitive Bidding | 2011-05-10 | Perfect Guide Venture Nig. Ltd. | 2011-07-10 | 2011-10-10 | ON-GOING | 10349113 | 10349113 | 10349113 | DEC. 2011 | 100%
5 | RENOVATION OF LAGOS STATE & MMIA COMMAND | Punch-26/07/11 & Daily Trust-27/07/15 | N250million | Competitive Bidding | 2011-05-10 | Bofab Nig. Ltd. | 2011-07-10 | 2011-10-10 | ON-GOING | 10802832 | 10802832 | 10802832 | DEC. 2011 | 100%
6 | COMPLETION OF FENCING- GOMBE STATE COMMAND | Punch-26/07/11 & Daily Trust-27/07/16 | N250million | Competitive Bidding | 2011-05-10 | Intertech Design Equip Affiliates Ltd. | 2011-07-10 | 2011-10-10 | ON-GOING | 10046634 | 10046634 | 10046634 | DEC. 2011 | 100%
7 | REHABILITATION OF ZAMFARA STATE COMMAND | Punch-26/07/11 & Daily Trust-27/07/17 | N250million | Competitive Bidding | 2011-05-10 | Danjiro Nig. Ltd. Danjiro Nig. Ltd. | 2011-07-10 | 2011-10-10 | ON-GOING | 10146309 | 10146309 | 10146309 | DEC. 2011 | 100%
8 | FENCING OF CROSS RIVER STATE COMMAND | Punch-26/07/11 & Daily Trust-27/07/18 | N250million | Competitive Bidding | 2011-05-10 | Emendi Associates Nige. Ltd. | 2011-07-10 | 2011-10-10 | ON-GOING | 9261214 | 9261214 | 0 | DEC. 2011 | 100% | NON RELEASE OF FUND
| TOTAL | [8 empty] | 84524781 | 84524781 | 61282732

## Summary
SUMMARY
LIST OF MDAs THAT HAVE SUBMITTED THEIR PROCUREMENT RECORD FOR YEAR 2011
SN | PARENT MINISTRY | SN | AGENCIES
1 | Education | 1 | Nigeria Arabic Language Village, Ngala
2 | Presidency | 2 | Economic and Financial Crime Commission
3 |  | 3 | Office of the Scretary to the Government of the Federation
4 |  | 4 | National Boundary Commission
5 |  | 5 | Office of the Head of Civil Service of the Federation
6 |  | 6 | Federal Civil Service Commission
|  | 7 | Infrastructure Concession Regulatory Commission
|  | 8 | Bureau of Public Procurement
|  | 9 | Code of Conduct Bureau
7 | Federal Ministry of Environment | 10 | Federal Ministry of Environment
8 | Ministry of Interior | 11 | Federal Road Safety Corps
9 |  | 12 | Nigeria Immigration Services
10 |  | 13 | Civil Defence, Fire, Immigration and Prisons Services Board
11 |  | 14 | Nigerian Prison Service
12 | Federal Ministry of National Planning | 15 | National Planning Commission
13 | Federal Ministry of Police Affairs | 16 | Nigeria Police Force
14 | Federal Ministry of Finance | 17 | Office of the Accountant-General of the Federation
15 | Federal Ministry of Health | 18 | Neuropsychiatric Hospital Aro beokuta
16 |  | 19 | Federal Medical Centre Bida
17 |  | 20 | Nnamdi Azikiwe University Teaching Hospital
18 |  | 21 | Federal Medical Centre Gusau
19 |  | 22 | Usman Danfodiyo University Teaching Hospital Sokoto
20 | Federal ministry of Information | 23 | Federal ministry of Information
21 | Federal Ministry of Agriculture and Rural Development | 24 | Federal Ministry of Agriculture and Rural Development
22 | Federal Ministry of Youth Development | 25 | National Youth Service Corps
23 | Feederal Ministry of Tourism, Culture and National Orientation | 26 | National Orientation Agency
|  | 27 | National Council For Arts and Culture
24 | Federal Ministry of works | 28 | Federal Ministry of works
25 | Federal Ministry of Mine & Steel | 29 | National Metallurgical Training Institute, Onitsha.
26 | Federal Ministry of Land,Housing & Uban Development | 30 | Federal Housing Authority
27 | Federal Ministry of Labour and Productivity | 31 | Labour and Productivity
28 | Federal Ministry Justice | 32 | Solicitor-General of The Federation and Permanent Secretary
29 | Federal Ministry of Transport | 33 | Council for the Regulation of Freight forwarding in Nigeria
30 | Federal Ministry of Women Affairs & Social Development | 34 | Federal Ministry of Women Affairs & Social Development
| National Drug Law Enforcement Agency | 35 | National Drug Law Enforcement Agency
| Independent Corrupt Practices and Other Related Offences Commission | 36 | Independent Corrupt Practices and Other Related Offences Commission
| Federal Ministry of Water Resources | 37 | Federal Ministry of Water Resources

## NSC
NIGERIAN SHIPPERS' COUNCIL:
FEDERAL MIN. OF TRANSPORT
| 2011 BUDGET YEAR | PROCUREMENT RECORDS
|  | BASIC DATA | [7 empty] | CONTRACT AWARD |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | ADVERTISEMENT DATE AND MEDIA | APPROVAL TRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | CONTRACTOR | DATE OF CONTRACT AWARD | DATE OF CONTRACT COMMENCEMENT | CONTRACT PERIOD | CONTRACT VALUE =N= | BUDGETARY PROVISION =N= | AMOUNT PAID AS AT 30th Dec, 2011 =N= | EXPECTED COMPLETION DATE | % OF COMPLETION AS AT 30th December, 2011 | REMARK
1 | Supply & Installation of hardware and software system | 18th May, 2011 | PTB | National Competitive bidding | 20th June, 2011 | Blessed Computers Sales & Repairs Ltd. | 2011-07-26 | 2011-07-29 | 2 weeks | 31873000 | 34706250 | NIL | 2011-09-02 | 75% | Contract yet to be paid for
2 | Supply of Project Vehicle: (2 nos Toyota Hiace 16 seaters bus and 1 no Toyota Corolla Saloon car) for Inland Container Depot. | 18th May, 2011 | PTB | National Competitive bidding | 20th June, 2011 | Kojo Motors Limited | 2011-07-26 | 2011-07-29 | 2 weeks | 16589471 | 17000000 | 16589471 | 2011-09-02 | 100% | Contract fully paid for
3 | Supply & Installation of hardware & Software System for Digitalization of Maritime Resources Library | 18th May, 2011 | PTB | National Competitive bidding | 20th June, 2011 | Information Access Ltd. | 2011-07-26 | 2011-08-03 | 2 weeks | 4780000 | 6800000 | NIL | 2011-09-02 | 90% | Payment yet to be effected
4 | Supply of Utility Vehicle 2011 models: 1 no Toyota coaster 30 seater bus, 1 no Toyota land cruiser VX, V8, 4.7ltr, 1 no Toyota prado VX. V6. 40 ltr engine. | 18th May, 2011 | MTB | National Competitive bidding | 20th June, 2011 | Elizade Nigeria Limited | 2011-07-26 | 2011-08-25 | 3 weeks | 95211000 | 97000000 | 95211000 | 2011-09-02 | 100% | Contract fully paid for
5 | Supply and Installation of 4 nos 27KVA (Sound Proof) and 12 nos 5KVA Generating Sets. | 18th May, 2011 | PTB | National Competitive bidding | 20th June, 2011 | Devine Power Products Ltd. | 2011-07-25 | 2011-07-29 | 90 days | 14000000 | 14000000 | NIL | 2011-11-30 | 100% | Payment yet to be effected
6 | Supply of Medical equipment (1 no sterilizer & 1 no Auto Clave. | 18th May, 2011 | PTB | National Competitive bidding | 20th June, 2011 | Ezegodsons International Nig. Ltd. | 2011-07-26 | 2011-07-29 | 2 weeks | 2850000 | 3000000 | 2850000 | 2011-09-02 | 100% | Contract fully paid for
7 | Supply of 1 no Medical Ambulance. | 18th May, 2011 | PTB | National Competitive bidding | 20th June, 2011 | Vic-Royal Medi. Ltd | 2011-07-26 | 2011-08-02 | 4 weeks | 8,750,215,.00 | 10000000 | NIL | 2011-09-02 | 100% | Payment yet to be effected
165303471

## CRFFN
PROCURING ENTITY (MDA) : |  | COUNCIL FOR THE REGULATION OF FREIGHT FORWARDING IN NIGERIA
MINISTRY :
FINANCIAL YEAR : |  | 2011
| BASIC DATA |  |  |  |  | CONTRACT AWARD | [5 empty] | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | ADVERTISEMENT DATE AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | CONTRACTOR | DATE OF CONTRACT AWARD | DATE OF CONTRACT COMMENCEMENT | CONTRACT PERIOD | CONTRACT VALUE (=N=) | BUDGETARY PROVISION (=N=) | AMOUNT PAID AS AT Dec. 2011 | EXPECTED COMPLETION DATE | PERCENTAGE OF COMPLETION AS AT January 2012 | REMARKS
1 | CONSULTANCY SERVICE FOR THE ESTABLISHMENT OF MICROFINANCE BANK | IOTH OCTOBER, 2011,DAILY TRUST, VANGUARD&FED. TENDER JOURNAL | CRFFN | COST AND QUALITY BASE SELECTION | OCT.24TH ,2011 | UNIS MULTILINKS INVESTMENTS LTD | DEC. 14TH, 2011 | DEC.15TH, 2011 | 3WEEKS | 33000000 | 35000000 | 29700000 | 2012-01-01 | 84.85% | N5,300,000 balance outstanding
2 | CONSULTANCY SERVICE FOR THE ESTABLISHMENT OF COOPERATIVE SOCIETY | IOTH OCTOBER, 2011,DAILY TRUST, VANGUARD&FED. TENDER JOURNAL | CRFFN | LEAST COST SELECTION | OCT.24TH ,2011 | UNIS MULTILINKS INVESTMENTS LTD | DEC. 14TH, 2011 | DEC.15TH, 2011 | 3WEEKS | 4800000 | 5000000 | - | 2012-01-01 | - | -
3 | PURCHASE OF COMPUTER AND COMPUTER EQUIPMENTS | 13TH OCTOBER,2011, VANGUARD, DAILY TRUST& FED. TENDER JOURNAL | CRFFN | NATIONAL COMPETITIVE BIDDING | OCT.13TH ,2011 | PILOT KIRK PROCUREMENT SERVICES LTD. | DEC. 14TH, 2011 | DEC. 15TH, 2011 | 3WEEKS | 5400000 | 5401416 | - | 2012-01-01 | - | -
4 | PURCHASE OF KITS FOR SECURITY PERSONNEL | 13TH OCTOBER,2011, VANGUARD, DAILY TRUST& FED. TENDER JOURNAL | CRFFN | NATIONAL COMPETITIVE BIDDING | OCT.13TH ,2011 | CAPITALWOOD INDUSTRIES LTD. | DEC. 14TH, 2011 | DEC. 15TH, 2011 | 3WEEKS | 3150000 | 5401416 | 3150000 | 2012-01-01 | 58.31% | N2,251,416 balance outstanding
5 | SUPPLY OF COMPUTER SOFTWARE | 13TH OCTOBER,2011, VANGUARD, DAILY TRUST& FED. TENDER JOURNAL | CRFFN | NATIONAL COMPETITIVE BIDDING | OCT.13TH ,2011 | YET TO BE AWARDED | YET TO BE AWARDED | DEC. 15TH, 2011 | 3WEEKS | 2700708 | 2700708 |  |  |  | Contract Awarded
6 | SUPPLY OF PRINTERS | 13TH OCTOBER,2011, VANGUARD, DAILY TRUST& FED. TENDER JOURNAL | CRFFN | NATIONAL COMPETITIVE BIDDING | OCT.13TH ,2011 | YET TO BE AWARDED | YET TO BE AWARDED | DEC. 15TH, 2011 | 3WEEKS | 3267857 | 3267857 |  |  |  | Contract Awarded
7 | SUPPLY OF UTILITY VEHICLES | 7TH NOVEMBER , 2011& DAILY TRUST , VANGUARD & FED. TENDER JOURNAL | CRFFN | NATIONAL COMPETITIVE BIDDING | DEC.19TH,2011 | PILOT KIRK PROCUREMENT SERVICES LTD. | DEC. 14TH, 2011 | DEC. 15TH, 2011 | 3WEEKS | 32178637.6 | 35757374 | 21150000 | 2012-01-01 | 59.15% | N14,607,374 balance outstanding
8 | PURCHASE OF PHOTOCOPYING MACHINES | N/A | CEO | NATIONAL SHOPPING | OCT.13TH ,2011 | AKIN SHARP SERVICES LTD. | DEC. 14TH, 2011 | DEC.15TH, 2011 | 3WEEKS | 1485389 | 1966010 | 1336850 | 2012-01-01 | 66.97% | N659,160 balance outstanding
28
29
30
31
32
33
34
35